## Summary
Meydenbauer VDC Phase 1 Data Package
101 Meydenbauer Condominiums - Building B Underground DWV Repipe
Project | 25-048
Schema | MEYD-VDC-001
Revision | VDC-P1-001
Coordinate contract | Scene is in imperial display units with one Blender unit treated as one foot.
Source SHA-256 | 1cb3a04f239e6f41acbe3d174f00b47c48df869d21f3e6196a12029f3263889e
VDC model SHA-256 | f51076ba34d85365ceb306f98ee3596e2986875ec9255aa003bfecaafc8d8ea9
Validation status | PASS
Model metrics |  | Phase register
Total model elements | 2980 | Phase | Name | Frame start | Frame end
Managed-scope elements | 753 | 01 | Existing + Investigation | 1 | 84
Context / visualization elements | 2227 | 02 | Staging + Fixture Removal | 85 | 168
Pipe routes | 66 | 03 | Demolition + Excavation | 169 | 252
Installation growth segments | 145 | 04 | New ABS Installation | 253 | 336
Hydrotest routes | 47 | 05 | Water Test | 337 | 420
Field verification items | 72 | 06 | Backfill + Slab Pourback | 421 | 504
Pipe routes with undocumented slope | 2 | 07 | Patching + Finishes | 505 | 588
|  | 08 | Fixture Reinstall + As-Built | 589 | 672
Validation checks
|  | Duplicate element IDs | 0
|  | Missing required properties | 0
|  | Managed scope missing fields | 0
|  | Pipe routes missing diameter | 0
|  | Unresolved parent routes | 0
|  | Core model changes | 0
|  | Render pixel difference | 0
Open data items
EX_Side_Sewer_Main_8in | Slope not documented; do not infer without field/design confirmation.
NEW_ABS_B103_4in_RAISED_FLOOR | Slope not documented; do not infer without field/design confirmation.

## Element_Register
element_id | name | type | collections | classification_collection | unit | level | discipline | system | status | phase_id | phase_name | phase_frame_start | phase_frame_end | component_type | route_role | model_state | animation_role | source | verification_status | cost_code | cost_code_status | lod | managed_scope | quantity_type | quantity_value | quantity_unit | quantity_basis | nominal_diameter_in | slope_in_per_ft | slope_status | parent_route_name | parent_route_id | material | world_dx_ft | world_dy_ft | world_dz_ft
ARC-B101-CTX-CTX-0001 | CTX_B101_STACK_3inA | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | B101 | L1 | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01 stack note: 4x4in + 8x3in apparent stacks | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED | 3 |  | NA |  |  | ANIM_GhostWalls_MAT_Existing_CastIron_Rust | 0.2917 | 0.2917 | 27
ARC-B101-CTX-CTX-0002 | CTX_B101_STACK_3inB | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | B101 | L1 | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01 stack note: 4x4in + 8x3in apparent stacks | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED | 3 |  | NA |  |  | ANIM_GhostWalls_MAT_Existing_CastIron_Rust | 0.2917 | 0.2917 | 27
ARC-B101-CTX-CTX-0003 | CTX_B101_STACK_4in | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | B101 | L1 | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01 stack note: 4x4in + 8x3in apparent stacks | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED | 4 |  | NA |  |  | ANIM_GhostWalls_MAT_Existing_CastIron_Rust | 0.375 | 0.375 | 27
ARC-B102-CTX-CTX-0001 | CTX_B102_STACK_3inA | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | B102 | L1 | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01 stack note: 4x4in + 8x3in apparent stacks | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED | 3 |  | NA |  |  | ANIM_GhostWalls_MAT_Existing_CastIron_Rust | 0.2917 | 0.2917 | 27
ARC-B102-CTX-CTX-0002 | CTX_B102_STACK_3inB | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | B102 | L1 | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01 stack note: 4x4in + 8x3in apparent stacks | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED | 3 |  | NA |  |  | ANIM_GhostWalls_MAT_Existing_CastIron_Rust | 0.2917 | 0.2917 | 27
ARC-B102-CTX-CTX-0003 | CTX_B102_STACK_4in | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | B102 | L1 | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01 stack note: 4x4in + 8x3in apparent stacks | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED | 4 |  | NA |  |  | ANIM_GhostWalls_MAT_Existing_CastIron_Rust | 0.375 | 0.375 | 27
ARC-B103-CTX-CTX-0001 | CTX_B103_STACK_3inA | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | B103 | L1 | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01 stack note: 4x4in + 8x3in apparent stacks | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED | 3 |  | NA |  |  | ANIM_GhostWalls_MAT_Existing_CastIron_Rust | 0.2917 | 0.2917 | 27
ARC-B103-CTX-CTX-0002 | CTX_B103_STACK_3inB | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | B103 | L1 | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01 stack note: 4x4in + 8x3in apparent stacks | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED | 3 |  | NA |  |  | ANIM_GhostWalls_MAT_Existing_CastIron_Rust | 0.2917 | 0.2917 | 27
ARC-B103-CTX-CTX-0003 | CTX_B103_STACK_4in | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | B103 | L1 | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01 stack note: 4x4in + 8x3in apparent stacks | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED | 4 |  | NA |  |  | ANIM_GhostWalls_MAT_Existing_CastIron_Rust | 0.375 | 0.375 | 27
ARC-B104-CTX-CTX-0001 | CTX_B104_STACK_3inA | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | B104 | L1 | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01 stack note: 4x4in + 8x3in apparent stacks | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED | 3 |  | NA |  |  | ANIM_GhostWalls_MAT_Existing_CastIron_Rust | 0.2917 | 0.2917 | 27
ARC-B104-CTX-CTX-0002 | CTX_B104_STACK_3inB | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | B104 | L1 | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01 stack note: 4x4in + 8x3in apparent stacks | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED | 3 |  | NA |  |  | ANIM_GhostWalls_MAT_Existing_CastIron_Rust | 0.2917 | 0.2917 | 27
ARC-B104-CTX-CTX-0003 | CTX_B104_STACK_4in | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | B104 | L1 | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01 stack note: 4x4in + 8x3in apparent stacks | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED | 4 |  | NA |  |  | ANIM_GhostWalls_MAT_Existing_CastIron_Rust | 0.375 | 0.375 | 27
ARC-SITE-CTX-CTX-0001 | Air conditioner horizontal grille | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Anodized dark bronze aluminum | 1.85 | 0.06 | 0.045
ARC-SITE-CTX-CTX-0002 | Air conditioner horizontal grille.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Anodized dark bronze aluminum | 1.85 | 0.06 | 0.045
ARC-SITE-CTX-CTX-0003 | Air conditioner horizontal grille.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Anodized dark bronze aluminum | 1.85 | 0.06 | 0.045
ARC-SITE-CTX-CTX-0004 | Air conditioner horizontal grille.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Anodized dark bronze aluminum | 1.85 | 0.06 | 0.045
ARC-SITE-CTX-CTX-0005 | Air conditioner horizontal grille.004 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Anodized dark bronze aluminum | 1.85 | 0.06 | 0.045
ARC-SITE-CTX-CTX-0006 | Air conditioner horizontal grille.005 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Anodized dark bronze aluminum | 1.85 | 0.06 | 0.045
ARC-SITE-CTX-CTX-0007 | Air conditioner horizontal grille.006 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Anodized dark bronze aluminum | 1.85 | 0.06 | 0.045
ARC-SITE-CTX-CTX-0008 | Air conditioner horizontal grille.007 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Anodized dark bronze aluminum | 1.85 | 0.06 | 0.045
ARC-SITE-CTX-CTX-0009 | Air conditioner horizontal grille.008 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Anodized dark bronze aluminum | 1.85 | 0.06 | 0.045
ARC-SITE-CTX-CTX-0010 | Balcony edge slab | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Board-formed architectural concrete | 27 | 4.8 | 0.48
ARC-SITE-CTX-CTX-0011 | Balcony edge slab.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Board-formed architectural concrete | 27 | 4.8 | 0.48
ARC-SITE-CTX-CTX-0012 | Balcony edge slab.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Board-formed architectural concrete | 27 | 4.8 | 0.48
ARC-SITE-CTX-CTX-0013 | Balcony edge slab.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Board-formed architectural concrete | 27 | 4.8 | 0.48
ARC-SITE-CTX-CTX-0014 | Balcony edge slab.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Board-formed architectural concrete | 27 | 4.8 | 0.48
ARC-SITE-CTX-CTX-0015 | Balcony edge slab.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Board-formed architectural concrete | 27 | 4.8 | 0.48
ARC-SITE-CTX-CTX-0016 | Balcony guardrail bottom | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 26.3 | 0.09 | 0.09
ARC-SITE-CTX-CTX-0017 | Balcony guardrail bottom.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 26.3 | 0.09 | 0.09
ARC-SITE-CTX-CTX-0018 | Balcony guardrail bottom.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 26.3 | 0.09 | 0.09
ARC-SITE-CTX-CTX-0019 | Balcony guardrail bottom.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 26.3 | 0.09 | 0.09
ARC-SITE-CTX-CTX-0020 | Balcony guardrail bottom.004 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 26.3 | 0.09 | 0.09
ARC-SITE-CTX-CTX-0021 | Balcony guardrail bottom.005 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 26.3 | 0.09 | 0.09
ARC-SITE-CTX-CTX-0022 | Balcony guardrail picket | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0023 | Balcony guardrail picket.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0024 | Balcony guardrail picket.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0025 | Balcony guardrail picket.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0026 | Balcony guardrail picket.004 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0027 | Balcony guardrail picket.005 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0028 | Balcony guardrail picket.006 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0029 | Balcony guardrail picket.007 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0030 | Balcony guardrail picket.008 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0031 | Balcony guardrail picket.009 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0032 | Balcony guardrail picket.010 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0033 | Balcony guardrail picket.011 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0034 | Balcony guardrail picket.012 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0035 | Balcony guardrail picket.013 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0036 | Balcony guardrail picket.014 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0037 | Balcony guardrail picket.015 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0038 | Balcony guardrail picket.016 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0039 | Balcony guardrail picket.017 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0040 | Balcony guardrail picket.018 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0041 | Balcony guardrail picket.019 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0042 | Balcony guardrail picket.020 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0043 | Balcony guardrail picket.021 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0044 | Balcony guardrail picket.022 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0045 | Balcony guardrail picket.023 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0046 | Balcony guardrail picket.024 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0047 | Balcony guardrail picket.025 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0048 | Balcony guardrail picket.026 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0049 | Balcony guardrail picket.027 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0050 | Balcony guardrail picket.028 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0051 | Balcony guardrail picket.029 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0052 | Balcony guardrail picket.030 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0053 | Balcony guardrail picket.031 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0054 | Balcony guardrail picket.032 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0055 | Balcony guardrail picket.033 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0056 | Balcony guardrail picket.034 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0057 | Balcony guardrail picket.035 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0058 | Balcony guardrail picket.036 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0059 | Balcony guardrail picket.037 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0060 | Balcony guardrail picket.038 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0061 | Balcony guardrail picket.039 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0062 | Balcony guardrail picket.040 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0063 | Balcony guardrail picket.041 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0064 | Balcony guardrail picket.042 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0065 | Balcony guardrail picket.043 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0066 | Balcony guardrail picket.044 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0067 | Balcony guardrail picket.045 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0068 | Balcony guardrail picket.046 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0069 | Balcony guardrail picket.047 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0070 | Balcony guardrail picket.048 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0071 | Balcony guardrail picket.049 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0072 | Balcony guardrail picket.050 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0073 | Balcony guardrail picket.051 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0074 | Balcony guardrail picket.052 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0075 | Balcony guardrail picket.053 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0076 | Balcony guardrail picket.054 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0077 | Balcony guardrail picket.055 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0078 | Balcony guardrail picket.056 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0079 | Balcony guardrail picket.057 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0080 | Balcony guardrail picket.058 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0081 | Balcony guardrail picket.059 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0082 | Balcony guardrail picket.060 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0083 | Balcony guardrail picket.061 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0084 | Balcony guardrail picket.062 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0085 | Balcony guardrail picket.063 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0086 | Balcony guardrail picket.064 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0087 | Balcony guardrail picket.065 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0088 | Balcony guardrail picket.066 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0089 | Balcony guardrail picket.067 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0090 | Balcony guardrail picket.068 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0091 | Balcony guardrail picket.069 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0092 | Balcony guardrail picket.070 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0093 | Balcony guardrail picket.071 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0094 | Balcony guardrail picket.072 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0095 | Balcony guardrail picket.073 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0096 | Balcony guardrail picket.074 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0097 | Balcony guardrail picket.075 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0098 | Balcony guardrail picket.076 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0099 | Balcony guardrail picket.077 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0100 | Balcony guardrail picket.078 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0101 | Balcony guardrail picket.079 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0102 | Balcony guardrail picket.080 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0103 | Balcony guardrail picket.081 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0104 | Balcony guardrail picket.082 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0105 | Balcony guardrail picket.083 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0106 | Balcony guardrail picket.084 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0107 | Balcony guardrail picket.085 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0108 | Balcony guardrail picket.086 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0109 | Balcony guardrail picket.087 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0110 | Balcony guardrail picket.088 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0111 | Balcony guardrail picket.089 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0112 | Balcony guardrail picket.090 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0113 | Balcony guardrail picket.091 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0114 | Balcony guardrail picket.092 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0115 | Balcony guardrail picket.093 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0116 | Balcony guardrail picket.094 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0117 | Balcony guardrail picket.095 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0118 | Balcony guardrail picket.096 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0119 | Balcony guardrail picket.097 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0120 | Balcony guardrail picket.098 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0121 | Balcony guardrail picket.099 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0122 | Balcony guardrail picket.100 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0123 | Balcony guardrail picket.101 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0124 | Balcony guardrail picket.102 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0125 | Balcony guardrail picket.103 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0126 | Balcony guardrail picket.104 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0127 | Balcony guardrail picket.105 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0128 | Balcony guardrail picket.106 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0129 | Balcony guardrail picket.107 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0130 | Balcony guardrail picket.108 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0131 | Balcony guardrail picket.109 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0132 | Balcony guardrail picket.110 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0133 | Balcony guardrail picket.111 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0134 | Balcony guardrail picket.112 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0135 | Balcony guardrail picket.113 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0136 | Balcony guardrail picket.114 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0137 | Balcony guardrail picket.115 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0138 | Balcony guardrail picket.116 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0139 | Balcony guardrail picket.117 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0140 | Balcony guardrail picket.118 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0141 | Balcony guardrail picket.119 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0142 | Balcony guardrail picket.120 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0143 | Balcony guardrail picket.121 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0144 | Balcony guardrail picket.122 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0145 | Balcony guardrail picket.123 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0146 | Balcony guardrail picket.124 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0147 | Balcony guardrail picket.125 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0148 | Balcony guardrail picket.126 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0149 | Balcony guardrail picket.127 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0150 | Balcony guardrail picket.128 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0151 | Balcony guardrail picket.129 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0152 | Balcony guardrail picket.130 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0153 | Balcony guardrail picket.131 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0154 | Balcony guardrail picket.132 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0155 | Balcony guardrail picket.133 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0156 | Balcony guardrail picket.134 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0157 | Balcony guardrail picket.135 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0158 | Balcony guardrail picket.136 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0159 | Balcony guardrail picket.137 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0160 | Balcony guardrail picket.138 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0161 | Balcony guardrail picket.139 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0162 | Balcony guardrail picket.140 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0163 | Balcony guardrail picket.141 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0164 | Balcony guardrail picket.142 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0165 | Balcony guardrail picket.143 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0166 | Balcony guardrail picket.144 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0167 | Balcony guardrail picket.145 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0168 | Balcony guardrail picket.146 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0169 | Balcony guardrail picket.147 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0170 | Balcony guardrail picket.148 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0171 | Balcony guardrail picket.149 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0172 | Balcony guardrail picket.150 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0173 | Balcony guardrail picket.151 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0174 | Balcony guardrail picket.152 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0175 | Balcony guardrail picket.153 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0176 | Balcony guardrail picket.154 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0177 | Balcony guardrail picket.155 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0178 | Balcony guardrail picket.156 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0179 | Balcony guardrail picket.157 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0180 | Balcony guardrail picket.158 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0181 | Balcony guardrail picket.159 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0182 | Balcony guardrail picket.160 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0183 | Balcony guardrail picket.161 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0184 | Balcony guardrail picket.162 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0185 | Balcony guardrail picket.163 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0186 | Balcony guardrail picket.164 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0187 | Balcony guardrail picket.165 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0188 | Balcony guardrail picket.166 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0189 | Balcony guardrail picket.167 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0190 | Balcony guardrail picket.168 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0191 | Balcony guardrail picket.169 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0192 | Balcony guardrail picket.170 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0193 | Balcony guardrail picket.171 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0194 | Balcony guardrail picket.172 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0195 | Balcony guardrail picket.173 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0196 | Balcony guardrail picket.174 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0197 | Balcony guardrail picket.175 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0198 | Balcony guardrail picket.176 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0199 | Balcony guardrail picket.177 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0200 | Balcony guardrail picket.178 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0201 | Balcony guardrail picket.179 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0202 | Balcony guardrail picket.180 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0203 | Balcony guardrail picket.181 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0204 | Balcony guardrail picket.182 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0205 | Balcony guardrail picket.183 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0206 | Balcony guardrail picket.184 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0207 | Balcony guardrail picket.185 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0208 | Balcony guardrail picket.186 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0209 | Balcony guardrail picket.187 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0210 | Balcony guardrail picket.188 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0211 | Balcony guardrail picket.189 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0212 | Balcony guardrail picket.190 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0213 | Balcony guardrail picket.191 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0214 | Balcony guardrail picket.192 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0215 | Balcony guardrail picket.193 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0216 | Balcony guardrail picket.194 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0217 | Balcony guardrail picket.195 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0218 | Balcony guardrail picket.196 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0219 | Balcony guardrail picket.197 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0220 | Balcony guardrail picket.198 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0221 | Balcony guardrail picket.199 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0222 | Balcony guardrail picket.200 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0223 | Balcony guardrail picket.201 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0224 | Balcony guardrail picket.202 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0225 | Balcony guardrail picket.203 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0226 | Balcony guardrail picket.204 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0227 | Balcony guardrail picket.205 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0228 | Balcony guardrail picket.206 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0229 | Balcony guardrail picket.207 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0230 | Balcony guardrail picket.208 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0231 | Balcony guardrail picket.209 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0232 | Balcony guardrail picket.210 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0233 | Balcony guardrail picket.211 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0234 | Balcony guardrail picket.212 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0235 | Balcony guardrail picket.213 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0236 | Balcony guardrail picket.214 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0237 | Balcony guardrail picket.215 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0238 | Balcony guardrail picket.216 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0239 | Balcony guardrail picket.217 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0240 | Balcony guardrail picket.218 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0241 | Balcony guardrail picket.219 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0242 | Balcony guardrail picket.220 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0243 | Balcony guardrail picket.221 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0244 | Balcony guardrail picket.222 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0245 | Balcony guardrail picket.223 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0246 | Balcony guardrail picket.224 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0247 | Balcony guardrail picket.225 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0248 | Balcony guardrail picket.226 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0249 | Balcony guardrail picket.227 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0250 | Balcony guardrail picket.228 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0251 | Balcony guardrail picket.229 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0252 | Balcony guardrail picket.230 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0253 | Balcony guardrail picket.231 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0254 | Balcony guardrail picket.232 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0255 | Balcony guardrail picket.233 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0256 | Balcony guardrail picket.234 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0257 | Balcony guardrail picket.235 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0258 | Balcony guardrail picket.236 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0259 | Balcony guardrail picket.237 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0260 | Balcony guardrail picket.238 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0261 | Balcony guardrail picket.239 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0262 | Balcony guardrail picket.240 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0263 | Balcony guardrail picket.241 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0264 | Balcony guardrail picket.242 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0265 | Balcony guardrail picket.243 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0266 | Balcony guardrail picket.244 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0267 | Balcony guardrail picket.245 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0268 | Balcony guardrail picket.246 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0269 | Balcony guardrail picket.247 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0270 | Balcony guardrail picket.248 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0271 | Balcony guardrail picket.249 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0272 | Balcony guardrail picket.250 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0273 | Balcony guardrail picket.251 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0274 | Balcony guardrail picket.252 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0275 | Balcony guardrail picket.253 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0276 | Balcony guardrail picket.254 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0277 | Balcony guardrail picket.255 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0278 | Balcony guardrail picket.256 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0279 | Balcony guardrail picket.257 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0280 | Balcony guardrail picket.258 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0281 | Balcony guardrail picket.259 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0282 | Balcony guardrail picket.260 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0283 | Balcony guardrail picket.261 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0284 | Balcony guardrail picket.262 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0285 | Balcony guardrail picket.263 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0286 | Balcony guardrail picket.264 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0287 | Balcony guardrail picket.265 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0288 | Balcony guardrail picket.266 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0289 | Balcony guardrail picket.267 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0290 | Balcony guardrail picket.268 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0291 | Balcony guardrail picket.269 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0292 | Balcony guardrail picket.270 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0293 | Balcony guardrail picket.271 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0294 | Balcony guardrail picket.272 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0295 | Balcony guardrail picket.273 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0296 | Balcony guardrail picket.274 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0297 | Balcony guardrail picket.275 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0298 | Balcony guardrail picket.276 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0299 | Balcony guardrail picket.277 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0300 | Balcony guardrail picket.278 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0301 | Balcony guardrail picket.279 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0302 | Balcony guardrail picket.280 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0303 | Balcony guardrail picket.281 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0304 | Balcony guardrail picket.282 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0305 | Balcony guardrail picket.283 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0306 | Balcony guardrail picket.284 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0307 | Balcony guardrail picket.285 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0308 | Balcony guardrail picket.286 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0309 | Balcony guardrail picket.287 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0310 | Balcony guardrail picket.288 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0311 | Balcony guardrail picket.289 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0312 | Balcony guardrail picket.290 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0313 | Balcony guardrail picket.291 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0314 | Balcony guardrail picket.292 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0315 | Balcony guardrail picket.293 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0316 | Balcony guardrail picket.294 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0317 | Balcony guardrail picket.295 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0318 | Balcony guardrail picket.296 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0319 | Balcony guardrail picket.297 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0320 | Balcony guardrail picket.298 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0321 | Balcony guardrail picket.299 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0322 | Balcony guardrail picket.300 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0323 | Balcony guardrail picket.301 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0324 | Balcony guardrail picket.302 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0325 | Balcony guardrail picket.303 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0326 | Balcony guardrail picket.304 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0327 | Balcony guardrail picket.305 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0328 | Balcony guardrail picket.306 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0329 | Balcony guardrail picket.307 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0330 | Balcony guardrail picket.308 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0331 | Balcony guardrail picket.309 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0332 | Balcony guardrail picket.310 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0333 | Balcony guardrail picket.311 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0334 | Balcony guardrail picket.312 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0335 | Balcony guardrail picket.313 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0336 | Balcony guardrail picket.314 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0337 | Balcony guardrail picket.315 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0338 | Balcony guardrail picket.316 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0339 | Balcony guardrail picket.317 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0340 | Balcony guardrail picket.318 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0341 | Balcony guardrail picket.319 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0342 | Balcony guardrail picket.320 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0343 | Balcony guardrail picket.321 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0344 | Balcony guardrail picket.322 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0345 | Balcony guardrail picket.323 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0346 | Balcony guardrail picket.324 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0347 | Balcony guardrail picket.325 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0348 | Balcony guardrail picket.326 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0349 | Balcony guardrail picket.327 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0350 | Balcony guardrail picket.328 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0351 | Balcony guardrail picket.329 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0352 | Balcony guardrail picket.330 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0353 | Balcony guardrail picket.331 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0354 | Balcony guardrail picket.332 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0355 | Balcony guardrail picket.333 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0356 | Balcony guardrail picket.334 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0357 | Balcony guardrail picket.335 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0358 | Balcony guardrail picket.336 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0359 | Balcony guardrail picket.337 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0360 | Balcony guardrail picket.338 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0361 | Balcony guardrail picket.339 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0362 | Balcony guardrail picket.340 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0363 | Balcony guardrail picket.341 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0364 | Balcony guardrail picket.342 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0365 | Balcony guardrail picket.343 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0366 | Balcony guardrail picket.344 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0367 | Balcony guardrail picket.345 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0368 | Balcony guardrail picket.346 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0369 | Balcony guardrail picket.347 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0370 | Balcony guardrail picket.348 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0371 | Balcony guardrail picket.349 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0372 | Balcony guardrail picket.350 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0373 | Balcony guardrail picket.351 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0374 | Balcony guardrail picket.352 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0375 | Balcony guardrail picket.353 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0376 | Balcony guardrail picket.354 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0377 | Balcony guardrail picket.355 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0378 | Balcony guardrail picket.356 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0379 | Balcony guardrail picket.357 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0380 | Balcony guardrail picket.358 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0381 | Balcony guardrail picket.359 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0382 | Balcony guardrail picket.360 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0383 | Balcony guardrail picket.361 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0384 | Balcony guardrail picket.362 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0385 | Balcony guardrail picket.363 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0386 | Balcony guardrail picket.364 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0387 | Balcony guardrail picket.365 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0388 | Balcony guardrail picket.366 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0389 | Balcony guardrail picket.367 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0390 | Balcony guardrail picket.368 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0391 | Balcony guardrail picket.369 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0392 | Balcony guardrail picket.370 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0393 | Balcony guardrail picket.371 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0394 | Balcony guardrail picket.372 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0395 | Balcony guardrail picket.373 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0396 | Balcony guardrail picket.374 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0397 | Balcony guardrail picket.375 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0398 | Balcony guardrail picket.376 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0399 | Balcony guardrail picket.377 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0400 | Balcony guardrail picket.378 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0401 | Balcony guardrail picket.379 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0402 | Balcony guardrail picket.380 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0403 | Balcony guardrail picket.381 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0404 | Balcony guardrail picket.382 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0405 | Balcony guardrail picket.383 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0406 | Balcony guardrail picket.384 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0407 | Balcony guardrail picket.385 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0408 | Balcony guardrail picket.386 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0409 | Balcony guardrail picket.387 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0410 | Balcony guardrail picket.388 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0411 | Balcony guardrail picket.389 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0412 | Balcony guardrail picket.390 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0413 | Balcony guardrail picket.391 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0414 | Balcony guardrail picket.392 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0415 | Balcony guardrail picket.393 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0416 | Balcony guardrail picket.394 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0417 | Balcony guardrail picket.395 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0418 | Balcony guardrail picket.396 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0419 | Balcony guardrail picket.397 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0420 | Balcony guardrail picket.398 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0421 | Balcony guardrail picket.399 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0422 | Balcony guardrail picket.400 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0423 | Balcony guardrail picket.401 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0424 | Balcony guardrail picket.402 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0425 | Balcony guardrail picket.403 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0426 | Balcony guardrail picket.404 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0427 | Balcony guardrail picket.405 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0428 | Balcony guardrail picket.406 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0429 | Balcony guardrail picket.407 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0430 | Balcony guardrail picket.408 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0431 | Balcony guardrail picket.409 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0432 | Balcony guardrail picket.410 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0433 | Balcony guardrail picket.411 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0434 | Balcony guardrail picket.412 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0435 | Balcony guardrail picket.413 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0436 | Balcony guardrail picket.414 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0437 | Balcony guardrail picket.415 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0438 | Balcony guardrail picket.416 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0439 | Balcony guardrail picket.417 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0440 | Balcony guardrail picket.418 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0441 | Balcony guardrail picket.419 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0442 | Balcony guardrail picket.420 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0443 | Balcony guardrail picket.421 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0444 | Balcony guardrail picket.422 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0445 | Balcony guardrail picket.423 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0446 | Balcony guardrail picket.424 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0447 | Balcony guardrail picket.425 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0448 | Balcony guardrail picket.426 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0449 | Balcony guardrail picket.427 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0450 | Balcony guardrail picket.428 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0451 | Balcony guardrail picket.429 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0452 | Balcony guardrail picket.430 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0453 | Balcony guardrail picket.431 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0454 | Balcony guardrail picket.432 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0455 | Balcony guardrail picket.433 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0456 | Balcony guardrail picket.434 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0457 | Balcony guardrail picket.435 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0458 | Balcony guardrail picket.436 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0459 | Balcony guardrail picket.437 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0460 | Balcony guardrail picket.438 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0461 | Balcony guardrail picket.439 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0462 | Balcony guardrail picket.440 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0463 | Balcony guardrail picket.441 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0464 | Balcony guardrail picket.442 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0465 | Balcony guardrail picket.443 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0466 | Balcony guardrail post | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-0467 | Balcony guardrail post.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-0468 | Balcony guardrail post.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-0469 | Balcony guardrail post.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-0470 | Balcony guardrail post.004 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-0471 | Balcony guardrail post.005 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-0472 | Balcony guardrail post.006 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-0473 | Balcony guardrail post.007 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-0474 | Balcony guardrail post.008 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-0475 | Balcony guardrail post.009 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-0476 | Balcony guardrail post.010 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-0477 | Balcony guardrail post.011 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-0478 | Balcony guardrail top | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 26.3 | 0.13 | 0.13
ARC-SITE-CTX-CTX-0479 | Balcony guardrail top.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 26.3 | 0.13 | 0.13
ARC-SITE-CTX-CTX-0480 | Balcony guardrail top.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 26.3 | 0.13 | 0.13
ARC-SITE-CTX-CTX-0481 | Balcony guardrail top.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 26.3 | 0.13 | 0.13
ARC-SITE-CTX-CTX-0482 | Balcony guardrail top.004 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 26.3 | 0.13 | 0.13
ARC-SITE-CTX-CTX-0483 | Balcony guardrail top.005 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 26.3 | 0.13 | 0.13
ARC-SITE-CTX-CTX-0484 | Balcony interior rear partition | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 27 | 0.4 | 27
ARC-SITE-CTX-CTX-0485 | Balcony interior rear partition.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 27 | 0.4 | 27
ARC-SITE-CTX-CTX-0486 | Balcony potted foliage | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 1.2272 | 1.2039 | 0.7672
ARC-SITE-CTX-CTX-0487 | Balcony potted foliage.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 1.0237 | 1.0103 | 0.6178
ARC-SITE-CTX-CTX-0488 | Balcony potted foliage.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 1.1419 | 1.1203 | 0.7277
ARC-SITE-CTX-CTX-0489 | Balcony potted foliage.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 1.2177 | 1.2308 | 0.8588
ARC-SITE-CTX-CTX-0490 | Balcony side stucco pier | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.5 | 4.8 | 9
ARC-SITE-CTX-CTX-0491 | Balcony side stucco pier.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.5 | 4.8 | 9
ARC-SITE-CTX-CTX-0492 | Balcony side stucco pier.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.5 | 4.8 | 9
ARC-SITE-CTX-CTX-0493 | Balcony side stucco pier.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.5 | 4.8 | 9
ARC-SITE-CTX-CTX-0494 | Balcony side stucco pier.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.5 | 4.8 | 9
ARC-SITE-CTX-CTX-0495 | Balcony side stucco pier.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.5 | 4.8 | 9
ARC-SITE-CTX-CTX-0496 | Balcony side stucco pier.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.5 | 4.8 | 9
ARC-SITE-CTX-CTX-0497 | Balcony side stucco pier.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.5 | 4.8 | 9
ARC-SITE-CTX-CTX-0498 | Balcony side stucco pier.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.5 | 4.8 | 9
ARC-SITE-CTX-CTX-0499 | Balcony side stucco pier.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.5 | 4.8 | 9
ARC-SITE-CTX-CTX-0500 | Balcony side stucco pier.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.5 | 4.8 | 9
ARC-SITE-CTX-CTX-0501 | Balcony side stucco pier.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.5 | 4.8 | 9
ARC-SITE-CTX-CTX-0502 | Beige roller shade cassette | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 21.9 | 0.32 | 0.28
ARC-SITE-CTX-CTX-0503 | Beige roller shade cassette.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 21.9 | 0.32 | 0.28
ARC-SITE-CTX-CTX-0504 | Beige roller shade cassette.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 21.9 | 0.32 | 0.28
ARC-SITE-CTX-CTX-0505 | Beige roller shade cassette.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 25.9 | 0.32 | 0.28
ARC-SITE-CTX-CTX-0506 | Beige roller shade cassette.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 25.9 | 0.32 | 0.28
ARC-SITE-CTX-CTX-0507 | Beige roller shade cassette.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 25.9 | 0.32 | 0.28
ARC-SITE-CTX-CTX-0508 | Beige roller shade cassette.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 25.9 | 0.32 | 0.28
ARC-SITE-CTX-CTX-0509 | Beige roller shade cassette.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 25.9 | 0.32 | 0.28
ARC-SITE-CTX-CTX-0510 | Beige roller shade cassette.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 25.9 | 0.32 | 0.28
ARC-SITE-CTX-CTX-0511 | Beige roller shade cassette.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 21.9 | 0.32 | 0.28
ARC-SITE-CTX-CTX-0512 | Beige roller shade cassette.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 21.9 | 0.32 | 0.28
ARC-SITE-CTX-CTX-0513 | Beige roller shade cassette.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 21.9 | 0.32 | 0.28
ARC-SITE-CTX-CTX-0514 | Beige roller shade cassette.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 27.358 | 0.32 | 0.28
ARC-SITE-CTX-CTX-0515 | Beige roller shade cassette.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 27.358 | 0.32 | 0.28
ARC-SITE-CTX-CTX-0516 | Beige roller shade cassette.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 27.358 | 0.32 | 0.28
ARC-SITE-CTX-CTX-0517 | Beige shade hem | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 21.75 | 0.1 | 0.16
ARC-SITE-CTX-CTX-0518 | Beige shade hem.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 21.75 | 0.1 | 0.16
ARC-SITE-CTX-CTX-0519 | Beige shade hem.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 21.75 | 0.1 | 0.16
ARC-SITE-CTX-CTX-0520 | Beige shade hem.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 25.75 | 0.1 | 0.16
ARC-SITE-CTX-CTX-0521 | Beige shade hem.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 25.75 | 0.1 | 0.16
ARC-SITE-CTX-CTX-0522 | Beige shade hem.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 25.75 | 0.1 | 0.16
ARC-SITE-CTX-CTX-0523 | Beige shade hem.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 25.75 | 0.1 | 0.16
ARC-SITE-CTX-CTX-0524 | Beige shade hem.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 25.75 | 0.1 | 0.16
ARC-SITE-CTX-CTX-0525 | Beige shade hem.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 25.75 | 0.1 | 0.16
ARC-SITE-CTX-CTX-0526 | Beige shade hem.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 21.75 | 0.1 | 0.16
ARC-SITE-CTX-CTX-0527 | Beige shade hem.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 21.75 | 0.1 | 0.16
ARC-SITE-CTX-CTX-0528 | Beige shade hem.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 21.75 | 0.1 | 0.16
ARC-SITE-CTX-CTX-0529 | Beige shade hem.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 27.208 | 0.1 | 0.16
ARC-SITE-CTX-CTX-0530 | Beige shade hem.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 27.208 | 0.1 | 0.16
ARC-SITE-CTX-CTX-0531 | Beige shade hem.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Beige woven roller shades | 27.208 | 0.1 | 0.16
ARC-SITE-CTX-CTX-0532 | BldgB_UpperFloor_2 | MESH | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | 3-story Building B context | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Precast_Xray | 160.4583 | 66.3333 | 0.3333
ARC-SITE-CTX-CTX-0533 | BldgB_UpperFloor_3 | MESH | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | 3-story Building B context | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Precast_Xray | 160.4583 | 66.3333 | 0.3333
ARC-SITE-CTX-CTX-0534 | Bronze jamb | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0535 | Bronze jamb.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0536 | Bronze jamb.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0537 | Bronze jamb.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0538 | Bronze jamb.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0539 | Bronze jamb.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0540 | Bronze jamb.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0541 | Bronze jamb.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0542 | Bronze jamb.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0543 | Bronze jamb.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0544 | Bronze jamb.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0545 | Bronze jamb.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0546 | Bronze jamb.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0547 | Bronze jamb.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0548 | Bronze jamb.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0549 | Bronze jamb.015 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0550 | Bronze jamb.016 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0551 | Bronze jamb.017 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0552 | Bronze jamb.018 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0553 | Bronze jamb.019 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0554 | Bronze jamb.020 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0555 | Bronze jamb.021 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0556 | Bronze jamb.022 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0557 | Bronze jamb.023 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0558 | Bronze jamb.024 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0559 | Bronze jamb.025 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0560 | Bronze jamb.026 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0561 | Bronze jamb.027 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0562 | Bronze jamb.028 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0563 | Bronze jamb.029 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0564 | Bronze jamb.030 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0565 | Bronze jamb.031 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0566 | Bronze jamb.032 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0567 | Bronze jamb.033 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0568 | Bronze jamb.034 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0569 | Bronze jamb.035 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.15 | 6.92
ARC-SITE-CTX-CTX-0570 | Bronze mullion | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0571 | Bronze mullion.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0572 | Bronze mullion.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0573 | Bronze mullion.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0574 | Bronze mullion.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0575 | Bronze mullion.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0576 | Bronze mullion.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0577 | Bronze mullion.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0578 | Bronze mullion.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0579 | Bronze mullion.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0580 | Bronze mullion.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0581 | Bronze mullion.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0582 | Bronze mullion.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0583 | Bronze mullion.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0584 | Bronze mullion.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0585 | Bronze mullion.015 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0586 | Bronze mullion.016 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0587 | Bronze mullion.017 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0588 | Bronze mullion.018 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0589 | Bronze mullion.019 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0590 | Bronze mullion.020 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0591 | Bronze mullion.021 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0592 | Bronze mullion.022 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0593 | Bronze mullion.023 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0594 | Bronze mullion.024 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0595 | Bronze mullion.025 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0596 | Bronze mullion.026 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0597 | Bronze mullion.027 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0598 | Bronze mullion.028 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0599 | Bronze mullion.029 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0600 | Bronze mullion.030 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0601 | Bronze mullion.031 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0602 | Bronze mullion.032 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.105 | 0.15 | 6.8
ARC-SITE-CTX-CTX-0603 | Bronze rail | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 21.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0604 | Bronze rail.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 21.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0605 | Bronze rail.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 21.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0606 | Bronze rail.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 21.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0607 | Bronze rail.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 21.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0608 | Bronze rail.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 21.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0609 | Bronze rail.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 25.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0610 | Bronze rail.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 25.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0611 | Bronze rail.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 25.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0612 | Bronze rail.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 25.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0613 | Bronze rail.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 25.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0614 | Bronze rail.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 25.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0615 | Bronze rail.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 8.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0616 | Bronze rail.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 8.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0617 | Bronze rail.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 8.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0618 | Bronze rail.015 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 8.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0619 | Bronze rail.016 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 8.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0620 | Bronze rail.017 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 8.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0621 | Bronze rail.018 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 25.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0622 | Bronze rail.019 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 25.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0623 | Bronze rail.020 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 25.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0624 | Bronze rail.021 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 25.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0625 | Bronze rail.022 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 25.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0626 | Bronze rail.023 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 25.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0627 | Bronze rail.024 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 21.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0628 | Bronze rail.025 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 21.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0629 | Bronze rail.026 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 21.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0630 | Bronze rail.027 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 21.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0631 | Bronze rail.028 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 21.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0632 | Bronze rail.029 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 21.82 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0633 | Bronze rail.030 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 27.278 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0634 | Bronze rail.031 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 27.278 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0635 | Bronze rail.032 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 27.278 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0636 | Bronze rail.033 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 27.278 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0637 | Bronze rail.034 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 27.278 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0638 | Bronze rail.035 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 27.278 | 0.15 | 0.12
ARC-SITE-CTX-CTX-0639 | Bronze rainwater downspout | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.23 | 0.23 | 26.7
ARC-SITE-CTX-CTX-0640 | Bronze rainwater downspout.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.23 | 0.23 | 26.7
ARC-SITE-CTX-CTX-0641 | Bronze rainwater downspout.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.23 | 0.23 | 26.7
ARC-SITE-CTX-CTX-0642 | Bronze rainwater downspout.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.23 | 0.23 | 26.7
ARC-SITE-CTX-CTX-0643 | Bronze rainwater downspout.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.23 | 0.23 | 26.7
ARC-SITE-CTX-CTX-0644 | Bronze rainwater downspout.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.23 | 0.23 | 26.7
ARC-SITE-CTX-CTX-0645 | Continuous precast floor band | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 160.808 | 0.72 | 0.42
ARC-SITE-CTX-CTX-0646 | Continuous precast floor band.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 160.808 | 0.72 | 0.42
ARC-SITE-CTX-CTX-0647 | Continuous precast floor band.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 160.808 | 0.72 | 0.42
ARC-SITE-CTX-CTX-0648 | Cream roof cap | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 161.408 | 0.72 | 0.13
ARC-SITE-CTX-CTX-0649 | Dark bronze roof fascia | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 161.258 | 0.55 | 0.55
ARC-SITE-CTX-CTX-0650 | Dark siding stair tower | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Dark bronze horizontal siding | 14 | 0.65 | 9
ARC-SITE-CTX-CTX-0651 | Dark siding stair tower.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Dark bronze horizontal siding | 14 | 0.65 | 9
ARC-SITE-CTX-CTX-0652 | Dark siding stair tower.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Dark bronze horizontal siding | 14 | 0.65 | 9
ARC-SITE-CTX-CTX-0653 | Downspout wall strap | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0654 | Downspout wall strap.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0655 | Downspout wall strap.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0656 | Downspout wall strap.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0657 | Downspout wall strap.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0658 | Downspout wall strap.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0659 | Downspout wall strap.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0660 | Downspout wall strap.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0661 | Downspout wall strap.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0662 | Downspout wall strap.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0663 | Downspout wall strap.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0664 | Downspout wall strap.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0665 | Downspout wall strap.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0666 | Downspout wall strap.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0667 | Downspout wall strap.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0668 | Downspout wall strap.015 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0669 | Downspout wall strap.016 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0670 | Downspout wall strap.017 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.34 | 0.25 | 0.09
ARC-SITE-CTX-CTX-0671 | East_Garage_Block_1 | MESH | East_Garages_&_Planter_Strip | East_Garages_&_Planter_Strip | SITE | SITE | ARCHITECTURE | SITE_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | SOR: garages ~10 ft east of Building B | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | MAT_Precast_Xray | 1 | 1 | 1
ARC-SITE-CTX-CTX-0672 | East_Garage_Block_2 | MESH | East_Garages_&_Planter_Strip | East_Garages_&_Planter_Strip | SITE | SITE | ARCHITECTURE | SITE_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | SOR: garages ~10 ft east of Building B | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | MAT_Precast_Xray | 1 | 1 | 1
ARC-SITE-CTX-CTX-0673 | East_Garage_Block_3 | MESH | East_Garages_&_Planter_Strip | East_Garages_&_Planter_Strip | SITE | SITE | ARCHITECTURE | SITE_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | SOR: garages ~10 ft east of Building B | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | MAT_Precast_Xray | 1 | 1 | 1
ARC-SITE-CTX-CTX-0674 | End elevation window | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0675 | End elevation window.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0676 | End elevation window.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0677 | End elevation window.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0678 | End elevation window.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0679 | End elevation window.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0680 | End elevation window.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0681 | End elevation window.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0682 | End elevation window.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0683 | End elevation window.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0684 | End elevation window.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0685 | End elevation window.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0686 | End elevation window.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0687 | End elevation window.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0688 | End elevation window.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0689 | End elevation window.015 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0690 | End elevation window.016 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0691 | End elevation window.017 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0692 | End elevation window.018 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0693 | End elevation window.019 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0694 | End elevation window.020 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0695 | End elevation window.021 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0696 | End elevation window.022 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0697 | End elevation window.023 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 0.07 | 5.5 | 5.6
ARC-SITE-CTX-CTX-0698 | End stucco elevation | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.55 | 66.333 | 27
ARC-SITE-CTX-CTX-0699 | End stucco elevation.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.55 | 66.333 | 27
ARC-SITE-CTX-CTX-0700 | End window jamb | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0701 | End window jamb.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0702 | End window jamb.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0703 | End window jamb.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0704 | End window jamb.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0705 | End window jamb.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0706 | End window jamb.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0707 | End window jamb.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0708 | End window jamb.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0709 | End window jamb.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0710 | End window jamb.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0711 | End window jamb.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0712 | End window jamb.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0713 | End window jamb.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0714 | End window jamb.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0715 | End window jamb.015 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0716 | End window jamb.016 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0717 | End window jamb.017 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0718 | End window jamb.018 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0719 | End window jamb.019 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0720 | End window jamb.020 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0721 | End window jamb.021 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0722 | End window jamb.022 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0723 | End window jamb.023 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0724 | End window jamb.024 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0725 | End window jamb.025 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0726 | End window jamb.026 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0727 | End window jamb.027 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0728 | End window jamb.028 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0729 | End window jamb.029 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0730 | End window jamb.030 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0731 | End window jamb.031 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0732 | End window jamb.032 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0733 | End window jamb.033 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0734 | End window jamb.034 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0735 | End window jamb.035 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0736 | End window jamb.036 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0737 | End window jamb.037 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0738 | End window jamb.038 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0739 | End window jamb.039 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0740 | End window jamb.040 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0741 | End window jamb.041 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0742 | End window jamb.042 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0743 | End window jamb.043 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0744 | End window jamb.044 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0745 | End window jamb.045 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0746 | End window jamb.046 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0747 | End window jamb.047 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.14 | 0.12 | 5.8
ARC-SITE-CTX-CTX-0748 | Exterior sconce backplate | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Anodized dark bronze aluminum | 0.34 | 0.18 | 0.75
ARC-SITE-CTX-CTX-0749 | Exterior sconce backplate.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Anodized dark bronze aluminum | 0.34 | 0.18 | 0.75
ARC-SITE-CTX-CTX-0750 | Exterior sconce backplate.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Anodized dark bronze aluminum | 0.34 | 0.18 | 0.75
ARC-SITE-CTX-CTX-0751 | Exterior sconce backplate.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Anodized dark bronze aluminum | 0.34 | 0.18 | 0.75
ARC-SITE-CTX-CTX-0752 | Exterior sconce diffuser | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Painted cream trim | 0.22 | 0.16 | 0.48
ARC-SITE-CTX-CTX-0753 | Exterior sconce diffuser.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Painted cream trim | 0.22 | 0.16 | 0.48
ARC-SITE-CTX-CTX-0754 | Exterior sconce diffuser.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Painted cream trim | 0.22 | 0.16 | 0.48
ARC-SITE-CTX-CTX-0755 | Exterior sconce diffuser.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Painted cream trim | 0.22 | 0.16 | 0.48
ARC-SITE-CTX-CTX-0756 | Flat insulated roof | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Flat roof membrane | 160.458 | 66.333 | 0.38
ARC-SITE-CTX-CTX-0757 | GRID_1 | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 166.4583 | 0.03 | 0.03
ARC-SITE-CTX-CTX-0758 | GRID_2 | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 166.4583 | 0.03 | 0.03
ARC-SITE-CTX-CTX-0759 | GRID_3 | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 166.4583 | 0.03 | 0.03
ARC-SITE-CTX-CTX-0760 | GRID_4 | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 166.4583 | 0.03 | 0.03
ARC-SITE-CTX-CTX-0761 | GRID_5 | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 166.4583 | 0.03 | 0.03
ARC-SITE-CTX-CTX-0762 | GRID_6 | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 166.4583 | 0.03 | 0.03
ARC-SITE-CTX-CTX-0763 | GRID_A | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.03 | 72.3333 | 0.03
ARC-SITE-CTX-CTX-0764 | GRID_B | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.03 | 72.3333 | 0.03
ARC-SITE-CTX-CTX-0765 | GRID_C | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.03 | 72.3333 | 0.03
ARC-SITE-CTX-CTX-0766 | GRID_D | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.03 | 72.3333 | 0.03
ARC-SITE-CTX-CTX-0767 | GRID_E | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.03 | 72.3333 | 0.03
ARC-SITE-CTX-CTX-0768 | GRID_F | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.03 | 72.3333 | 0.03
ARC-SITE-CTX-CTX-0769 | GRID_G | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.03 | 72.3333 | 0.03
ARC-SITE-CTX-CTX-0770 | GRID_H | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.03 | 72.3333 | 0.03
ARC-SITE-CTX-CTX-0771 | GRID_I | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.03 | 72.3333 | 0.03
ARC-SITE-CTX-CTX-0772 | GRID_J | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.03 | 72.3333 | 0.03
ARC-SITE-CTX-CTX-0773 | GRID_K | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.03 | 72.3333 | 0.03
ARC-SITE-CTX-CTX-0774 | GRID_L | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.03 | 72.3333 | 0.03
ARC-SITE-CTX-CTX-0775 | GRID_LABEL_1 | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.0784 | 0.5456 | 0
ARC-SITE-CTX-CTX-0776 | GRID_LABEL_2 | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.3456 | 0.5528 | 0
ARC-SITE-CTX-CTX-0777 | GRID_LABEL_3 | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.288 | 0.56 | 0
ARC-SITE-CTX-CTX-0778 | GRID_LABEL_4 | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.368 | 0.5528 | 0
ARC-SITE-CTX-CTX-0779 | GRID_LABEL_5 | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.3104 | 0.5528 | 0
ARC-SITE-CTX-CTX-0780 | GRID_LABEL_6 | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.3368 | 0.56 | 0
ARC-SITE-CTX-CTX-0781 | GRID_LABEL_A | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.5336 | 0.5488 | 0
ARC-SITE-CTX-CTX-0782 | GRID_LABEL_B | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.3744 | 0.5456 | 0
ARC-SITE-CTX-CTX-0783 | GRID_LABEL_C | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.492 | 0.56 | 0
ARC-SITE-CTX-CTX-0784 | GRID_LABEL_D | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.5024 | 0.5456 | 0
ARC-SITE-CTX-CTX-0785 | GRID_LABEL_E | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.3168 | 0.5456 | 0
ARC-SITE-CTX-CTX-0786 | GRID_LABEL_F | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.2912 | 0.5456 | 0
ARC-SITE-CTX-CTX-0787 | GRID_LABEL_G | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.4984 | 0.56 | 0
ARC-SITE-CTX-CTX-0788 | GRID_LABEL_H | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.4624 | 0.5456 | 0
ARC-SITE-CTX-CTX-0789 | GRID_LABEL_I | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.0784 | 0.5456 | 0
ARC-SITE-CTX-CTX-0790 | GRID_LABEL_J | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.1888 | 0.7296 | 0
ARC-SITE-CTX-CTX-0791 | GRID_LABEL_K | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.464 | 0.5456 | 0
ARC-SITE-CTX-CTX-0792 | GRID_LABEL_L | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.3248 | 0.5456 | 0
ARC-SITE-CTX-CTX-0793 | GRID_LABEL_M | FONT | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.5088 | 0.5456 | 0
ARC-SITE-CTX-CTX-0794 | GRID_M | CURVE | Bldg_B_Shell_&_Upper_Stacks | Bldg_B_Shell_&_Upper_Stacks | SITE | SITE | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | P1.01/P1.02 grid | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_GhostWalls_MAT_Grid | 0.03 | 72.3333 | 0.03
ARC-SITE-CTX-CTX-0795 | Ground patio fence bottom | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 25.7 | 0.09 | 0.09
ARC-SITE-CTX-CTX-0796 | Ground patio fence bottom.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 25.7 | 0.09 | 0.09
ARC-SITE-CTX-CTX-0797 | Ground patio fence picket | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0798 | Ground patio fence picket.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0799 | Ground patio fence picket.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0800 | Ground patio fence picket.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0801 | Ground patio fence picket.004 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0802 | Ground patio fence picket.005 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0803 | Ground patio fence picket.006 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0804 | Ground patio fence picket.007 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0805 | Ground patio fence picket.008 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0806 | Ground patio fence picket.009 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0807 | Ground patio fence picket.010 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0808 | Ground patio fence picket.011 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0809 | Ground patio fence picket.012 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0810 | Ground patio fence picket.013 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0811 | Ground patio fence picket.014 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0812 | Ground patio fence picket.015 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0813 | Ground patio fence picket.016 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0814 | Ground patio fence picket.017 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0815 | Ground patio fence picket.018 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0816 | Ground patio fence picket.019 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0817 | Ground patio fence picket.020 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0818 | Ground patio fence picket.021 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0819 | Ground patio fence picket.022 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0820 | Ground patio fence picket.023 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0821 | Ground patio fence picket.024 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0822 | Ground patio fence picket.025 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0823 | Ground patio fence picket.026 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0824 | Ground patio fence picket.027 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0825 | Ground patio fence picket.028 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0826 | Ground patio fence picket.029 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0827 | Ground patio fence picket.030 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0828 | Ground patio fence picket.031 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0829 | Ground patio fence picket.032 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0830 | Ground patio fence picket.033 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0831 | Ground patio fence picket.034 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0832 | Ground patio fence picket.035 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0833 | Ground patio fence picket.036 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0834 | Ground patio fence picket.037 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0835 | Ground patio fence picket.038 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0836 | Ground patio fence picket.039 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0837 | Ground patio fence picket.040 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0838 | Ground patio fence picket.041 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0839 | Ground patio fence picket.042 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0840 | Ground patio fence picket.043 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0841 | Ground patio fence picket.044 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0842 | Ground patio fence picket.045 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0843 | Ground patio fence picket.046 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0844 | Ground patio fence picket.047 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0845 | Ground patio fence picket.048 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0846 | Ground patio fence picket.049 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0847 | Ground patio fence picket.050 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0848 | Ground patio fence picket.051 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0849 | Ground patio fence picket.052 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0850 | Ground patio fence picket.053 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0851 | Ground patio fence picket.054 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0852 | Ground patio fence picket.055 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0853 | Ground patio fence picket.056 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0854 | Ground patio fence picket.057 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0855 | Ground patio fence picket.058 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0856 | Ground patio fence picket.059 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0857 | Ground patio fence picket.060 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0858 | Ground patio fence picket.061 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0859 | Ground patio fence picket.062 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0860 | Ground patio fence picket.063 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0861 | Ground patio fence picket.064 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0862 | Ground patio fence picket.065 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0863 | Ground patio fence picket.066 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0864 | Ground patio fence picket.067 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0865 | Ground patio fence picket.068 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0866 | Ground patio fence picket.069 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0867 | Ground patio fence picket.070 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0868 | Ground patio fence picket.071 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0869 | Ground patio fence picket.072 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0870 | Ground patio fence picket.073 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0871 | Ground patio fence picket.074 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0872 | Ground patio fence picket.075 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0873 | Ground patio fence picket.076 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0874 | Ground patio fence picket.077 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0875 | Ground patio fence picket.078 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0876 | Ground patio fence picket.079 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0877 | Ground patio fence picket.080 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0878 | Ground patio fence picket.081 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0879 | Ground patio fence picket.082 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0880 | Ground patio fence picket.083 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0881 | Ground patio fence picket.084 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0882 | Ground patio fence picket.085 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0883 | Ground patio fence picket.086 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0884 | Ground patio fence picket.087 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0885 | Ground patio fence picket.088 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0886 | Ground patio fence picket.089 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0887 | Ground patio fence picket.090 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0888 | Ground patio fence picket.091 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0889 | Ground patio fence picket.092 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0890 | Ground patio fence picket.093 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0891 | Ground patio fence picket.094 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0892 | Ground patio fence picket.095 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0893 | Ground patio fence picket.096 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0894 | Ground patio fence picket.097 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0895 | Ground patio fence picket.098 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0896 | Ground patio fence picket.099 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0897 | Ground patio fence picket.100 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0898 | Ground patio fence picket.101 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0899 | Ground patio fence picket.102 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0900 | Ground patio fence picket.103 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0901 | Ground patio fence picket.104 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0902 | Ground patio fence picket.105 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0903 | Ground patio fence picket.106 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0904 | Ground patio fence picket.107 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0905 | Ground patio fence picket.108 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0906 | Ground patio fence picket.109 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0907 | Ground patio fence picket.110 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0908 | Ground patio fence picket.111 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0909 | Ground patio fence picket.112 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0910 | Ground patio fence picket.113 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0911 | Ground patio fence picket.114 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0912 | Ground patio fence picket.115 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0913 | Ground patio fence picket.116 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0914 | Ground patio fence picket.117 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0915 | Ground patio fence picket.118 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0916 | Ground patio fence picket.119 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0917 | Ground patio fence picket.120 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0918 | Ground patio fence picket.121 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0919 | Ground patio fence picket.122 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0920 | Ground patio fence picket.123 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0921 | Ground patio fence picket.124 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0922 | Ground patio fence picket.125 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0923 | Ground patio fence picket.126 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0924 | Ground patio fence picket.127 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0925 | Ground patio fence picket.128 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0926 | Ground patio fence picket.129 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0927 | Ground patio fence picket.130 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0928 | Ground patio fence picket.131 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0929 | Ground patio fence picket.132 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0930 | Ground patio fence picket.133 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0931 | Ground patio fence picket.134 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0932 | Ground patio fence picket.135 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0933 | Ground patio fence picket.136 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0934 | Ground patio fence picket.137 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0935 | Ground patio fence picket.138 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0936 | Ground patio fence picket.139 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0937 | Ground patio fence picket.140 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0938 | Ground patio fence picket.141 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0939 | Ground patio fence picket.142 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0940 | Ground patio fence picket.143 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-0941 | Ground patio fence post | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-0942 | Ground patio fence post.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-0943 | Ground patio fence post.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-0944 | Ground patio fence post.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-0945 | Ground patio fence top | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 25.7 | 0.13 | 0.13
ARC-SITE-CTX-CTX-0946 | Ground patio fence top.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 25.7 | 0.13 | 0.13
ARC-SITE-CTX-CTX-0947 | HVAC grille louver | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0948 | HVAC grille louver.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0949 | HVAC grille louver.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0950 | HVAC grille louver.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0951 | HVAC grille louver.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0952 | HVAC grille louver.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0953 | HVAC grille louver.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0954 | HVAC grille louver.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0955 | HVAC grille louver.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0956 | HVAC grille louver.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0957 | HVAC grille louver.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0958 | HVAC grille louver.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0959 | HVAC grille louver.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0960 | HVAC grille louver.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0961 | HVAC grille louver.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0962 | HVAC grille louver.015 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0963 | HVAC grille louver.016 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0964 | HVAC grille louver.017 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0965 | HVAC grille louver.018 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0966 | HVAC grille louver.019 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0967 | HVAC grille louver.020 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0968 | HVAC grille louver.021 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0969 | HVAC grille louver.022 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0970 | HVAC grille louver.023 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Black powder-coated steel | 0.23 | 0.08 | 1.55
ARC-SITE-CTX-CTX-0971 | Horizontal siding shadow reveal | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0972 | Horizontal siding shadow reveal.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0973 | Horizontal siding shadow reveal.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0974 | Horizontal siding shadow reveal.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0975 | Horizontal siding shadow reveal.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0976 | Horizontal siding shadow reveal.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0977 | Horizontal siding shadow reveal.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0978 | Horizontal siding shadow reveal.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0979 | Horizontal siding shadow reveal.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0980 | Horizontal siding shadow reveal.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0981 | Horizontal siding shadow reveal.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0982 | Horizontal siding shadow reveal.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0983 | Horizontal siding shadow reveal.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0984 | Horizontal siding shadow reveal.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0985 | Horizontal siding shadow reveal.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0986 | Horizontal siding shadow reveal.015 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0987 | Horizontal siding shadow reveal.016 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0988 | Horizontal siding shadow reveal.017 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0989 | Horizontal siding shadow reveal.018 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0990 | Horizontal siding shadow reveal.019 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0991 | Horizontal siding shadow reveal.020 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0992 | Horizontal siding shadow reveal.021 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0993 | Horizontal siding shadow reveal.022 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0994 | Horizontal siding shadow reveal.023 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0995 | Horizontal siding shadow reveal.024 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0996 | Horizontal siding shadow reveal.025 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0997 | Horizontal siding shadow reveal.026 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0998 | Horizontal siding shadow reveal.027 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-0999 | Horizontal siding shadow reveal.028 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1000 | Horizontal siding shadow reveal.029 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1001 | Horizontal siding shadow reveal.030 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1002 | Horizontal siding shadow reveal.031 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1003 | Horizontal siding shadow reveal.032 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1004 | Horizontal siding shadow reveal.033 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1005 | Horizontal siding shadow reveal.034 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1006 | Horizontal siding shadow reveal.035 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1007 | Horizontal siding shadow reveal.036 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1008 | Horizontal siding shadow reveal.037 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1009 | Horizontal siding shadow reveal.038 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1010 | Horizontal siding shadow reveal.039 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1011 | Horizontal siding shadow reveal.040 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1012 | Horizontal siding shadow reveal.041 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1013 | Horizontal siding shadow reveal.042 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1014 | Horizontal siding shadow reveal.043 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1015 | Horizontal siding shadow reveal.044 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1016 | Horizontal siding shadow reveal.045 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1017 | Horizontal siding shadow reveal.046 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1018 | Horizontal siding shadow reveal.047 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1019 | Horizontal siding shadow reveal.048 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1020 | Horizontal siding shadow reveal.049 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1021 | Horizontal siding shadow reveal.050 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1022 | Horizontal siding shadow reveal.051 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1023 | Horizontal siding shadow reveal.052 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1024 | Horizontal siding shadow reveal.053 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1025 | Horizontal siding shadow reveal.054 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1026 | Horizontal siding shadow reveal.055 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1027 | Horizontal siding shadow reveal.056 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1028 | Horizontal siding shadow reveal.057 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1029 | Horizontal siding shadow reveal.058 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1030 | Horizontal siding shadow reveal.059 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1031 | Horizontal siding shadow reveal.060 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1032 | Horizontal siding shadow reveal.061 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1033 | Horizontal siding shadow reveal.062 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1034 | Horizontal siding shadow reveal.063 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1035 | Horizontal siding shadow reveal.064 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1036 | Horizontal siding shadow reveal.065 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1037 | Horizontal siding shadow reveal.066 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1038 | Horizontal siding shadow reveal.067 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1039 | Horizontal siding shadow reveal.068 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1040 | Horizontal siding shadow reveal.069 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1041 | Horizontal siding shadow reveal.070 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1042 | Horizontal siding shadow reveal.071 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1043 | Horizontal siding shadow reveal.072 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1044 | Horizontal siding shadow reveal.073 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1045 | Horizontal siding shadow reveal.074 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1046 | Horizontal siding shadow reveal.075 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1047 | Horizontal siding shadow reveal.076 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1048 | Horizontal siding shadow reveal.077 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 14 | 0.06 | 0.035
ARC-SITE-CTX-CTX-1049 | Interior roller blind | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1050 | Interior roller blind.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1051 | Interior roller blind.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1052 | Interior roller blind.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1053 | Interior roller blind.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1054 | Interior roller blind.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1055 | Interior roller blind.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 1.224
ARC-SITE-CTX-CTX-1056 | Interior roller blind.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 5.576
ARC-SITE-CTX-CTX-1057 | Interior roller blind.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 3.74
ARC-SITE-CTX-CTX-1058 | Interior roller blind.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1059 | Interior roller blind.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 5.576
ARC-SITE-CTX-CTX-1060 | Interior roller blind.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 3.74
ARC-SITE-CTX-CTX-1061 | Interior roller blind.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 3.74
ARC-SITE-CTX-CTX-1062 | Interior roller blind.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1063 | Interior roller blind.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 3.74
ARC-SITE-CTX-CTX-1064 | Interior roller blind.015 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 5.576
ARC-SITE-CTX-CTX-1065 | Interior roller blind.016 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 3.74
ARC-SITE-CTX-CTX-1066 | Interior roller blind.017 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 1.224
ARC-SITE-CTX-CTX-1067 | Interior roller blind.018 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1068 | Interior roller blind.019 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 3.74
ARC-SITE-CTX-CTX-1069 | Interior roller blind.020 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 5.576
ARC-SITE-CTX-CTX-1070 | Interior roller blind.021 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 8.54 | 0.035 | 5.576
ARC-SITE-CTX-CTX-1071 | Interior roller blind.022 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 8.54 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1072 | Interior roller blind.023 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 8.54 | 0.035 | 1.224
ARC-SITE-CTX-CTX-1073 | Interior roller blind.024 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 5.576
ARC-SITE-CTX-CTX-1074 | Interior roller blind.025 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 5.576
ARC-SITE-CTX-CTX-1075 | Interior roller blind.026 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1076 | Interior roller blind.027 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1077 | Interior roller blind.028 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 5.576
ARC-SITE-CTX-CTX-1078 | Interior roller blind.029 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1079 | Interior roller blind.030 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 3.74
ARC-SITE-CTX-CTX-1080 | Interior roller blind.031 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1081 | Interior roller blind.032 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1082 | Interior roller blind.033 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 3.74
ARC-SITE-CTX-CTX-1083 | Interior roller blind.034 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 3.74
ARC-SITE-CTX-CTX-1084 | Interior roller blind.035 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 6.265 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1085 | Interior roller blind.036 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 1.224
ARC-SITE-CTX-CTX-1086 | Interior roller blind.037 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 3.74
ARC-SITE-CTX-CTX-1087 | Interior roller blind.038 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 1.224
ARC-SITE-CTX-CTX-1088 | Interior roller blind.039 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 1.224
ARC-SITE-CTX-CTX-1089 | Interior roller blind.040 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 5.576
ARC-SITE-CTX-CTX-1090 | Interior roller blind.041 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 1.224
ARC-SITE-CTX-CTX-1091 | Interior roller blind.042 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 3.74
ARC-SITE-CTX-CTX-1092 | Interior roller blind.043 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 5.576
ARC-SITE-CTX-CTX-1093 | Interior roller blind.044 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 7.0733 | 0.035 | 3.74
ARC-SITE-CTX-CTX-1094 | Interior roller blind.045 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 13.419 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1095 | Interior roller blind.046 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 13.419 | 0.035 | 3.74
ARC-SITE-CTX-CTX-1096 | Interior roller blind.047 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 13.419 | 0.035 | 1.224
ARC-SITE-CTX-CTX-1097 | Interior roller blind.048 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 13.419 | 0.035 | 5.576
ARC-SITE-CTX-CTX-1098 | Interior roller blind.049 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 13.419 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1099 | Interior roller blind.050 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm interior blinds | 13.419 | 0.035 | 2.176
ARC-SITE-CTX-CTX-1100 | Juliet guardrail bottom | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 25.5 | 0.09 | 0.09
ARC-SITE-CTX-CTX-1101 | Juliet guardrail bottom.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 25.5 | 0.09 | 0.09
ARC-SITE-CTX-CTX-1102 | Juliet guardrail bottom.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 25.5 | 0.09 | 0.09
ARC-SITE-CTX-CTX-1103 | Juliet guardrail bottom.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 25.5 | 0.09 | 0.09
ARC-SITE-CTX-CTX-1104 | Juliet guardrail bottom.004 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 25.5 | 0.09 | 0.09
ARC-SITE-CTX-CTX-1105 | Juliet guardrail bottom.005 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 25.5 | 0.09 | 0.09
ARC-SITE-CTX-CTX-1106 | Juliet guardrail picket | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1107 | Juliet guardrail picket.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1108 | Juliet guardrail picket.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1109 | Juliet guardrail picket.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1110 | Juliet guardrail picket.004 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1111 | Juliet guardrail picket.005 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1112 | Juliet guardrail picket.006 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1113 | Juliet guardrail picket.007 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1114 | Juliet guardrail picket.008 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1115 | Juliet guardrail picket.009 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1116 | Juliet guardrail picket.010 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1117 | Juliet guardrail picket.011 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1118 | Juliet guardrail picket.012 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1119 | Juliet guardrail picket.013 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1120 | Juliet guardrail picket.014 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1121 | Juliet guardrail picket.015 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1122 | Juliet guardrail picket.016 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1123 | Juliet guardrail picket.017 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1124 | Juliet guardrail picket.018 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1125 | Juliet guardrail picket.019 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1126 | Juliet guardrail picket.020 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1127 | Juliet guardrail picket.021 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1128 | Juliet guardrail picket.022 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1129 | Juliet guardrail picket.023 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1130 | Juliet guardrail picket.024 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1131 | Juliet guardrail picket.025 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1132 | Juliet guardrail picket.026 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1133 | Juliet guardrail picket.027 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1134 | Juliet guardrail picket.028 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1135 | Juliet guardrail picket.029 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1136 | Juliet guardrail picket.030 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1137 | Juliet guardrail picket.031 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1138 | Juliet guardrail picket.032 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1139 | Juliet guardrail picket.033 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1140 | Juliet guardrail picket.034 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1141 | Juliet guardrail picket.035 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1142 | Juliet guardrail picket.036 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1143 | Juliet guardrail picket.037 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1144 | Juliet guardrail picket.038 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1145 | Juliet guardrail picket.039 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1146 | Juliet guardrail picket.040 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1147 | Juliet guardrail picket.041 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1148 | Juliet guardrail picket.042 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1149 | Juliet guardrail picket.043 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1150 | Juliet guardrail picket.044 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1151 | Juliet guardrail picket.045 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1152 | Juliet guardrail picket.046 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1153 | Juliet guardrail picket.047 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1154 | Juliet guardrail picket.048 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1155 | Juliet guardrail picket.049 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1156 | Juliet guardrail picket.050 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1157 | Juliet guardrail picket.051 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1158 | Juliet guardrail picket.052 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1159 | Juliet guardrail picket.053 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1160 | Juliet guardrail picket.054 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1161 | Juliet guardrail picket.055 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1162 | Juliet guardrail picket.056 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1163 | Juliet guardrail picket.057 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1164 | Juliet guardrail picket.058 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1165 | Juliet guardrail picket.059 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1166 | Juliet guardrail picket.060 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1167 | Juliet guardrail picket.061 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1168 | Juliet guardrail picket.062 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1169 | Juliet guardrail picket.063 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1170 | Juliet guardrail picket.064 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1171 | Juliet guardrail picket.065 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1172 | Juliet guardrail picket.066 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1173 | Juliet guardrail picket.067 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1174 | Juliet guardrail picket.068 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1175 | Juliet guardrail picket.069 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1176 | Juliet guardrail picket.070 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1177 | Juliet guardrail picket.071 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1178 | Juliet guardrail picket.072 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1179 | Juliet guardrail picket.073 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1180 | Juliet guardrail picket.074 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1181 | Juliet guardrail picket.075 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1182 | Juliet guardrail picket.076 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1183 | Juliet guardrail picket.077 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1184 | Juliet guardrail picket.078 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1185 | Juliet guardrail picket.079 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1186 | Juliet guardrail picket.080 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1187 | Juliet guardrail picket.081 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1188 | Juliet guardrail picket.082 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1189 | Juliet guardrail picket.083 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1190 | Juliet guardrail picket.084 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1191 | Juliet guardrail picket.085 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1192 | Juliet guardrail picket.086 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1193 | Juliet guardrail picket.087 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1194 | Juliet guardrail picket.088 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1195 | Juliet guardrail picket.089 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1196 | Juliet guardrail picket.090 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1197 | Juliet guardrail picket.091 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1198 | Juliet guardrail picket.092 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1199 | Juliet guardrail picket.093 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1200 | Juliet guardrail picket.094 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1201 | Juliet guardrail picket.095 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1202 | Juliet guardrail picket.096 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1203 | Juliet guardrail picket.097 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1204 | Juliet guardrail picket.098 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1205 | Juliet guardrail picket.099 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1206 | Juliet guardrail picket.100 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1207 | Juliet guardrail picket.101 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1208 | Juliet guardrail picket.102 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1209 | Juliet guardrail picket.103 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1210 | Juliet guardrail picket.104 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1211 | Juliet guardrail picket.105 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1212 | Juliet guardrail picket.106 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1213 | Juliet guardrail picket.107 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1214 | Juliet guardrail picket.108 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1215 | Juliet guardrail picket.109 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1216 | Juliet guardrail picket.110 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1217 | Juliet guardrail picket.111 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1218 | Juliet guardrail picket.112 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1219 | Juliet guardrail picket.113 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1220 | Juliet guardrail picket.114 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1221 | Juliet guardrail picket.115 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1222 | Juliet guardrail picket.116 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1223 | Juliet guardrail picket.117 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1224 | Juliet guardrail picket.118 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1225 | Juliet guardrail picket.119 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1226 | Juliet guardrail picket.120 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1227 | Juliet guardrail picket.121 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1228 | Juliet guardrail picket.122 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1229 | Juliet guardrail picket.123 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1230 | Juliet guardrail picket.124 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1231 | Juliet guardrail picket.125 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1232 | Juliet guardrail picket.126 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1233 | Juliet guardrail picket.127 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1234 | Juliet guardrail picket.128 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1235 | Juliet guardrail picket.129 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1236 | Juliet guardrail picket.130 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1237 | Juliet guardrail picket.131 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1238 | Juliet guardrail picket.132 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1239 | Juliet guardrail picket.133 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1240 | Juliet guardrail picket.134 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1241 | Juliet guardrail picket.135 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1242 | Juliet guardrail picket.136 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1243 | Juliet guardrail picket.137 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1244 | Juliet guardrail picket.138 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1245 | Juliet guardrail picket.139 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1246 | Juliet guardrail picket.140 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1247 | Juliet guardrail picket.141 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1248 | Juliet guardrail picket.142 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1249 | Juliet guardrail picket.143 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1250 | Juliet guardrail picket.144 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1251 | Juliet guardrail picket.145 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1252 | Juliet guardrail picket.146 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1253 | Juliet guardrail picket.147 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1254 | Juliet guardrail picket.148 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1255 | Juliet guardrail picket.149 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1256 | Juliet guardrail picket.150 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1257 | Juliet guardrail picket.151 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1258 | Juliet guardrail picket.152 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1259 | Juliet guardrail picket.153 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1260 | Juliet guardrail picket.154 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1261 | Juliet guardrail picket.155 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1262 | Juliet guardrail picket.156 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1263 | Juliet guardrail picket.157 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1264 | Juliet guardrail picket.158 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1265 | Juliet guardrail picket.159 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1266 | Juliet guardrail picket.160 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1267 | Juliet guardrail picket.161 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1268 | Juliet guardrail picket.162 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1269 | Juliet guardrail picket.163 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1270 | Juliet guardrail picket.164 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1271 | Juliet guardrail picket.165 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1272 | Juliet guardrail picket.166 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1273 | Juliet guardrail picket.167 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1274 | Juliet guardrail picket.168 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1275 | Juliet guardrail picket.169 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1276 | Juliet guardrail picket.170 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1277 | Juliet guardrail picket.171 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1278 | Juliet guardrail picket.172 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1279 | Juliet guardrail picket.173 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1280 | Juliet guardrail picket.174 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1281 | Juliet guardrail picket.175 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1282 | Juliet guardrail picket.176 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1283 | Juliet guardrail picket.177 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1284 | Juliet guardrail picket.178 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1285 | Juliet guardrail picket.179 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1286 | Juliet guardrail picket.180 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1287 | Juliet guardrail picket.181 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1288 | Juliet guardrail picket.182 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1289 | Juliet guardrail picket.183 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1290 | Juliet guardrail picket.184 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1291 | Juliet guardrail picket.185 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1292 | Juliet guardrail picket.186 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1293 | Juliet guardrail picket.187 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1294 | Juliet guardrail picket.188 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1295 | Juliet guardrail picket.189 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1296 | Juliet guardrail picket.190 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1297 | Juliet guardrail picket.191 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1298 | Juliet guardrail picket.192 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1299 | Juliet guardrail picket.193 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1300 | Juliet guardrail picket.194 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1301 | Juliet guardrail picket.195 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1302 | Juliet guardrail picket.196 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1303 | Juliet guardrail picket.197 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1304 | Juliet guardrail picket.198 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1305 | Juliet guardrail picket.199 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1306 | Juliet guardrail picket.200 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1307 | Juliet guardrail picket.201 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1308 | Juliet guardrail picket.202 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1309 | Juliet guardrail picket.203 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1310 | Juliet guardrail picket.204 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1311 | Juliet guardrail picket.205 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1312 | Juliet guardrail picket.206 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1313 | Juliet guardrail picket.207 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1314 | Juliet guardrail picket.208 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1315 | Juliet guardrail picket.209 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1316 | Juliet guardrail picket.210 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1317 | Juliet guardrail picket.211 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1318 | Juliet guardrail picket.212 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1319 | Juliet guardrail picket.213 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1320 | Juliet guardrail picket.214 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1321 | Juliet guardrail picket.215 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1322 | Juliet guardrail picket.216 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1323 | Juliet guardrail picket.217 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1324 | Juliet guardrail picket.218 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1325 | Juliet guardrail picket.219 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1326 | Juliet guardrail picket.220 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1327 | Juliet guardrail picket.221 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1328 | Juliet guardrail picket.222 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1329 | Juliet guardrail picket.223 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1330 | Juliet guardrail picket.224 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1331 | Juliet guardrail picket.225 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1332 | Juliet guardrail picket.226 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1333 | Juliet guardrail picket.227 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1334 | Juliet guardrail picket.228 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1335 | Juliet guardrail picket.229 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1336 | Juliet guardrail picket.230 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1337 | Juliet guardrail picket.231 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1338 | Juliet guardrail picket.232 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1339 | Juliet guardrail picket.233 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1340 | Juliet guardrail picket.234 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1341 | Juliet guardrail picket.235 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1342 | Juliet guardrail picket.236 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1343 | Juliet guardrail picket.237 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1344 | Juliet guardrail picket.238 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1345 | Juliet guardrail picket.239 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1346 | Juliet guardrail picket.240 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1347 | Juliet guardrail picket.241 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1348 | Juliet guardrail picket.242 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1349 | Juliet guardrail picket.243 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1350 | Juliet guardrail picket.244 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1351 | Juliet guardrail picket.245 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1352 | Juliet guardrail picket.246 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1353 | Juliet guardrail picket.247 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1354 | Juliet guardrail picket.248 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1355 | Juliet guardrail picket.249 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1356 | Juliet guardrail picket.250 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1357 | Juliet guardrail picket.251 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1358 | Juliet guardrail picket.252 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1359 | Juliet guardrail picket.253 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1360 | Juliet guardrail picket.254 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1361 | Juliet guardrail picket.255 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1362 | Juliet guardrail picket.256 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1363 | Juliet guardrail picket.257 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1364 | Juliet guardrail picket.258 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1365 | Juliet guardrail picket.259 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1366 | Juliet guardrail picket.260 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1367 | Juliet guardrail picket.261 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1368 | Juliet guardrail picket.262 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1369 | Juliet guardrail picket.263 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1370 | Juliet guardrail picket.264 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1371 | Juliet guardrail picket.265 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1372 | Juliet guardrail picket.266 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1373 | Juliet guardrail picket.267 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1374 | Juliet guardrail picket.268 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1375 | Juliet guardrail picket.269 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1376 | Juliet guardrail picket.270 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1377 | Juliet guardrail picket.271 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1378 | Juliet guardrail picket.272 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1379 | Juliet guardrail picket.273 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1380 | Juliet guardrail picket.274 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1381 | Juliet guardrail picket.275 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1382 | Juliet guardrail picket.276 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1383 | Juliet guardrail picket.277 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1384 | Juliet guardrail picket.278 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1385 | Juliet guardrail picket.279 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1386 | Juliet guardrail picket.280 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1387 | Juliet guardrail picket.281 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1388 | Juliet guardrail picket.282 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1389 | Juliet guardrail picket.283 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1390 | Juliet guardrail picket.284 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1391 | Juliet guardrail picket.285 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1392 | Juliet guardrail picket.286 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1393 | Juliet guardrail picket.287 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1394 | Juliet guardrail picket.288 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1395 | Juliet guardrail picket.289 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1396 | Juliet guardrail picket.290 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1397 | Juliet guardrail picket.291 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1398 | Juliet guardrail picket.292 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1399 | Juliet guardrail picket.293 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1400 | Juliet guardrail picket.294 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1401 | Juliet guardrail picket.295 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1402 | Juliet guardrail picket.296 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1403 | Juliet guardrail picket.297 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1404 | Juliet guardrail picket.298 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1405 | Juliet guardrail picket.299 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1406 | Juliet guardrail picket.300 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1407 | Juliet guardrail picket.301 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1408 | Juliet guardrail picket.302 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1409 | Juliet guardrail picket.303 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1410 | Juliet guardrail picket.304 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1411 | Juliet guardrail picket.305 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1412 | Juliet guardrail picket.306 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1413 | Juliet guardrail picket.307 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1414 | Juliet guardrail picket.308 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1415 | Juliet guardrail picket.309 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1416 | Juliet guardrail picket.310 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1417 | Juliet guardrail picket.311 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1418 | Juliet guardrail picket.312 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1419 | Juliet guardrail picket.313 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1420 | Juliet guardrail picket.314 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1421 | Juliet guardrail picket.315 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1422 | Juliet guardrail picket.316 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1423 | Juliet guardrail picket.317 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1424 | Juliet guardrail picket.318 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1425 | Juliet guardrail picket.319 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1426 | Juliet guardrail picket.320 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1427 | Juliet guardrail picket.321 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1428 | Juliet guardrail picket.322 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1429 | Juliet guardrail picket.323 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1430 | Juliet guardrail picket.324 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1431 | Juliet guardrail picket.325 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1432 | Juliet guardrail picket.326 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1433 | Juliet guardrail picket.327 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1434 | Juliet guardrail picket.328 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1435 | Juliet guardrail picket.329 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1436 | Juliet guardrail picket.330 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1437 | Juliet guardrail picket.331 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1438 | Juliet guardrail picket.332 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1439 | Juliet guardrail picket.333 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1440 | Juliet guardrail picket.334 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1441 | Juliet guardrail picket.335 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1442 | Juliet guardrail picket.336 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1443 | Juliet guardrail picket.337 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1444 | Juliet guardrail picket.338 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1445 | Juliet guardrail picket.339 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1446 | Juliet guardrail picket.340 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1447 | Juliet guardrail picket.341 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1448 | Juliet guardrail picket.342 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1449 | Juliet guardrail picket.343 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1450 | Juliet guardrail picket.344 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1451 | Juliet guardrail picket.345 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1452 | Juliet guardrail picket.346 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1453 | Juliet guardrail picket.347 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1454 | Juliet guardrail picket.348 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1455 | Juliet guardrail picket.349 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1456 | Juliet guardrail picket.350 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1457 | Juliet guardrail picket.351 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1458 | Juliet guardrail picket.352 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1459 | Juliet guardrail picket.353 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1460 | Juliet guardrail picket.354 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1461 | Juliet guardrail picket.355 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1462 | Juliet guardrail picket.356 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1463 | Juliet guardrail picket.357 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1464 | Juliet guardrail picket.358 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1465 | Juliet guardrail picket.359 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1466 | Juliet guardrail picket.360 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1467 | Juliet guardrail picket.361 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1468 | Juliet guardrail picket.362 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1469 | Juliet guardrail picket.363 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1470 | Juliet guardrail picket.364 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1471 | Juliet guardrail picket.365 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1472 | Juliet guardrail picket.366 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1473 | Juliet guardrail picket.367 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1474 | Juliet guardrail picket.368 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1475 | Juliet guardrail picket.369 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1476 | Juliet guardrail picket.370 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1477 | Juliet guardrail picket.371 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1478 | Juliet guardrail picket.372 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1479 | Juliet guardrail picket.373 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1480 | Juliet guardrail picket.374 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1481 | Juliet guardrail picket.375 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1482 | Juliet guardrail picket.376 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1483 | Juliet guardrail picket.377 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1484 | Juliet guardrail picket.378 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1485 | Juliet guardrail picket.379 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1486 | Juliet guardrail picket.380 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1487 | Juliet guardrail picket.381 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1488 | Juliet guardrail picket.382 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1489 | Juliet guardrail picket.383 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1490 | Juliet guardrail picket.384 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1491 | Juliet guardrail picket.385 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1492 | Juliet guardrail picket.386 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1493 | Juliet guardrail picket.387 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1494 | Juliet guardrail picket.388 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1495 | Juliet guardrail picket.389 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1496 | Juliet guardrail picket.390 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1497 | Juliet guardrail picket.391 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1498 | Juliet guardrail picket.392 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1499 | Juliet guardrail picket.393 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1500 | Juliet guardrail picket.394 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1501 | Juliet guardrail picket.395 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1502 | Juliet guardrail picket.396 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1503 | Juliet guardrail picket.397 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1504 | Juliet guardrail picket.398 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1505 | Juliet guardrail picket.399 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1506 | Juliet guardrail picket.400 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1507 | Juliet guardrail picket.401 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1508 | Juliet guardrail picket.402 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1509 | Juliet guardrail picket.403 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1510 | Juliet guardrail picket.404 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1511 | Juliet guardrail picket.405 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1512 | Juliet guardrail picket.406 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1513 | Juliet guardrail picket.407 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1514 | Juliet guardrail picket.408 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1515 | Juliet guardrail picket.409 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1516 | Juliet guardrail picket.410 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1517 | Juliet guardrail picket.411 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1518 | Juliet guardrail picket.412 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1519 | Juliet guardrail picket.413 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1520 | Juliet guardrail picket.414 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1521 | Juliet guardrail picket.415 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1522 | Juliet guardrail picket.416 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1523 | Juliet guardrail picket.417 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1524 | Juliet guardrail picket.418 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1525 | Juliet guardrail picket.419 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1526 | Juliet guardrail picket.420 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1527 | Juliet guardrail picket.421 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1528 | Juliet guardrail picket.422 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1529 | Juliet guardrail picket.423 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1530 | Juliet guardrail picket.424 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1531 | Juliet guardrail picket.425 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.054 | 0.054 | 2.97
ARC-SITE-CTX-CTX-1532 | Juliet guardrail post | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-1533 | Juliet guardrail post.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-1534 | Juliet guardrail post.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-1535 | Juliet guardrail post.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-1536 | Juliet guardrail post.004 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-1537 | Juliet guardrail post.005 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-1538 | Juliet guardrail post.006 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-1539 | Juliet guardrail post.007 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-1540 | Juliet guardrail post.008 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-1541 | Juliet guardrail post.009 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-1542 | Juliet guardrail post.010 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-1543 | Juliet guardrail post.011 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.15 | 0.15 | 3.35
ARC-SITE-CTX-CTX-1544 | Juliet guardrail top | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 25.5 | 0.13 | 0.13
ARC-SITE-CTX-CTX-1545 | Juliet guardrail top.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 25.5 | 0.13 | 0.13
ARC-SITE-CTX-CTX-1546 | Juliet guardrail top.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 25.5 | 0.13 | 0.13
ARC-SITE-CTX-CTX-1547 | Juliet guardrail top.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 25.5 | 0.13 | 0.13
ARC-SITE-CTX-CTX-1548 | Juliet guardrail top.004 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 25.5 | 0.13 | 0.13
ARC-SITE-CTX-CTX-1549 | Juliet guardrail top.005 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 25.5 | 0.13 | 0.13
ARC-SITE-CTX-CTX-1550 | MEYD_AREA_FILL | LIGHT | 00_Site_&_Context | 00_Site_&_Context | SITE | SITE | ARCHITECTURE | SITE_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Visualization light | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
ARC-SITE-CTX-CTX-1551 | MEYD_ISO_CAMERA | CAMERA | 00_Site_&_Context | 00_Site_&_Context | SITE | SITE | ARCHITECTURE | SITE_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Default 3/4 coordination camera | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
ARC-SITE-CTX-CTX-1552 | MEYD_SUN | LIGHT | 00_Site_&_Context | 00_Site_&_Context | SITE | SITE | ARCHITECTURE | SITE_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Visualization light | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
ARC-SITE-CTX-CTX-1553 | PHASE_CONTROLLER | EMPTY | 00_Site_&_Context | 00_Site_&_Context | SITE | SITE | ARCHITECTURE | SITE_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | 4D construction phase controller | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
ARC-SITE-CTX-CTX-1554 | Patio chair arm | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 1 | 0.09
ARC-SITE-CTX-CTX-1555 | Patio chair arm.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 1 | 0.09
ARC-SITE-CTX-CTX-1556 | Patio chair arm.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 1 | 0.09
ARC-SITE-CTX-CTX-1557 | Patio chair arm.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 1 | 0.09
ARC-SITE-CTX-CTX-1558 | Patio chair arm.004 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 1 | 0.09
ARC-SITE-CTX-CTX-1559 | Patio chair arm.005 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 1 | 0.09
ARC-SITE-CTX-CTX-1560 | Patio chair arm.006 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 1 | 0.09
ARC-SITE-CTX-CTX-1561 | Patio chair arm.007 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 1 | 0.09
ARC-SITE-CTX-CTX-1562 | Patio chair arm.008 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 1 | 0.09
ARC-SITE-CTX-CTX-1563 | Patio chair arm.009 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 1 | 0.09
ARC-SITE-CTX-CTX-1564 | Patio chair arm.010 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 1 | 0.09
ARC-SITE-CTX-CTX-1565 | Patio chair arm.011 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 1 | 0.09
ARC-SITE-CTX-CTX-1566 | Patio chair arm.012 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 1 | 0.09
ARC-SITE-CTX-CTX-1567 | Patio chair arm.013 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 1 | 0.09
ARC-SITE-CTX-CTX-1568 | Patio chair arm.014 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 1 | 0.09
ARC-SITE-CTX-CTX-1569 | Patio chair arm.015 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 1 | 0.09
ARC-SITE-CTX-CTX-1570 | Patio chair leg | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1571 | Patio chair leg.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1572 | Patio chair leg.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1573 | Patio chair leg.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1574 | Patio chair leg.004 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1575 | Patio chair leg.005 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1576 | Patio chair leg.006 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1577 | Patio chair leg.007 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1578 | Patio chair leg.008 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1579 | Patio chair leg.009 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1580 | Patio chair leg.010 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1581 | Patio chair leg.011 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1582 | Patio chair leg.012 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1583 | Patio chair leg.013 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1584 | Patio chair leg.014 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1585 | Patio chair leg.015 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1586 | Patio chair leg.016 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1587 | Patio chair leg.017 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1588 | Patio chair leg.018 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1589 | Patio chair leg.019 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1590 | Patio chair leg.020 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1591 | Patio chair leg.021 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1592 | Patio chair leg.022 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1593 | Patio chair leg.023 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1594 | Patio chair leg.024 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1595 | Patio chair leg.025 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1596 | Patio chair leg.026 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1597 | Patio chair leg.027 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1598 | Patio chair leg.028 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1599 | Patio chair leg.029 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1600 | Patio chair leg.030 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1601 | Patio chair leg.031 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.09 | 0.09 | 1.45
ARC-SITE-CTX-CTX-1602 | Patio chair mesh back | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.35 | 0.12 | 1.55
ARC-SITE-CTX-CTX-1603 | Patio chair mesh back.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.35 | 0.12 | 1.55
ARC-SITE-CTX-CTX-1604 | Patio chair mesh back.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.35 | 0.12 | 1.55
ARC-SITE-CTX-CTX-1605 | Patio chair mesh back.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.35 | 0.12 | 1.55
ARC-SITE-CTX-CTX-1606 | Patio chair mesh back.004 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.35 | 0.12 | 1.55
ARC-SITE-CTX-CTX-1607 | Patio chair mesh back.005 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.35 | 0.12 | 1.55
ARC-SITE-CTX-CTX-1608 | Patio chair mesh back.006 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.35 | 0.12 | 1.55
ARC-SITE-CTX-CTX-1609 | Patio chair mesh back.007 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.35 | 0.12 | 1.55
ARC-SITE-CTX-CTX-1610 | Patio chair mesh seat | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.35 | 1.28 | 0.12
ARC-SITE-CTX-CTX-1611 | Patio chair mesh seat.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.35 | 1.28 | 0.12
ARC-SITE-CTX-CTX-1612 | Patio chair mesh seat.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.35 | 1.28 | 0.12
ARC-SITE-CTX-CTX-1613 | Patio chair mesh seat.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.35 | 1.28 | 0.12
ARC-SITE-CTX-CTX-1614 | Patio chair mesh seat.004 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.35 | 1.28 | 0.12
ARC-SITE-CTX-CTX-1615 | Patio chair mesh seat.005 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.35 | 1.28 | 0.12
ARC-SITE-CTX-CTX-1616 | Patio chair mesh seat.006 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.35 | 1.28 | 0.12
ARC-SITE-CTX-CTX-1617 | Patio chair mesh seat.007 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.35 | 1.28 | 0.12
ARC-SITE-CTX-CTX-1618 | Patio table base | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.3 | 0.12 | 0.12
ARC-SITE-CTX-CTX-1619 | Patio table base.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.12 | 1.3 | 0.12
ARC-SITE-CTX-CTX-1620 | Patio table base.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.3 | 0.12 | 0.12
ARC-SITE-CTX-CTX-1621 | Patio table base.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.12 | 1.3 | 0.12
ARC-SITE-CTX-CTX-1622 | Patio table base.004 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.3 | 0.12 | 0.12
ARC-SITE-CTX-CTX-1623 | Patio table base.005 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.12 | 1.3 | 0.12
ARC-SITE-CTX-CTX-1624 | Patio table base.006 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 1.3 | 0.12 | 0.12
ARC-SITE-CTX-CTX-1625 | Patio table base.007 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.12 | 1.3 | 0.12
ARC-SITE-CTX-CTX-1626 | Patio table pedestal | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.2 | 0.2 | 2.25
ARC-SITE-CTX-CTX-1627 | Patio table pedestal.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.2 | 0.2 | 2.25
ARC-SITE-CTX-CTX-1628 | Patio table pedestal.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.2 | 0.2 | 2.25
ARC-SITE-CTX-CTX-1629 | Patio table pedestal.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Black powder-coated steel | 0.2 | 0.2 | 2.25
ARC-SITE-CTX-CTX-1630 | Projecting sill | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 22 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1631 | Projecting sill.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 22 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1632 | Projecting sill.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 22 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1633 | Projecting sill.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 26 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1634 | Projecting sill.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 26 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1635 | Projecting sill.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 26 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1636 | Projecting sill.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 9 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1637 | Projecting sill.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 9 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1638 | Projecting sill.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 9 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1639 | Projecting sill.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 26 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1640 | Projecting sill.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 26 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1641 | Projecting sill.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 26 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1642 | Projecting sill.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 22 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1643 | Projecting sill.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 22 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1644 | Projecting sill.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 22 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1645 | Projecting sill.015 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 27.458 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1646 | Projecting sill.016 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 27.458 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1647 | Projecting sill.017 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Painted cream trim | 27.458 | 0.55 | 0.12
ARC-SITE-CTX-CTX-1648 | Rear elevation window | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1649 | Rear elevation window.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1650 | Rear elevation window.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1651 | Rear elevation window.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1652 | Rear elevation window.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1653 | Rear elevation window.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1654 | Rear elevation window.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1655 | Rear elevation window.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1656 | Rear elevation window.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1657 | Rear elevation window.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1658 | Rear elevation window.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1659 | Rear elevation window.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1660 | Rear elevation window.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1661 | Rear elevation window.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1662 | Rear elevation window.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1663 | Rear elevation window.015 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1664 | Rear elevation window.016 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1665 | Rear elevation window.017 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1666 | Rear elevation window.018 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1667 | Rear elevation window.019 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1668 | Rear elevation window.020 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1669 | Rear elevation window.021 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1670 | Rear elevation window.022 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1671 | Rear elevation window.023 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1672 | Rear elevation window.024 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1673 | Rear elevation window.025 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1674 | Rear elevation window.026 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 6 | 0.07 | 5.6
ARC-SITE-CTX-CTX-1675 | Rear roof fascia | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 160.458 | 0.55 | 0.55
ARC-SITE-CTX-CTX-1676 | Rear window jamb | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1677 | Rear window jamb.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1678 | Rear window jamb.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1679 | Rear window jamb.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1680 | Rear window jamb.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1681 | Rear window jamb.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1682 | Rear window jamb.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1683 | Rear window jamb.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1684 | Rear window jamb.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1685 | Rear window jamb.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1686 | Rear window jamb.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1687 | Rear window jamb.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1688 | Rear window jamb.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1689 | Rear window jamb.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1690 | Rear window jamb.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1691 | Rear window jamb.015 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1692 | Rear window jamb.016 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1693 | Rear window jamb.017 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1694 | Rear window jamb.018 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1695 | Rear window jamb.019 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1696 | Rear window jamb.020 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1697 | Rear window jamb.021 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1698 | Rear window jamb.022 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1699 | Rear window jamb.023 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1700 | Rear window jamb.024 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1701 | Rear window jamb.025 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1702 | Rear window jamb.026 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1703 | Rear window jamb.027 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1704 | Rear window jamb.028 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1705 | Rear window jamb.029 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1706 | Rear window jamb.030 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1707 | Rear window jamb.031 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1708 | Rear window jamb.032 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1709 | Rear window jamb.033 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1710 | Rear window jamb.034 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1711 | Rear window jamb.035 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1712 | Rear window jamb.036 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1713 | Rear window jamb.037 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1714 | Rear window jamb.038 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1715 | Rear window jamb.039 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1716 | Rear window jamb.040 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1717 | Rear window jamb.041 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1718 | Rear window jamb.042 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1719 | Rear window jamb.043 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1720 | Rear window jamb.044 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1721 | Rear window jamb.045 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1722 | Rear window jamb.046 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1723 | Rear window jamb.047 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1724 | Rear window jamb.048 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1725 | Rear window jamb.049 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1726 | Rear window jamb.050 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1727 | Rear window jamb.051 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1728 | Rear window jamb.052 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1729 | Rear window jamb.053 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.12 | 0.14 | 5.8
ARC-SITE-CTX-CTX-1730 | Recessed balcony back wall | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 27 | 0.5 | 9
ARC-SITE-CTX-CTX-1731 | Recessed balcony back wall.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 27 | 0.5 | 9
ARC-SITE-CTX-CTX-1732 | Recessed balcony back wall.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 27 | 0.5 | 9
ARC-SITE-CTX-CTX-1733 | Recessed balcony back wall.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 27 | 0.5 | 9
ARC-SITE-CTX-CTX-1734 | Recessed balcony back wall.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 27 | 0.5 | 9
ARC-SITE-CTX-CTX-1735 | Recessed balcony back wall.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 27 | 0.5 | 9
ARC-SITE-CTX-CTX-1736 | Reflective photographed glazing | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 0 0 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1737 | Reflective photographed glazing.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 0 1 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1738 | Reflective photographed glazing.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 0 2 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1739 | Reflective photographed glazing.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 1 0 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1740 | Reflective photographed glazing.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 1 1 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1741 | Reflective photographed glazing.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 1 2 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1742 | Reflective photographed glazing.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 2 0 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1743 | Reflective photographed glazing.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 2 1 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1744 | Reflective photographed glazing.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 2 2 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1745 | Reflective photographed glazing.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 0 0 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1746 | Reflective photographed glazing.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 0 1 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1747 | Reflective photographed glazing.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 0 2 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1748 | Reflective photographed glazing.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 0 3 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1749 | Reflective photographed glazing.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 1 0 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1750 | Reflective photographed glazing.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 1 1 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1751 | Reflective photographed glazing.015 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 1 2 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1752 | Reflective photographed glazing.016 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 1 3 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1753 | Reflective photographed glazing.017 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 2 0 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1754 | Reflective photographed glazing.018 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 2 1 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1755 | Reflective photographed glazing.019 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 2 2 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1756 | Reflective photographed glazing.020 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 2 3 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1757 | Reflective photographed glazing.021 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 0 0 | 8.59 | 0 | 6.69
ARC-SITE-CTX-CTX-1758 | Reflective photographed glazing.022 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 1 0 | 8.59 | 0 | 6.69
ARC-SITE-CTX-CTX-1759 | Reflective photographed glazing.023 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 2 0 | 8.59 | 0 | 6.69
ARC-SITE-CTX-CTX-1760 | Reflective photographed glazing.024 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 0 0 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1761 | Reflective photographed glazing.025 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 0 1 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1762 | Reflective photographed glazing.026 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 0 2 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1763 | Reflective photographed glazing.027 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 0 3 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1764 | Reflective photographed glazing.028 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 1 0 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1765 | Reflective photographed glazing.029 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 1 1 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1766 | Reflective photographed glazing.030 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 1 2 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1767 | Reflective photographed glazing.031 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 1 3 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1768 | Reflective photographed glazing.032 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 2 0 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1769 | Reflective photographed glazing.033 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 2 1 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1770 | Reflective photographed glazing.034 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 2 2 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1771 | Reflective photographed glazing.035 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 2 3 | 6.315 | 0 | 6.69
ARC-SITE-CTX-CTX-1772 | Reflective photographed glazing.036 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 0 0 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1773 | Reflective photographed glazing.037 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 0 1 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1774 | Reflective photographed glazing.038 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 0 2 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1775 | Reflective photographed glazing.039 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 1 0 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1776 | Reflective photographed glazing.040 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 1 1 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1777 | Reflective photographed glazing.041 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 1 2 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1778 | Reflective photographed glazing.042 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 2 0 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1779 | Reflective photographed glazing.043 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 2 1 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1780 | Reflective photographed glazing.044 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 2 2 | 7.1233 | 0 | 6.69
ARC-SITE-CTX-CTX-1781 | Reflective photographed glazing.045 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 0 0 | 13.469 | 0 | 6.69
ARC-SITE-CTX-CTX-1782 | Reflective photographed glazing.046 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 0 1 | 13.469 | 0 | 6.69
ARC-SITE-CTX-CTX-1783 | Reflective photographed glazing.047 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 1 0 | 13.469 | 0 | 6.69
ARC-SITE-CTX-CTX-1784 | Reflective photographed glazing.048 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 1 1 | 13.469 | 0 | 6.69
ARC-SITE-CTX-CTX-1785 | Reflective photographed glazing.049 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 2 0 | 13.469 | 0 | 6.69
ARC-SITE-CTX-CTX-1786 | Reflective photographed glazing.050 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Photographic glazing 2 1 | 13.469 | 0 | 6.69
ARC-SITE-CTX-CTX-1787 | Roof plumbing vent | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.32 | 0.32 | 1.8
ARC-SITE-CTX-CTX-1788 | Roof plumbing vent.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.32 | 0.32 | 1.8
ARC-SITE-CTX-CTX-1789 | Roof plumbing vent.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.32 | 0.32 | 1.8
ARC-SITE-CTX-CTX-1790 | Roof plumbing vent.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.32 | 0.32 | 1.8
ARC-SITE-CTX-CTX-1791 | Rooftop HVAC curb | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Board-formed architectural concrete | 6 | 4 | 0.7
ARC-SITE-CTX-CTX-1792 | Rooftop HVAC curb.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Board-formed architectural concrete | 6 | 4 | 0.7
ARC-SITE-CTX-CTX-1793 | Rooftop HVAC curb.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Board-formed architectural concrete | 6 | 4 | 0.7
ARC-SITE-CTX-CTX-1794 | Rooftop packaged unit | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 5.3 | 3.5 | 2.1
ARC-SITE-CTX-CTX-1795 | Rooftop packaged unit.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 5.3 | 3.5 | 2.1
ARC-SITE-CTX-CTX-1796 | Rooftop packaged unit.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 5.3 | 3.5 | 2.1
ARC-SITE-CTX-CTX-1797 | Round glass patio tabletop | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Anodized dark bronze aluminum | 2.3 | 2.3 | 0.08
ARC-SITE-CTX-CTX-1798 | Round glass patio tabletop.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Anodized dark bronze aluminum | 2.3 | 2.3 | 0.08
ARC-SITE-CTX-CTX-1799 | Round glass patio tabletop.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Anodized dark bronze aluminum | 2.3 | 2.3 | 0.08
ARC-SITE-CTX-CTX-1800 | Round glass patio tabletop.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Anodized dark bronze aluminum | 2.3 | 2.3 | 0.08
ARC-SITE-CTX-CTX-1801 | Side roof fascia | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.55 | 66.333 | 0.55
ARC-SITE-CTX-CTX-1802 | Side roof fascia.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.55 | 66.333 | 0.55
ARC-SITE-CTX-CTX-1803 | Stucco header | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 21.7 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1804 | Stucco header.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 21.7 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1805 | Stucco header.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 21.7 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1806 | Stucco header.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 25.7 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1807 | Stucco header.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 25.7 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1808 | Stucco header.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 25.7 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1809 | Stucco header.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 8.7 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1810 | Stucco header.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 8.7 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1811 | Stucco header.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 8.7 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1812 | Stucco header.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 25.7 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1813 | Stucco header.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 25.7 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1814 | Stucco header.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 25.7 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1815 | Stucco header.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 21.7 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1816 | Stucco header.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 21.7 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1817 | Stucco header.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 21.7 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1818 | Stucco header.015 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 27.158 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1819 | Stucco header.016 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 27.158 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1820 | Stucco header.017 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 27.158 | 0.5 | 0.95
ARC-SITE-CTX-CTX-1821 | Stucco left pier | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1822 | Stucco left pier.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1823 | Stucco left pier.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1824 | Stucco left pier.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1825 | Stucco left pier.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1826 | Stucco left pier.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1827 | Stucco left pier.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1828 | Stucco left pier.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1829 | Stucco left pier.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1830 | Stucco left pier.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1831 | Stucco left pier.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1832 | Stucco left pier.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1833 | Stucco left pier.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1834 | Stucco left pier.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1835 | Stucco left pier.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1836 | Stucco left pier.015 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1837 | Stucco left pier.016 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1838 | Stucco left pier.017 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1839 | Stucco right pier | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1840 | Stucco right pier.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1841 | Stucco right pier.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1842 | Stucco right pier.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1843 | Stucco right pier.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1844 | Stucco right pier.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1845 | Stucco right pier.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1846 | Stucco right pier.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1847 | Stucco right pier.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1848 | Stucco right pier.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1849 | Stucco right pier.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1850 | Stucco right pier.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1851 | Stucco right pier.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1852 | Stucco right pier.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1853 | Stucco right pier.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1854 | Stucco right pier.015 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1855 | Stucco right pier.016 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1856 | Stucco right pier.017 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 0.65 | 0.5 | 9
ARC-SITE-CTX-CTX-1857 | Stucco spandrel | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 21.7 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1858 | Stucco spandrel.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 21.7 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1859 | Stucco spandrel.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 21.7 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1860 | Stucco spandrel.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 25.7 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1861 | Stucco spandrel.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 25.7 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1862 | Stucco spandrel.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 25.7 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1863 | Stucco spandrel.006 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 8.7 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1864 | Stucco spandrel.007 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 8.7 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1865 | Stucco spandrel.008 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 8.7 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1866 | Stucco spandrel.009 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 25.7 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1867 | Stucco spandrel.010 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 25.7 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1868 | Stucco spandrel.011 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 25.7 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1869 | Stucco spandrel.012 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 21.7 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1870 | Stucco spandrel.013 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 21.7 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1871 | Stucco spandrel.014 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 21.7 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1872 | Stucco spandrel.015 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 27.158 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1873 | Stucco spandrel.016 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 27.158 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1874 | Stucco spandrel.017 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 27.158 | 0.5 | 1.25
ARC-SITE-CTX-CTX-1875 | Terracotta balcony planter | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Terracotta planters | 1.1 | 1.1 | 0.9
ARC-SITE-CTX-CTX-1876 | Terracotta balcony planter.001 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Terracotta planters | 1.1 | 1.1 | 0.9
ARC-SITE-CTX-CTX-1877 | Terracotta balcony planter.002 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Terracotta planters | 1.1 | 1.1 | 0.9
ARC-SITE-CTX-CTX-1878 | Terracotta balcony planter.003 | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Terracotta planters | 1.1 | 1.1 | 0.9
ARC-SITE-CTX-CTX-1879 | Tower slit glazing | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 1.15 | 0.08 | 4.6
ARC-SITE-CTX-CTX-1880 | Tower slit glazing.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 1.15 | 0.08 | 4.6
ARC-SITE-CTX-CTX-1881 | Tower slit glazing.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Blue-gray reflective architectural glass | 1.15 | 0.08 | 4.6
ARC-SITE-CTX-CTX-1882 | Tower slit jamb | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.1 | 0.15 | 4.8
ARC-SITE-CTX-CTX-1883 | Tower slit jamb.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.1 | 0.15 | 4.8
ARC-SITE-CTX-CTX-1884 | Tower slit jamb.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.1 | 0.15 | 4.8
ARC-SITE-CTX-CTX-1885 | Tower slit jamb.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.1 | 0.15 | 4.8
ARC-SITE-CTX-CTX-1886 | Tower slit jamb.004 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.1 | 0.15 | 4.8
ARC-SITE-CTX-CTX-1887 | Tower slit jamb.005 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.1 | 0.15 | 4.8
ARC-SITE-CTX-CTX-1888 | Vent flashing cap | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.96 | 0.96 | 0.18
ARC-SITE-CTX-CTX-1889 | Vent flashing cap.001 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.96 | 0.96 | 0.18
ARC-SITE-CTX-CTX-1890 | Vent flashing cap.002 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.96 | 0.96 | 0.18
ARC-SITE-CTX-CTX-1891 | Vent flashing cap.003 | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Anodized dark bronze aluminum | 0.96 | 0.96 | 0.18
ARC-SITE-CTX-CTX-1892 | West stucco elevation | MESH | PHOTOREAL_Architecture | PHOTOREAL_Architecture | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Architecture and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Architecture_Warm off-white mineral stucco | 160.458 | 0.55 | 27
ARC-SITE-CTX-CTX-1893 | Window air conditioner cabinet | MESH | PHOTOREAL_Fixtures_&_Details | PHOTOREAL_Fixtures_&_Details | SITE | SITE | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Fixtures_&_Details and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Painted cream trim | 2.3 | 1.35 | 1.45
CAR-B101-EXG-FRM-0001 | PART_B101_01 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B101 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 24 | 8.5
CAR-B101-EXG-FRM-0002 | PART_B101_02 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B101 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 24 | 8.5
CAR-B101-EXG-FRM-0003 | PART_B101_03 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B101 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 34.8967 | 0.375 | 8.5
CAR-B101-EXG-FRM-0004 | PART_B101_04 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B101 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 8 | 8.5
CAR-B101-EXG-FRM-0005 | PART_B101_05 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B101 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 8 | 8.5
CAR-B101-EXG-FRM-0006 | PART_B101_06 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B101 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 15 | 8.5
CAR-B101-NEW-FRM-0001 | B101_Nailer_1_-1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B101 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B101-NEW-FRM-0002 | B101_Nailer_1_1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B101 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B101-NEW-FRM-0003 | B101_Nailer_2_-1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B101 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B101-NEW-FRM-0004 | B101_Nailer_2_1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B101 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B101-NEW-FRM-0005 | B101_Nailer_3_-1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B101 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B101-NEW-FRM-0006 | B101_Nailer_3_1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B101 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B102-EXG-FRM-0001 | PART_B102_01 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B102 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 24 | 8.5
CAR-B102-EXG-FRM-0002 | PART_B102_02 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B102 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 24 | 8.5
CAR-B102-EXG-FRM-0003 | PART_B102_03 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B102 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 31.2233 | 0.375 | 8.5
CAR-B102-EXG-FRM-0004 | PART_B102_04 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B102 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 8 | 8.5
CAR-B102-EXG-FRM-0005 | PART_B102_05 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B102 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 8 | 8.5
CAR-B102-EXG-FRM-0006 | PART_B102_06 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B102 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 15 | 8.5
CAR-B102-NEW-FRM-0001 | B102_Nailer_1_-1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B102 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B102-NEW-FRM-0002 | B102_Nailer_1_1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B102 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B102-NEW-FRM-0003 | B102_Nailer_2_-1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B102 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B102-NEW-FRM-0004 | B102_Nailer_2_1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B102 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B102-NEW-FRM-0005 | B102_Nailer_3_-1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B102 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B102-NEW-FRM-0006 | B102_Nailer_3_1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B102 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B103-EXG-FRM-0001 | PART_B103_01 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B103 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 24 | 8.5
CAR-B103-EXG-FRM-0002 | PART_B103_02 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B103 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 24 | 8.5
CAR-B103-EXG-FRM-0003 | PART_B103_03 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B103 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 31.9517 | 0.375 | 8.5
CAR-B103-EXG-FRM-0004 | PART_B103_04 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B103 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 8 | 8.5
CAR-B103-EXG-FRM-0005 | PART_B103_05 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B103 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 8 | 8.5
CAR-B103-EXG-FRM-0006 | PART_B103_06 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B103 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 15 | 8.5
CAR-B103-NEW-FRM-0001 | B103_Nailer_1_-1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B103 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B103-NEW-FRM-0002 | B103_Nailer_1_1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B103 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B103-NEW-FRM-0003 | B103_Nailer_2_-1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B103 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B103-NEW-FRM-0004 | B103_Nailer_2_1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B103 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B103-NEW-FRM-0005 | B103_Nailer_3_-1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B103 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B103-NEW-FRM-0006 | B103_Nailer_3_1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B103 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B104-EXG-FRM-0001 | PART_B104_01 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B104 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 24 | 8.5
CAR-B104-EXG-FRM-0002 | PART_B104_02 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B104 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 24 | 8.5
CAR-B104-EXG-FRM-0003 | PART_B104_03 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B104 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 23.8767 | 0.375 | 8.5
CAR-B104-EXG-FRM-0004 | PART_B104_04 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B104 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 8 | 8.5
CAR-B104-EXG-FRM-0005 | PART_B104_05 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B104 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 8 | 8.5
CAR-B104-EXG-FRM-0006 | PART_B104_06 | MESH | Wood_Stud_Partitions | Wood_Stud_Partitions | B104 | L1 | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P2/P3 room layout approximation | DOCUMENT_DERIVED | 06-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Gypsum_TypeX | 0.375 | 15 | 8.5
CAR-B104-NEW-FRM-0001 | B104_Nailer_1_-1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B104 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B104-NEW-FRM-0002 | B104_Nailer_1_1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B104 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B104-NEW-FRM-0003 | B104_Nailer_2_-1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B104 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B104-NEW-FRM-0004 | B104_Nailer_2_1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B104 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B104-NEW-FRM-0005 | B104_Nailer_3_-1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B104 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CAR-B104-NEW-FRM-0006 | B104_Nailer_3_1 | MESH | Wall_Framing_Nailers | Wall_Framing_Nailers | B104 | L1 | CARPENTRY | WALL_FRAMING | NEW | 07 | Patching + Finishes | 505 | 588 | FRAMING_MEMBER |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL patch nailer | DOCUMENT_DERIVED | 06-100 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_GhostWalls_MAT_Wood_Stud | 1 | 1 | 1
CIV-B101-EXG-PIPE-0001 | EX_B101_6in_LATERAL_REMAIN | CURVE | Side_Sewer_Main_6in | Side_Sewer_Main_6in | B101 | L1 | CIVIL | SITE_SEWER | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | PIPE_ROUTE | LATERAL | SOURCE_GEOMETRY | SOURCE_GEOMETRY | SOR/P1.02: existing 6in lateral outside 18in replacement limit | DOCUMENT_DERIVED | 33-300 | PROVISIONAL | 300 | TRUE | LENGTH | 18.504 | FT | CURVE_CENTERLINE | 6 | 0.25 | DOCUMENTED |  |  | MAT_Existing_CastIron_Rust | 0.5521 | 18.5115 | 0.9374
CIV-B102-EXG-PIPE-0001 | EX_B102_6in_LATERAL_REMAIN | CURVE | Side_Sewer_Main_6in | Side_Sewer_Main_6in | B102 | L1 | CIVIL | SITE_SEWER | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | PIPE_ROUTE | LATERAL | SOURCE_GEOMETRY | SOURCE_GEOMETRY | SOR/P1.02: existing 6in lateral outside 18in replacement limit | DOCUMENT_DERIVED | 33-300 | PROVISIONAL | 300 | TRUE | LENGTH | 18.504 | FT | CURVE_CENTERLINE | 6 | 0.25 | DOCUMENTED |  |  | MAT_Existing_CastIron_Rust | 0.5521 | 18.5115 | 0.9374
CIV-B103-EXG-PIPE-0001 | EX_B103_6in_LATERAL_REMAIN | CURVE | Side_Sewer_Main_6in | Side_Sewer_Main_6in | B103 | L1 | CIVIL | SITE_SEWER | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | PIPE_ROUTE | LATERAL | SOURCE_GEOMETRY | SOURCE_GEOMETRY | SOR/P1.02: existing 6in lateral outside 18in replacement limit | DOCUMENT_DERIVED | 33-300 | PROVISIONAL | 300 | TRUE | LENGTH | 18.504 | FT | CURVE_CENTERLINE | 6 | 0.25 | DOCUMENTED |  |  | MAT_Existing_CastIron_Rust | 0.5521 | 18.5115 | 0.9374
CIV-B104-EXG-PIPE-0001 | EX_B104_6in_LATERAL_REMAIN | CURVE | Side_Sewer_Main_6in | Side_Sewer_Main_6in | B104 | L1 | CIVIL | SITE_SEWER | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | PIPE_ROUTE | LATERAL | SOURCE_GEOMETRY | SOURCE_GEOMETRY | SOR/P1.02: existing 6in lateral outside 18in replacement limit | DOCUMENT_DERIVED | 33-300 | PROVISIONAL | 300 | TRUE | LENGTH | 18.504 | FT | CURVE_CENTERLINE | 6 | 0.25 | DOCUMENTED |  |  | MAT_Existing_CastIron_Rust | 0.5521 | 18.5115 | 0.9374
CIV-SITE-EXG-PIPE-0001 | EX_Side_Sewer_Main_8in | CURVE | Side_Sewer_Main_6in | Side_Sewer_Main_6in | SITE | SITE | CIVIL | SITE_SEWER | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | PIPE_ROUTE | MAIN | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3: existing 8in SS main under garages | DOCUMENT_DERIVED | 33-300 | PROVISIONAL | 300 | TRUE | LENGTH | 176.4583 | FT | CURVE_CENTERLINE | 8 |  | NOT_DOCUMENTED |  |  | MAT_Existing_CastIron_Rust | 176.4583 | 0.7188 | 0.7188
CON-B101-DEM-CUT-0001 | TrenchCutter_B101_001 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B101 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B101-DEM-CUT-0002 | TrenchCutter_B101_002 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B101 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B101-DEM-CUT-0003 | TrenchCutter_B101_003 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B101 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B101-DEM-CUT-0004 | TrenchCutter_B101_004 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B101 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B101-DEM-CUT-0005 | TrenchCutter_B101_005 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B101 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B101-DEM-CUT-0006 | TrenchCutter_B101_006 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B101 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B101-DEM-CUT-0007 | TrenchCutter_B101_007 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B101 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B101-DEM-CUT-0008 | TrenchCutter_B101_008 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B101 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B101-DEM-CUT-0009 | TrenchCutter_B101_009 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B101 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B101-DEM-CUT-0010 | TrenchCutter_B101_010 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B101 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B101-DEM-CUT-0011 | TrenchCutter_B101_011 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B101 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B101-NEW-PB-0001 | Pourback_B101_001 | MESH | Concrete_Pourback | Concrete_Pourback | B101 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B101-NEW-PB-0002 | Pourback_B101_002 | MESH | Concrete_Pourback | Concrete_Pourback | B101 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B101-NEW-PB-0003 | Pourback_B101_003 | MESH | Concrete_Pourback | Concrete_Pourback | B101 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B101-NEW-PB-0004 | Pourback_B101_004 | MESH | Concrete_Pourback | Concrete_Pourback | B101 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B101-NEW-PB-0005 | Pourback_B101_005 | MESH | Concrete_Pourback | Concrete_Pourback | B101 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B101-NEW-PB-0006 | Pourback_B101_006 | MESH | Concrete_Pourback | Concrete_Pourback | B101 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B101-NEW-PB-0007 | Pourback_B101_007 | MESH | Concrete_Pourback | Concrete_Pourback | B101 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B101-NEW-PB-0008 | Pourback_B101_008 | MESH | Concrete_Pourback | Concrete_Pourback | B101 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B101-NEW-PB-0009 | Pourback_B101_009 | MESH | Concrete_Pourback | Concrete_Pourback | B101 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B101-NEW-PB-0010 | Pourback_B101_010 | MESH | Concrete_Pourback | Concrete_Pourback | B101 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B101-NEW-PB-0011 | Pourback_B101_011 | MESH | Concrete_Pourback | Concrete_Pourback | B101 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B102-DEM-CUT-0001 | TrenchCutter_B102_012 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B102 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B102-DEM-CUT-0002 | TrenchCutter_B102_013 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B102 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B102-DEM-CUT-0003 | TrenchCutter_B102_014 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B102 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B102-DEM-CUT-0004 | TrenchCutter_B102_015 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B102 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B102-DEM-CUT-0005 | TrenchCutter_B102_016 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B102 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B102-DEM-CUT-0006 | TrenchCutter_B102_017 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B102 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B102-DEM-CUT-0007 | TrenchCutter_B102_018 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B102 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B102-DEM-CUT-0008 | TrenchCutter_B102_019 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B102 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B102-DEM-CUT-0009 | TrenchCutter_B102_020 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B102 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B102-DEM-CUT-0010 | TrenchCutter_B102_021 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B102 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B102-DEM-CUT-0011 | TrenchCutter_B102_022 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B102 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B102-NEW-PB-0001 | Pourback_B102_012 | MESH | Concrete_Pourback | Concrete_Pourback | B102 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B102-NEW-PB-0002 | Pourback_B102_013 | MESH | Concrete_Pourback | Concrete_Pourback | B102 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B102-NEW-PB-0003 | Pourback_B102_014 | MESH | Concrete_Pourback | Concrete_Pourback | B102 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B102-NEW-PB-0004 | Pourback_B102_015 | MESH | Concrete_Pourback | Concrete_Pourback | B102 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B102-NEW-PB-0005 | Pourback_B102_016 | MESH | Concrete_Pourback | Concrete_Pourback | B102 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B102-NEW-PB-0006 | Pourback_B102_017 | MESH | Concrete_Pourback | Concrete_Pourback | B102 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B102-NEW-PB-0007 | Pourback_B102_018 | MESH | Concrete_Pourback | Concrete_Pourback | B102 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B102-NEW-PB-0008 | Pourback_B102_019 | MESH | Concrete_Pourback | Concrete_Pourback | B102 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B102-NEW-PB-0009 | Pourback_B102_020 | MESH | Concrete_Pourback | Concrete_Pourback | B102 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B102-NEW-PB-0010 | Pourback_B102_021 | MESH | Concrete_Pourback | Concrete_Pourback | B102 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B102-NEW-PB-0011 | Pourback_B102_022 | MESH | Concrete_Pourback | Concrete_Pourback | B102 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B103-DEM-CUT-0001 | TrenchCutter_B103_023 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B103 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B103-DEM-CUT-0002 | TrenchCutter_B103_024 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B103 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B103-DEM-CUT-0003 | TrenchCutter_B103_025 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B103 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B103-DEM-CUT-0004 | TrenchCutter_B103_026 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B103 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B103-DEM-CUT-0005 | TrenchCutter_B103_027 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B103 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B103-DEM-CUT-0006 | TrenchCutter_B103_028 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B103 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B103-DEM-CUT-0007 | TrenchCutter_B103_029 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B103 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B103-DEM-CUT-0008 | TrenchCutter_B103_030 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B103 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B103-DEM-CUT-0009 | TrenchCutter_B103_031 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B103 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B103-NEW-PB-0001 | Pourback_B103_023 | MESH | Concrete_Pourback | Concrete_Pourback | B103 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B103-NEW-PB-0002 | Pourback_B103_024 | MESH | Concrete_Pourback | Concrete_Pourback | B103 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B103-NEW-PB-0003 | Pourback_B103_025 | MESH | Concrete_Pourback | Concrete_Pourback | B103 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B103-NEW-PB-0004 | Pourback_B103_026 | MESH | Concrete_Pourback | Concrete_Pourback | B103 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B103-NEW-PB-0005 | Pourback_B103_027 | MESH | Concrete_Pourback | Concrete_Pourback | B103 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B103-NEW-PB-0006 | Pourback_B103_028 | MESH | Concrete_Pourback | Concrete_Pourback | B103 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B103-NEW-PB-0007 | Pourback_B103_029 | MESH | Concrete_Pourback | Concrete_Pourback | B103 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B103-NEW-PB-0008 | Pourback_B103_030 | MESH | Concrete_Pourback | Concrete_Pourback | B103 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B103-NEW-PB-0009 | Pourback_B103_031 | MESH | Concrete_Pourback | Concrete_Pourback | B103 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B104-DEM-CUT-0001 | TrenchCutter_B104_032 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B104 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B104-DEM-CUT-0002 | TrenchCutter_B104_033 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B104 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B104-DEM-CUT-0003 | TrenchCutter_B104_034 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B104 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B104-DEM-CUT-0004 | TrenchCutter_B104_035 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B104 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B104-DEM-CUT-0005 | TrenchCutter_B104_036 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B104 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B104-DEM-CUT-0006 | TrenchCutter_B104_037 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B104 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B104-DEM-CUT-0007 | TrenchCutter_B104_038 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B104 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B104-DEM-CUT-0008 | TrenchCutter_B104_039 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B104 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B104-DEM-CUT-0009 | TrenchCutter_B104_040 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B104 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B104-DEM-CUT-0010 | TrenchCutter_B104_041 | MESH | Concrete_Slab_Trench_Cuts_DEMO | Concrete_Slab_Trench_Cuts_DEMO | B104 | L1 | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | SLAB_CUT_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 route + ~700 SF allowance; verify field route | FIELD_VERIFY_REQUIRED | 03-050 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Trench_Cutter | 1 | 1 | 1
CON-B104-NEW-PB-0001 | Pourback_B104_032 | MESH | Concrete_Pourback | Concrete_Pourback | B104 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B104-NEW-PB-0002 | Pourback_B104_033 | MESH | Concrete_Pourback | Concrete_Pourback | B104 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B104-NEW-PB-0003 | Pourback_B104_034 | MESH | Concrete_Pourback | Concrete_Pourback | B104 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B104-NEW-PB-0004 | Pourback_B104_035 | MESH | Concrete_Pourback | Concrete_Pourback | B104 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B104-NEW-PB-0005 | Pourback_B104_036 | MESH | Concrete_Pourback | Concrete_Pourback | B104 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B104-NEW-PB-0006 | Pourback_B104_037 | MESH | Concrete_Pourback | Concrete_Pourback | B104 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B104-NEW-PB-0007 | Pourback_B104_038 | MESH | Concrete_Pourback | Concrete_Pourback | B104 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B104-NEW-PB-0008 | Pourback_B104_039 | MESH | Concrete_Pourback | Concrete_Pourback | B104 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B104-NEW-PB-0009 | Pourback_B104_040 | MESH | Concrete_Pourback | Concrete_Pourback | B104 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-B104-NEW-PB-0010 | Pourback_B104_041 | MESH | Concrete_Pourback | Concrete_Pourback | B104 | L1 | CONCRETE | SLAB_ON_GRADE | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | POURBACK_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / Addendum: 3000 psi patch with crystalline additive | DOCUMENT_DERIVED | 03-300 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
CON-SITE-NEW-REI-0001 | Rebar_Epoxy_Dowels_#4_EveryOther | CURVE | Rebar_Dowels_&_Grid | Rebar_Dowels_&_Grid | SITE | SITE | CONCRETE | SLAB_REINFORCEMENT | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | REINFORCEMENT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1/brief: every other #4 transverse bar, 4in min epoxy embed | DOCUMENT_DERIVED | 03-210 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Rebar_Steel | 131.3616 | 43.335 | 2
CON-SITE-NEW-REI-0002 | Rebar_Longitudinal_#4_12in_MAX | CURVE | Rebar_Dowels_&_Grid | Rebar_Dowels_&_Grid | SITE | SITE | CONCRETE | SLAB_REINFORCEMENT | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | REINFORCEMENT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1/brief: #4 longitudinal grid <=12in OC | DOCUMENT_DERIVED | 03-210 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 12 |  | NA |  |  | MAT_Rebar_Steel | 130.5253 | 43.2639 | 2
CON-SITE-NEW-REI-0003 | Rebar_Transverse_#4_12in_MAX | CURVE | Rebar_Dowels_&_Grid | Rebar_Dowels_&_Grid | SITE | SITE | CONCRETE | SLAB_REINFORCEMENT | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | REINFORCEMENT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1/brief: #4 transverse grid <=12in OC | DOCUMENT_DERIVED | 03-210 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 12 |  | NA |  |  | MAT_Rebar_Steel | 129.9493 | 42.8755 | 2
DOC-B101-REC-CAL-0001 | CALL_B101_EXIT | FONT | As_Built_Callout_Overlay | As_Built_Callout_Overlay | B101 | L1 | DOCUMENTATION | AS_BUILT | RECORD | 08 | Fixture Reinstall + As-Built | 589 | 672 | CALLOUT |  | DOCUMENTATION | SOURCE_GEOMETRY | Final as-built callout overlay | DOCUMENT_DERIVED | 01-780 | PROVISIONAL | NA | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Grid | 5.6108 | 1.755 | 0
DOC-B102-REC-CAL-0001 | CALL_B102_EXIT | FONT | As_Built_Callout_Overlay | As_Built_Callout_Overlay | B102 | L1 | DOCUMENTATION | AS_BUILT | RECORD | 08 | Fixture Reinstall + As-Built | 589 | 672 | CALLOUT |  | DOCUMENTATION | SOURCE_GEOMETRY | Final as-built callout overlay | DOCUMENT_DERIVED | 01-780 | PROVISIONAL | NA | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Grid | 5.6108 | 1.755 | 0
DOC-B103-REC-CAL-0001 | CALL_B103_EXIT | FONT | As_Built_Callout_Overlay | As_Built_Callout_Overlay | B103 | L1 | DOCUMENTATION | AS_BUILT | RECORD | 08 | Fixture Reinstall + As-Built | 589 | 672 | CALLOUT |  | DOCUMENTATION | SOURCE_GEOMETRY | Final as-built callout overlay | DOCUMENT_DERIVED | 01-780 | PROVISIONAL | NA | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Grid | 5.6108 | 1.755 | 0
DOC-B104-REC-CAL-0001 | CALL_B104_EXIT | FONT | As_Built_Callout_Overlay | As_Built_Callout_Overlay | B104 | L1 | DOCUMENTATION | AS_BUILT | RECORD | 08 | Fixture Reinstall + As-Built | 589 | 672 | CALLOUT |  | DOCUMENTATION | SOURCE_GEOMETRY | Final as-built callout overlay | DOCUMENT_DERIVED | 01-780 | PROVISIONAL | NA | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Grid | 5.6108 | 1.755 | 0
DOC-SITE-REC-CAL-0001 | CALL_GENERAL_VERIFY | FONT | As_Built_Callout_Overlay | As_Built_Callout_Overlay | SITE | SITE | DOCUMENTATION | AS_BUILT | RECORD | 08 | Fixture Reinstall + As-Built | 589 | 672 | CALLOUT |  | DOCUMENTATION | SOURCE_GEOMETRY | WP3 documentation overlay | DOCUMENT_DERIVED | 01-780 | PROVISIONAL | NA | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Grid | 23.1192 | 2.04 | 0
EAR-B101-NEW-BED-0001 | Bedding_B101_001 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B101-NEW-BED-0002 | Bedding_B101_002 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B101-NEW-BED-0003 | Bedding_B101_003 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B101-NEW-BED-0004 | Bedding_B101_004 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B101-NEW-BED-0005 | Bedding_B101_005 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B101-NEW-BED-0006 | Bedding_B101_006 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B101-NEW-BED-0007 | Bedding_B101_007 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B101-NEW-BED-0008 | Bedding_B101_008 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B101-NEW-BED-0009 | Bedding_B101_009 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B101-NEW-BED-0010 | Bedding_B101_010 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B101-NEW-BED-0011 | Bedding_B101_011 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B101-NEW-BED-0012 | PipeZone_B101_001 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B101-NEW-BED-0013 | PipeZone_B101_002 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B101-NEW-BED-0014 | PipeZone_B101_003 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B101-NEW-BED-0015 | PipeZone_B101_004 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B101-NEW-BED-0016 | PipeZone_B101_005 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B101-NEW-BED-0017 | PipeZone_B101_006 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B101-NEW-BED-0018 | PipeZone_B101_007 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B101-NEW-BED-0019 | PipeZone_B101_008 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B101-NEW-BED-0020 | PipeZone_B101_009 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B101-NEW-BED-0021 | PipeZone_B101_010 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B101-NEW-BED-0022 | PipeZone_B101_011 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B101 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B101-NEW-BF-0001 | GeneralBackfill_B101_001 | MESH | General_Trench_Backfill | General_Trench_Backfill | B101 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B101-NEW-BF-0002 | GeneralBackfill_B101_002 | MESH | General_Trench_Backfill | General_Trench_Backfill | B101 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B101-NEW-BF-0003 | GeneralBackfill_B101_003 | MESH | General_Trench_Backfill | General_Trench_Backfill | B101 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B101-NEW-BF-0004 | GeneralBackfill_B101_004 | MESH | General_Trench_Backfill | General_Trench_Backfill | B101 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B101-NEW-BF-0005 | GeneralBackfill_B101_005 | MESH | General_Trench_Backfill | General_Trench_Backfill | B101 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B101-NEW-BF-0006 | GeneralBackfill_B101_006 | MESH | General_Trench_Backfill | General_Trench_Backfill | B101 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B101-NEW-BF-0007 | GeneralBackfill_B101_007 | MESH | General_Trench_Backfill | General_Trench_Backfill | B101 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B101-NEW-BF-0008 | GeneralBackfill_B101_008 | MESH | General_Trench_Backfill | General_Trench_Backfill | B101 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B101-NEW-BF-0009 | GeneralBackfill_B101_009 | MESH | General_Trench_Backfill | General_Trench_Backfill | B101 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B101-NEW-BF-0010 | GeneralBackfill_B101_010 | MESH | General_Trench_Backfill | General_Trench_Backfill | B101 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B101-NEW-BF-0011 | GeneralBackfill_B101_011 | MESH | General_Trench_Backfill | General_Trench_Backfill | B101 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B102-NEW-BED-0001 | Bedding_B102_012 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B102-NEW-BED-0002 | Bedding_B102_013 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B102-NEW-BED-0003 | Bedding_B102_014 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B102-NEW-BED-0004 | Bedding_B102_015 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B102-NEW-BED-0005 | Bedding_B102_016 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B102-NEW-BED-0006 | Bedding_B102_017 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B102-NEW-BED-0007 | Bedding_B102_018 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B102-NEW-BED-0008 | Bedding_B102_019 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B102-NEW-BED-0009 | Bedding_B102_020 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B102-NEW-BED-0010 | Bedding_B102_021 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B102-NEW-BED-0011 | Bedding_B102_022 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B102-NEW-BED-0012 | PipeZone_B102_012 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B102-NEW-BED-0013 | PipeZone_B102_013 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B102-NEW-BED-0014 | PipeZone_B102_014 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B102-NEW-BED-0015 | PipeZone_B102_015 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B102-NEW-BED-0016 | PipeZone_B102_016 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B102-NEW-BED-0017 | PipeZone_B102_017 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B102-NEW-BED-0018 | PipeZone_B102_018 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B102-NEW-BED-0019 | PipeZone_B102_019 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B102-NEW-BED-0020 | PipeZone_B102_020 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B102-NEW-BED-0021 | PipeZone_B102_021 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B102-NEW-BED-0022 | PipeZone_B102_022 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B102 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B102-NEW-BF-0001 | GeneralBackfill_B102_012 | MESH | General_Trench_Backfill | General_Trench_Backfill | B102 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B102-NEW-BF-0002 | GeneralBackfill_B102_013 | MESH | General_Trench_Backfill | General_Trench_Backfill | B102 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B102-NEW-BF-0003 | GeneralBackfill_B102_014 | MESH | General_Trench_Backfill | General_Trench_Backfill | B102 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B102-NEW-BF-0004 | GeneralBackfill_B102_015 | MESH | General_Trench_Backfill | General_Trench_Backfill | B102 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B102-NEW-BF-0005 | GeneralBackfill_B102_016 | MESH | General_Trench_Backfill | General_Trench_Backfill | B102 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B102-NEW-BF-0006 | GeneralBackfill_B102_017 | MESH | General_Trench_Backfill | General_Trench_Backfill | B102 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B102-NEW-BF-0007 | GeneralBackfill_B102_018 | MESH | General_Trench_Backfill | General_Trench_Backfill | B102 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B102-NEW-BF-0008 | GeneralBackfill_B102_019 | MESH | General_Trench_Backfill | General_Trench_Backfill | B102 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B102-NEW-BF-0009 | GeneralBackfill_B102_020 | MESH | General_Trench_Backfill | General_Trench_Backfill | B102 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B102-NEW-BF-0010 | GeneralBackfill_B102_021 | MESH | General_Trench_Backfill | General_Trench_Backfill | B102 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B102-NEW-BF-0011 | GeneralBackfill_B102_022 | MESH | General_Trench_Backfill | General_Trench_Backfill | B102 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B103-NEW-BED-0001 | Bedding_B103_023 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B103-NEW-BED-0002 | Bedding_B103_024 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B103-NEW-BED-0003 | Bedding_B103_025 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B103-NEW-BED-0004 | Bedding_B103_026 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B103-NEW-BED-0005 | Bedding_B103_027 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B103-NEW-BED-0006 | Bedding_B103_028 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B103-NEW-BED-0007 | Bedding_B103_029 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B103-NEW-BED-0008 | Bedding_B103_030 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B103-NEW-BED-0009 | Bedding_B103_031 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B103-NEW-BED-0010 | PipeZone_B103_023 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B103-NEW-BED-0011 | PipeZone_B103_024 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B103-NEW-BED-0012 | PipeZone_B103_025 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B103-NEW-BED-0013 | PipeZone_B103_026 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B103-NEW-BED-0014 | PipeZone_B103_027 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B103-NEW-BED-0015 | PipeZone_B103_028 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B103-NEW-BED-0016 | PipeZone_B103_029 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B103-NEW-BED-0017 | PipeZone_B103_030 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B103-NEW-BED-0018 | PipeZone_B103_031 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B103 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B103-NEW-BF-0001 | GeneralBackfill_B103_023 | MESH | General_Trench_Backfill | General_Trench_Backfill | B103 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B103-NEW-BF-0002 | GeneralBackfill_B103_024 | MESH | General_Trench_Backfill | General_Trench_Backfill | B103 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B103-NEW-BF-0003 | GeneralBackfill_B103_025 | MESH | General_Trench_Backfill | General_Trench_Backfill | B103 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B103-NEW-BF-0004 | GeneralBackfill_B103_026 | MESH | General_Trench_Backfill | General_Trench_Backfill | B103 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B103-NEW-BF-0005 | GeneralBackfill_B103_027 | MESH | General_Trench_Backfill | General_Trench_Backfill | B103 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B103-NEW-BF-0006 | GeneralBackfill_B103_028 | MESH | General_Trench_Backfill | General_Trench_Backfill | B103 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B103-NEW-BF-0007 | GeneralBackfill_B103_029 | MESH | General_Trench_Backfill | General_Trench_Backfill | B103 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B103-NEW-BF-0008 | GeneralBackfill_B103_030 | MESH | General_Trench_Backfill | General_Trench_Backfill | B103 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B103-NEW-BF-0009 | GeneralBackfill_B103_031 | MESH | General_Trench_Backfill | General_Trench_Backfill | B103 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B104-NEW-BED-0001 | Bedding_B104_032 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B104-NEW-BED-0002 | Bedding_B104_033 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B104-NEW-BED-0003 | Bedding_B104_034 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B104-NEW-BED-0004 | Bedding_B104_035 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B104-NEW-BED-0005 | Bedding_B104_036 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B104-NEW-BED-0006 | Bedding_B104_037 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B104-NEW-BED-0007 | Bedding_B104_038 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B104-NEW-BED-0008 | Bedding_B104_039 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B104-NEW-BED-0009 | Bedding_B104_040 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B104-NEW-BED-0010 | Bedding_B104_041 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0/P5.1: min 4in bedding | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Gravel_Bedding | 1 | 1 | 1
EAR-B104-NEW-BED-0011 | PipeZone_B104_032 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B104-NEW-BED-0012 | PipeZone_B104_033 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B104-NEW-BED-0013 | PipeZone_B104_034 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B104-NEW-BED-0014 | PipeZone_B104_035 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B104-NEW-BED-0015 | PipeZone_B104_036 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B104-NEW-BED-0016 | PipeZone_B104_037 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B104-NEW-BED-0017 | PipeZone_B104_038 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B104-NEW-BED-0018 | PipeZone_B104_039 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B104-NEW-BED-0019 | PipeZone_B104_040 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B104-NEW-BED-0020 | PipeZone_B104_041 | MESH | Pipe_Zone_Bedding | Pipe_Zone_Bedding | B104 | L1 | EARTHWORK | TRENCH | NEW | 04 | New ABS Installation | 253 | 336 | BEDDING_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: pipe zone to 12in above top of pipe | DOCUMENT_DERIVED | 31-200 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_PipeZone_Backfill | 1 | 1 | 1
EAR-B104-NEW-BF-0001 | GeneralBackfill_B104_032 | MESH | General_Trench_Backfill | General_Trench_Backfill | B104 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B104-NEW-BF-0002 | GeneralBackfill_B104_033 | MESH | General_Trench_Backfill | General_Trench_Backfill | B104 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B104-NEW-BF-0003 | GeneralBackfill_B104_034 | MESH | General_Trench_Backfill | General_Trench_Backfill | B104 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B104-NEW-BF-0004 | GeneralBackfill_B104_035 | MESH | General_Trench_Backfill | General_Trench_Backfill | B104 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B104-NEW-BF-0005 | GeneralBackfill_B104_036 | MESH | General_Trench_Backfill | General_Trench_Backfill | B104 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B104-NEW-BF-0006 | GeneralBackfill_B104_037 | MESH | General_Trench_Backfill | General_Trench_Backfill | B104 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B104-NEW-BF-0007 | GeneralBackfill_B104_038 | MESH | General_Trench_Backfill | General_Trench_Backfill | B104 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B104-NEW-BF-0008 | GeneralBackfill_B104_039 | MESH | General_Trench_Backfill | General_Trench_Backfill | B104 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B104-NEW-BF-0009 | GeneralBackfill_B104_040 | MESH | General_Trench_Backfill | General_Trench_Backfill | B104 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-B104-NEW-BF-0010 | GeneralBackfill_B104_041 | MESH | General_Trench_Backfill | General_Trench_Backfill | B104 | L1 | EARTHWORK | TRENCH | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | BACKFILL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.0: compacted 6–8in lifts to slab | DOCUMENT_DERIVED | 31-230 | PROVISIONAL | 300 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_General_Backfill | 1 | 1 | 1
EAR-SITE-EXG-SOIL-0001 | Subgrade_Soil_Mass | MESH | Subgrade_&_Soil | Subgrade_&_Soil | SITE | SITE | EARTHWORK | SUBGRADE | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | SOIL_VOLUME |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | SOR excavation depth 2.5–4.5 ft | DOCUMENT_DERIVED | 31-000 | PROVISIONAL | 200 | TRUE | VOLUME | 1 | CF | BBOX_APPROX |  |  | NA |  |  | MAT_Subgrade_Soil | 1 | 1 | 1
FIN-B101-NEW-CTG-0001 | B101_EpoxyPrimer_WetArea | MESH | Vapor_Mitigating_Epoxy_Primer | Vapor_Mitigating_Epoxy_Primer | B101 | L1 | FINISHES | FLOOR_PREP | NEW | 07 | Patching + Finishes | 505 | 588 | COATING_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum: vapor-mitigating epoxy primer | DOCUMENT_DERIVED | 09-600 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Vapor_Mitigating_Epoxy_Primer | 1 | 1 | 1
FIN-B101-REI-CWD-0001 | B101_Kitchen_BaseCab | MESH | Cabinets_&_Countertops | Cabinets_&_Countertops | B101 | L1 | FINISHES | CASEWORK | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | CASEWORK |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Kitchen base cabinet restoration | DOCUMENT_DERIVED | 12-300 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B101_MAT_Wood_Stud | 1 | 1 | 1
FIN-B101-REI-CWD-0002 | B101_Kitchen_Countertop | MESH | Cabinets_&_Countertops | Cabinets_&_Countertops | B101 | L1 | FINISHES | CASEWORK | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | CASEWORK |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Countertop restoration | DOCUMENT_DERIVED | 12-300 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B101_MAT_Porcelain_White | 1 | 1 | 1
FIN-B101-REI-CWD-0003 | B101_LAV_N_Vanity | MESH | Cabinets_&_Countertops | Cabinets_&_Countertops | B101 | L1 | FINISHES | CASEWORK | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | CASEWORK |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Vanity/casework restoration representation | DOCUMENT_DERIVED | 12-300 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B101_MAT_Wood_Stud | 1 | 1 | 1
FIN-B101-REI-CWD-0004 | B101_LAV_S_Vanity | MESH | Cabinets_&_Countertops | Cabinets_&_Countertops | B101 | L1 | FINISHES | CASEWORK | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | CASEWORK |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Vanity/casework restoration representation | DOCUMENT_DERIVED | 12-300 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B101_MAT_Wood_Stud | 1 | 1 | 1
FIN-B101-REI-FIN-0001 | B101_GuestBath_PT6 | MESH | Unit_B101_Finishes | Unit_B101_Finishes | B101 | L1 | FINISHES | UNIT_FINISHES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FINISH |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum custom finish schedule / 4D brief | DOCUMENT_DERIVED | 09-900 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Finish_B101_MAT_PT6_Evolution_Ivory | 1 | 1 | 1
FIN-B101-REI-FIN-0002 | B101_MasterBath_PT8 | MESH | Unit_B101_Finishes | Unit_B101_Finishes | B101 | L1 | FINISHES | UNIT_FINISHES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FINISH |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum custom finish schedule / 4D brief | DOCUMENT_DERIVED | 09-900 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Finish_B101_MAT_PT8_Bernini_Bianco | 1 | 1 | 1
FIN-B101-REI-FIN-0003 | B101_Master_Carpet_C1 | MESH | Unit_B101_Finishes | Unit_B101_Finishes | B101 | L1 | FINISHES | UNIT_FINISHES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FINISH |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum custom finish schedule / 4D brief | DOCUMENT_DERIVED | 09-900 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Finish_B101_MAT_C1_SoftSand_ToneBlue_Carpet | 1 | 1 | 1
FIN-B102-NEW-CTG-0001 | B102_EpoxyPrimer_WetArea | MESH | Vapor_Mitigating_Epoxy_Primer | Vapor_Mitigating_Epoxy_Primer | B102 | L1 | FINISHES | FLOOR_PREP | NEW | 07 | Patching + Finishes | 505 | 588 | COATING_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum: vapor-mitigating epoxy primer | DOCUMENT_DERIVED | 09-600 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Vapor_Mitigating_Epoxy_Primer | 1 | 1 | 1
FIN-B102-REI-CWD-0001 | B102_Kitchen_BaseCab | MESH | Cabinets_&_Countertops | Cabinets_&_Countertops | B102 | L1 | FINISHES | CASEWORK | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | CASEWORK |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Kitchen base cabinet restoration | DOCUMENT_DERIVED | 12-300 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B102_MAT_Wood_Stud | 1 | 1 | 1
FIN-B102-REI-CWD-0002 | B102_Kitchen_Countertop | MESH | Cabinets_&_Countertops | Cabinets_&_Countertops | B102 | L1 | FINISHES | CASEWORK | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | CASEWORK |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Countertop restoration | DOCUMENT_DERIVED | 12-300 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B102_MAT_Porcelain_White | 1 | 1 | 1
FIN-B102-REI-CWD-0003 | B102_LAV_N_Vanity | MESH | Cabinets_&_Countertops | Cabinets_&_Countertops | B102 | L1 | FINISHES | CASEWORK | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | CASEWORK |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Vanity/casework restoration representation | DOCUMENT_DERIVED | 12-300 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B102_MAT_B102_DarkGray_Vanity | 1 | 1 | 1
FIN-B102-REI-CWD-0004 | B102_LAV_S_Vanity | MESH | Cabinets_&_Countertops | Cabinets_&_Countertops | B102 | L1 | FINISHES | CASEWORK | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | CASEWORK |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Vanity/casework restoration representation | DOCUMENT_DERIVED | 12-300 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B102_MAT_B102_DarkGray_Vanity | 1 | 1 | 1
FIN-B102-REI-FIN-0001 | B102_Bedrooms_EHF1 | MESH | Unit_B102_Finishes | Unit_B102_Finishes | B102 | L1 | FINISHES | UNIT_FINISHES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FINISH |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum custom finish schedule / 4D brief | DOCUMENT_DERIVED | 09-900 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Finish_B102_MAT_EHF1_European_WhiteOak | 1 | 1 | 1
FIN-B102-REI-FIN-0002 | B102_GuestBath_PT10 | MESH | Unit_B102_Finishes | Unit_B102_Finishes | B102 | L1 | FINISHES | UNIT_FINISHES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FINISH |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum custom finish schedule / 4D brief | DOCUMENT_DERIVED | 09-900 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Finish_B102_MAT_PT10_Daltile_WhiteOctagon | 1 | 1 | 1
FIN-B102-REI-FIN-0003 | B102_Hall_NS2 | MESH | Unit_B102_Finishes | Unit_B102_Finishes | B102 | L1 | FINISHES | UNIT_FINISHES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FINISH |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum custom finish schedule / 4D brief | DOCUMENT_DERIVED | 09-900 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Finish_B102_MAT_NS2_Pental_Pluvium_Gesso | 1 | 1 | 1
FIN-B102-REI-FIN-0004 | B102_MasterBath_NS3 | MESH | Unit_B102_Finishes | Unit_B102_Finishes | B102 | L1 | FINISHES | UNIT_FINISHES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FINISH |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum custom finish schedule / 4D brief | DOCUMENT_DERIVED | 09-900 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Finish_B102_MAT_NS3_Statuario_Honed | 1 | 1 | 1
FIN-B103-NEW-CTG-0001 | B103_EpoxyPrimer_WetArea | MESH | Vapor_Mitigating_Epoxy_Primer | Vapor_Mitigating_Epoxy_Primer | B103 | L1 | FINISHES | FLOOR_PREP | NEW | 07 | Patching + Finishes | 505 | 588 | COATING_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum: vapor-mitigating epoxy primer | DOCUMENT_DERIVED | 09-600 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Vapor_Mitigating_Epoxy_Primer | 1 | 1 | 1
FIN-B103-REI-CWD-0001 | B103_Kitchen_BaseCab | MESH | Cabinets_&_Countertops | Cabinets_&_Countertops | B103 | L1 | FINISHES | CASEWORK | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | CASEWORK |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Kitchen base cabinet restoration | DOCUMENT_DERIVED | 12-300 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B103_MAT_Wood_Stud | 1 | 1 | 1
FIN-B103-REI-CWD-0002 | B103_Kitchen_Countertop | MESH | Cabinets_&_Countertops | Cabinets_&_Countertops | B103 | L1 | FINISHES | CASEWORK | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | CASEWORK |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Countertop restoration | DOCUMENT_DERIVED | 12-300 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B103_MAT_Porcelain_White | 1 | 1 | 1
FIN-B103-REI-CWD-0003 | B103_LAV_N_Vanity | MESH | Cabinets_&_Countertops | Cabinets_&_Countertops | B103 | L1 | FINISHES | CASEWORK | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | CASEWORK |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Vanity/casework restoration representation | DOCUMENT_DERIVED | 12-300 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B103_MAT_Wood_Stud | 1 | 1 | 1
FIN-B103-REI-CWD-0004 | B103_LAV_S_Vanity | MESH | Cabinets_&_Countertops | Cabinets_&_Countertops | B103 | L1 | FINISHES | CASEWORK | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | CASEWORK |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Vanity/casework restoration representation | DOCUMENT_DERIVED | 12-300 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B103_MAT_Wood_Stud | 1 | 1 | 1
FIN-B103-REI-FIN-0001 | B103_Bath_PT1 | MESH | Unit_B103_Finishes | Unit_B103_Finishes | B103 | L1 | FINISHES | UNIT_FINISHES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FINISH |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum custom finish schedule / 4D brief | DOCUMENT_DERIVED | 09-900 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Finish_B103_MAT_PT1_Shen_WhiteShades | 1 | 1 | 1
FIN-B103-REI-FIN-0002 | B103_HallStudy_PT5 | MESH | Unit_B103_Finishes | Unit_B103_Finishes | B103 | L1 | FINISHES | UNIT_FINISHES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FINISH |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum custom finish schedule / 4D brief | DOCUMENT_DERIVED | 09-900 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Finish_B103_MAT_PT5_Emser_Cabin_Yosemite | 1 | 1 | 1
FIN-B103-REI-FIN-0003 | B103_Laundry_PT4 | MESH | Unit_B103_Finishes | Unit_B103_Finishes | B103 | L1 | FINISHES | UNIT_FINISHES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FINISH |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum custom finish schedule / 4D brief | DOCUMENT_DERIVED | 09-900 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Finish_B103_MAT_PT4_Nobleza_Astorga | 1 | 1 | 1
FIN-B104-NEW-CTG-0001 | B104_EpoxyPrimer_WetArea | MESH | Vapor_Mitigating_Epoxy_Primer | Vapor_Mitigating_Epoxy_Primer | B104 | L1 | FINISHES | FLOOR_PREP | NEW | 07 | Patching + Finishes | 505 | 588 | COATING_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum: vapor-mitigating epoxy primer | DOCUMENT_DERIVED | 09-600 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Vapor_Mitigating_Epoxy_Primer | 1 | 1 | 1
FIN-B104-REI-CWD-0001 | B104_Kitchen_BaseCab | MESH | Cabinets_&_Countertops | Cabinets_&_Countertops | B104 | L1 | FINISHES | CASEWORK | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | CASEWORK |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Kitchen base cabinet restoration | DOCUMENT_DERIVED | 12-300 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B104_MAT_CAB1_DeWils_JustWhite | 1 | 1 | 1
FIN-B104-REI-CWD-0002 | B104_Kitchen_Countertop | MESH | Cabinets_&_Countertops | Cabinets_&_Countertops | B104 | L1 | FINISHES | CASEWORK | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | CASEWORK |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Countertop restoration | DOCUMENT_DERIVED | 12-300 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B104_MAT_QCT1_Pental_Borghini | 1 | 1 | 1
FIN-B104-REI-CWD-0003 | B104_LAV_N_Vanity | MESH | Cabinets_&_Countertops | Cabinets_&_Countertops | B104 | L1 | FINISHES | CASEWORK | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | CASEWORK |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Vanity/casework restoration representation | DOCUMENT_DERIVED | 12-300 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B104_MAT_Wood_Stud | 1 | 1 | 1
FIN-B104-REI-CWD-0004 | B104_LAV_S_Vanity | MESH | Cabinets_&_Countertops | Cabinets_&_Countertops | B104 | L1 | FINISHES | CASEWORK | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | CASEWORK |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Vanity/casework restoration representation | DOCUMENT_DERIVED | 12-300 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B104_MAT_Wood_Stud | 1 | 1 | 1
FIN-B104-REI-FIN-0001 | B104_Bath_NS2 | MESH | Unit_B104_Finishes | Unit_B104_Finishes | B104 | L1 | FINISHES | UNIT_FINISHES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FINISH |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum custom finish schedule / 4D brief | DOCUMENT_DERIVED | 09-900 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Finish_B104_MAT_NS2_Pental_Pluvium_Gesso | 1 | 1 | 1
FIN-B104-REI-FIN-0002 | B104_Hardwood_EHF2 | MESH | Unit_B104_Finishes | Unit_B104_Finishes | B104 | L1 | FINISHES | UNIT_FINISHES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FINISH |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum custom finish schedule / 4D brief | DOCUMENT_DERIVED | 09-900 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Finish_B104_MAT_EHF2_Brentwood_BeechwoodOak | 1 | 1 | 1
FST-B101-NEW-FST-0001 | B101_Firestop_Collar_1 | MESH | Firestop_&_Sleeves | Firestop_&_Sleeves | B101 | L1 | FIRESTOPPING | PENETRATION_FIRESTOP | NEW | 04 | New ABS Installation | 253 | 336 | FIRESTOP |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 UL-listed firestop penetration | DOCUMENT_DERIVED | 07-840 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Firestop_Red | 0.515 | 0.515 | 0.02
FST-B101-NEW-FST-0002 | B101_Firestop_Collar_2 | MESH | Firestop_&_Sleeves | Firestop_&_Sleeves | B101 | L1 | FIRESTOPPING | PENETRATION_FIRESTOP | NEW | 04 | New ABS Installation | 253 | 336 | FIRESTOP |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 UL-listed firestop penetration | DOCUMENT_DERIVED | 07-840 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Firestop_Red | 0.405 | 0.405 | 0.02
FST-B101-NEW-FST-0003 | B101_Firestop_Collar_3 | MESH | Firestop_&_Sleeves | Firestop_&_Sleeves | B101 | L1 | FIRESTOPPING | PENETRATION_FIRESTOP | NEW | 04 | New ABS Installation | 253 | 336 | FIRESTOP |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 UL-listed firestop penetration | DOCUMENT_DERIVED | 07-840 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Firestop_Red | 0.405 | 0.405 | 0.02
FST-B102-NEW-FST-0001 | B102_Firestop_Collar_1 | MESH | Firestop_&_Sleeves | Firestop_&_Sleeves | B102 | L1 | FIRESTOPPING | PENETRATION_FIRESTOP | NEW | 04 | New ABS Installation | 253 | 336 | FIRESTOP |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 UL-listed firestop penetration | DOCUMENT_DERIVED | 07-840 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Firestop_Red | 0.515 | 0.515 | 0.02
FST-B102-NEW-FST-0002 | B102_Firestop_Collar_2 | MESH | Firestop_&_Sleeves | Firestop_&_Sleeves | B102 | L1 | FIRESTOPPING | PENETRATION_FIRESTOP | NEW | 04 | New ABS Installation | 253 | 336 | FIRESTOP |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 UL-listed firestop penetration | DOCUMENT_DERIVED | 07-840 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Firestop_Red | 0.405 | 0.405 | 0.02
FST-B102-NEW-FST-0003 | B102_Firestop_Collar_3 | MESH | Firestop_&_Sleeves | Firestop_&_Sleeves | B102 | L1 | FIRESTOPPING | PENETRATION_FIRESTOP | NEW | 04 | New ABS Installation | 253 | 336 | FIRESTOP |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 UL-listed firestop penetration | DOCUMENT_DERIVED | 07-840 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Firestop_Red | 0.405 | 0.405 | 0.02
FST-B103-NEW-FST-0001 | B103_Firestop_Collar_1 | MESH | Firestop_&_Sleeves | Firestop_&_Sleeves | B103 | L1 | FIRESTOPPING | PENETRATION_FIRESTOP | NEW | 04 | New ABS Installation | 253 | 336 | FIRESTOP |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 UL-listed firestop penetration | DOCUMENT_DERIVED | 07-840 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Firestop_Red | 0.515 | 0.515 | 0.02
FST-B103-NEW-FST-0002 | B103_Firestop_Collar_2 | MESH | Firestop_&_Sleeves | Firestop_&_Sleeves | B103 | L1 | FIRESTOPPING | PENETRATION_FIRESTOP | NEW | 04 | New ABS Installation | 253 | 336 | FIRESTOP |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 UL-listed firestop penetration | DOCUMENT_DERIVED | 07-840 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Firestop_Red | 0.405 | 0.405 | 0.02
FST-B103-NEW-FST-0003 | B103_Firestop_Collar_3 | MESH | Firestop_&_Sleeves | Firestop_&_Sleeves | B103 | L1 | FIRESTOPPING | PENETRATION_FIRESTOP | NEW | 04 | New ABS Installation | 253 | 336 | FIRESTOP |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 UL-listed firestop penetration | DOCUMENT_DERIVED | 07-840 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Firestop_Red | 0.405 | 0.405 | 0.02
FST-B104-NEW-FST-0001 | B104_Firestop_Collar_1 | MESH | Firestop_&_Sleeves | Firestop_&_Sleeves | B104 | L1 | FIRESTOPPING | PENETRATION_FIRESTOP | NEW | 04 | New ABS Installation | 253 | 336 | FIRESTOP |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 UL-listed firestop penetration | DOCUMENT_DERIVED | 07-840 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Firestop_Red | 0.515 | 0.515 | 0.02
FST-B104-NEW-FST-0002 | B104_Firestop_Collar_2 | MESH | Firestop_&_Sleeves | Firestop_&_Sleeves | B104 | L1 | FIRESTOPPING | PENETRATION_FIRESTOP | NEW | 04 | New ABS Installation | 253 | 336 | FIRESTOP |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 UL-listed firestop penetration | DOCUMENT_DERIVED | 07-840 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Firestop_Red | 0.405 | 0.405 | 0.02
FST-B104-NEW-FST-0003 | B104_Firestop_Collar_3 | MESH | Firestop_&_Sleeves | Firestop_&_Sleeves | B104 | L1 | FIRESTOPPING | PENETRATION_FIRESTOP | NEW | 04 | New ABS Installation | 253 | 336 | FIRESTOP |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 UL-listed firestop penetration | DOCUMENT_DERIVED | 07-840 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Firestop_Red | 0.405 | 0.405 | 0.02
GEN-B101-ANI-ANI-0001 | CUT_EX_CI_B101_BR2_lav_n | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B101_BR2_lav_n | PLM-B101-DEM-PIPE-0001 | ANIM_Laser_Cut | 8.5196 | 3.9616 | 0.0666
GEN-B101-ANI-ANI-0002 | CUT_EX_CI_B101_BR2_lav_s | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B101_BR2_lav_s | PLM-B101-DEM-PIPE-0002 | ANIM_Laser_Cut | 2.5615 | 2.4308 | 0.0666
GEN-B101-ANI-ANI-0003 | CUT_EX_CI_B101_BR3_bath_n | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B101_BR3_bath_n | PLM-B101-DEM-PIPE-0003 | ANIM_Laser_Cut | 5.0376 | 0.8625 | 0.0666
GEN-B101-ANI-ANI-0004 | CUT_EX_CI_B101_BR3_bath_s | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B101_BR3_bath_s | PLM-B101-DEM-PIPE-0004 | ANIM_Laser_Cut | 4.0975 | 0.862 | 0.0666
GEN-B101-ANI-ANI-0005 | CUT_EX_CI_B101_BR3_laundry | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B101_BR3_laundry | PLM-B101-DEM-PIPE-0005 | ANIM_Laser_Cut | 0.9692 | 0.4531 | 0.0666
GEN-B101-ANI-ANI-0006 | CUT_EX_CI_B101_LAT6_REPLACE | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED | 6 |  | NA | EX_CI_B101_LAT6_REPLACE | PLM-B101-DEM-PIPE-0006 | ANIM_Laser_Cut | 0.07 | 1.5 | 0.0666
GEN-B101-ANI-ANI-0007 | CUT_EX_CI_B101_MAIN4 | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED | 4 |  | NA | EX_CI_B101_MAIN4 | PLM-B101-DEM-PIPE-0007 | ANIM_Laser_Cut | 13.7156 | 39.0087 | 0.0666
GEN-B101-ANI-ANI-0008 | Protection_Roll_B101 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 02 | Staging + Fixture Removal | 85 | 168 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Floor_Protection | 0.028 | 5 | 0.035
GEN-B101-ANI-SEG-0001 | CUT_GROWTH_EX_CI_B101_BR2_lav_n_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 3.42 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B101_BR2_lav_n | PLM-B101-DEM-PIPE-0001 | ANIM_Laser_Cut | 0.07 | 0.0034 | 0.07
GEN-B101-ANI-SEG-0002 | CUT_GROWTH_EX_CI_B101_BR2_lav_n_001 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 8.4976 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B101_BR2_lav_n | PLM-B101-DEM-PIPE-0001 | ANIM_Laser_Cut | 0.0127 | 0.0704 | 0.07
GEN-B101-ANI-SEG-0003 | CUT_GROWTH_EX_CI_B101_BR2_lav_s_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 3.4614 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B101_BR2_lav_s | PLM-B101-DEM-PIPE-0002 | ANIM_Laser_Cut | 0.0506 | 0.0532 | 0.07
GEN-B101-ANI-SEG-0004 | CUT_GROWTH_EX_CI_B101_BR3_bath_n_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | BATH_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 5.0889 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B101_BR3_bath_n | PLM-B101-DEM-PIPE-0003 | ANIM_Laser_Cut | 0.0159 | 0.0699 | 0.07
GEN-B101-ANI-SEG-0005 | CUT_GROWTH_EX_CI_B101_BR3_bath_s_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | BATH_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 4.1605 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B101_BR3_bath_s | PLM-B101-DEM-PIPE-0004 | ANIM_Laser_Cut | 0.0174 | 0.0695 | 0.07
GEN-B101-ANI-SEG-0006 | CUT_GROWTH_EX_CI_B101_BR3_laundry_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 1.0194 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B101_BR3_laundry | PLM-B101-DEM-PIPE-0005 | ANIM_Laser_Cut | 0.0276 | 0.0651 | 0.07
GEN-B101-ANI-SEG-0007 | CUT_GROWTH_EX_CI_B101_LAT6_REPLACE_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | LATERAL | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 1.5 | FT | GROWTH_LENGTH | 6 |  | NOT_DOCUMENTED | EX_CI_B101_LAT6_REPLACE | PLM-B101-DEM-PIPE-0006 | ANIM_Laser_Cut | 0.07 | 0.0015 | 0.07
GEN-B101-ANI-SEG-0008 | CUT_GROWTH_EX_CI_B101_MAIN4_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 17.7024 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B101_MAIN4 | PLM-B101-DEM-PIPE-0007 | ANIM_Laser_Cut | 0.0582 | 0.0653 | 0.07
GEN-B101-ANI-SEG-0009 | CUT_GROWTH_EX_CI_B101_MAIN4_001 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 11.0733 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B101_MAIN4 | PLM-B101-DEM-PIPE-0007 | ANIM_Laser_Cut | 0.07 | 0.0111 | 0.07
GEN-B101-ANI-SEG-0010 | CUT_GROWTH_EX_CI_B101_MAIN4_002 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 4.76 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B101_MAIN4 | PLM-B101-DEM-PIPE-0007 | ANIM_Laser_Cut | 0.07 | 0.0048 | 0.07
GEN-B101-ANI-SEG-0011 | CUT_GROWTH_EX_CI_B101_MAIN4_003 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 7.0733 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B101_MAIN4 | PLM-B101-DEM-PIPE-0007 | ANIM_Laser_Cut | 0.07 | 0.0071 | 0.07
GEN-B101-ANI-SEG-0012 | CUT_GROWTH_EX_CI_B101_MAIN4_004 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B101 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 4.8133 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B101_MAIN4 | PLM-B101-DEM-PIPE-0007 | ANIM_Laser_Cut | 0.07 | 0.0048 | 0.07
GEN-B101-TMP-PRO-0001 | B101_DustPartition | MESH | Temporary_Protection | Temporary_Protection | B101 | L1 | GENERAL_REQUIREMENTS | TEMPORARY_PROTECTION | TEMPORARY | 02 | Staging + Fixture Removal | 85 | 168 | PROTECTION_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Phase 2 floor-to-ceiling dustproof partition | DOCUMENT_DERIVED | 01-500 | PROVISIONAL | 200 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Temp_Dust_Poly | 1 | 1 | 1
GEN-B101-TMP-PRO-0002 | B101_WalkoffMat | MESH | Temporary_Protection | Temporary_Protection | B101 | L1 | GENERAL_REQUIREMENTS | TEMPORARY_PROTECTION | TEMPORARY | 02 | Staging + Fixture Removal | 85 | 168 | PROTECTION_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Temporary walk-off mat | DOCUMENT_DERIVED | 01-500 | PROVISIONAL | 200 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Walkoff | 1 | 1 | 1
GEN-B102-ANI-ANI-0001 | CUT_EX_CI_B102_BR2_lav_n | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B102_BR2_lav_n | PLM-B102-DEM-PIPE-0001 | ANIM_Laser_Cut | 6.2652 | 3.7967 | 0.0666
GEN-B102-ANI-ANI-0002 | CUT_EX_CI_B102_BR2_lav_s | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B102_BR2_lav_s | PLM-B102-DEM-PIPE-0002 | ANIM_Laser_Cut | 5.9861 | 2.6426 | 0.0666
GEN-B102-ANI-ANI-0003 | CUT_EX_CI_B102_BR3_bath_n | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B102_BR3_bath_n | PLM-B102-DEM-PIPE-0003 | ANIM_Laser_Cut | 4.6217 | 1.2578 | 0.0666
GEN-B102-ANI-ANI-0004 | CUT_EX_CI_B102_BR3_bath_s | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B102_BR3_bath_s | PLM-B102-DEM-PIPE-0004 | ANIM_Laser_Cut | 4.8967 | 1.6532 | 0.0666
GEN-B102-ANI-ANI-0005 | CUT_EX_CI_B102_BR3_kitchen | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B102_BR3_kitchen | PLM-B102-DEM-PIPE-0005 | ANIM_Laser_Cut | 1.1241 | 0.8336 | 0.0666
GEN-B102-ANI-ANI-0006 | CUT_EX_CI_B102_BR3_laundry | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B102_BR3_laundry | PLM-B102-DEM-PIPE-0006 | ANIM_Laser_Cut | 1.1069 | 0.4542 | 0.0666
GEN-B102-ANI-ANI-0007 | CUT_EX_CI_B102_LAT6_REPLACE | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED | 6 |  | NA | EX_CI_B102_LAT6_REPLACE | PLM-B102-DEM-PIPE-0007 | ANIM_Laser_Cut | 0.07 | 1.5 | 0.0666
GEN-B102-ANI-ANI-0008 | CUT_EX_CI_B102_MAIN4 | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED | 4 |  | NA | EX_CI_B102_MAIN4 | PLM-B102-DEM-PIPE-0008 | ANIM_Laser_Cut | 22.9732 | 39.4223 | 0.0666
GEN-B102-ANI-ANI-0009 | Protection_Roll_B102 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 02 | Staging + Fixture Removal | 85 | 168 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Floor_Protection | 0.028 | 5 | 0.035
GEN-B102-ANI-SEG-0001 | CUT_GROWTH_EX_CI_B102_BR2_lav_n_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 7.264 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B102_BR2_lav_n | PLM-B102-DEM-PIPE-0001 | ANIM_Laser_Cut | 0.0422 | 0.0638 | 0.07
GEN-B102-ANI-SEG-0002 | CUT_GROWTH_EX_CI_B102_BR2_lav_s_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 6.4923 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B102_BR2_lav_s | PLM-B102-DEM-PIPE-0002 | ANIM_Laser_Cut | 0.0338 | 0.0668 | 0.07
GEN-B102-ANI-SEG-0003 | CUT_GROWTH_EX_CI_B102_BR3_bath_n_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | BATH_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 4.7555 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B102_BR3_bath_n | PLM-B102-DEM-PIPE-0003 | ANIM_Laser_Cut | 0.0221 | 0.069 | 0.07
GEN-B102-ANI-SEG-0004 | CUT_GROWTH_EX_CI_B102_BR3_bath_s_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | BATH_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 5.1267 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B102_BR3_bath_s | PLM-B102-DEM-PIPE-0004 | ANIM_Laser_Cut | 0.0265 | 0.0681 | 0.07
GEN-B102-ANI-SEG-0005 | CUT_GROWTH_EX_CI_B102_BR3_kitchen_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | KITCHEN_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 1.333 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B102_BR3_kitchen | PLM-B102-DEM-PIPE-0005 | ANIM_Laser_Cut | 0.0419 | 0.0577 | 0.07
GEN-B102-ANI-SEG-0006 | CUT_GROWTH_EX_CI_B102_BR3_laundry_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 1.1508 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B102_BR3_laundry | PLM-B102-DEM-PIPE-0006 | ANIM_Laser_Cut | 0.0247 | 0.0663 | 0.07
GEN-B102-ANI-SEG-0007 | CUT_GROWTH_EX_CI_B102_LAT6_REPLACE_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | LATERAL | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 1.5 | FT | GROWTH_LENGTH | 6 |  | NOT_DOCUMENTED | EX_CI_B102_LAT6_REPLACE | PLM-B102-DEM-PIPE-0007 | ANIM_Laser_Cut | 0.07 | 0.0015 | 0.07
GEN-B102-ANI-SEG-0008 | CUT_GROWTH_EX_CI_B102_MAIN4_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 18.5273 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B102_MAIN4 | PLM-B102-DEM-PIPE-0008 | ANIM_Laser_Cut | 0.0596 | 0.0652 | 0.07
GEN-B102-ANI-SEG-0009 | CUT_GROWTH_EX_CI_B102_MAIN4_001 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 9.1599 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B102_MAIN4 | PLM-B102-DEM-PIPE-0008 | ANIM_Laser_Cut | 0.0702 | 0.0255 | 0.07
GEN-B102-ANI-SEG-0010 | CUT_GROWTH_EX_CI_B102_MAIN4_002 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 5.4163 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B102_MAIN4 | PLM-B102-DEM-PIPE-0008 | ANIM_Laser_Cut | 0.07 | 0.0159 | 0.07
GEN-B102-ANI-SEG-0011 | CUT_GROWTH_EX_CI_B102_MAIN4_003 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 8.4293 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B102_MAIN4 | PLM-B102-DEM-PIPE-0008 | ANIM_Laser_Cut | 0.0705 | 0.0151 | 0.07
GEN-B102-ANI-SEG-0012 | CUT_GROWTH_EX_CI_B102_MAIN4_004 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B102 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 6.8909 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B102_MAIN4 | PLM-B102-DEM-PIPE-0008 | ANIM_Laser_Cut | 0.0527 | 0.056 | 0.07
GEN-B102-TMP-PRO-0001 | B102_DustPartition | MESH | Temporary_Protection | Temporary_Protection | B102 | L1 | GENERAL_REQUIREMENTS | TEMPORARY_PROTECTION | TEMPORARY | 02 | Staging + Fixture Removal | 85 | 168 | PROTECTION_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Phase 2 floor-to-ceiling dustproof partition | DOCUMENT_DERIVED | 01-500 | PROVISIONAL | 200 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Temp_Dust_Poly | 1 | 1 | 1
GEN-B102-TMP-PRO-0002 | B102_WalkoffMat | MESH | Temporary_Protection | Temporary_Protection | B102 | L1 | GENERAL_REQUIREMENTS | TEMPORARY_PROTECTION | TEMPORARY | 02 | Staging + Fixture Removal | 85 | 168 | PROTECTION_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Temporary walk-off mat | DOCUMENT_DERIVED | 01-500 | PROVISIONAL | 200 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Walkoff | 1 | 1 | 1
GEN-B103-ANI-ANI-0001 | CUT_EX_CI_B103_BR2_lav_n | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B103_BR2_lav_n | PLM-B103-DEM-PIPE-0001 | ANIM_Laser_Cut | 5.2745 | 3.9196 | 0.0666
GEN-B103-ANI-ANI-0002 | CUT_EX_CI_B103_BR2_lav_s | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B103_BR2_lav_s | PLM-B103-DEM-PIPE-0002 | ANIM_Laser_Cut | 8.8316 | 2.4476 | 0.0666
GEN-B103-ANI-ANI-0003 | CUT_EX_CI_B103_BR3_bath_n | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B103_BR3_bath_n | PLM-B103-DEM-PIPE-0003 | ANIM_Laser_Cut | 5.7885 | 0.4665 | 0.0666
GEN-B103-ANI-ANI-0004 | CUT_EX_CI_B103_BR3_bath_s | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B103_BR3_bath_s | PLM-B103-DEM-PIPE-0004 | ANIM_Laser_Cut | 7.7188 | 0.863 | 0.0666
GEN-B103-ANI-ANI-0005 | CUT_EX_CI_B103_BR3_laundry | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B103_BR3_laundry | PLM-B103-DEM-PIPE-0005 | ANIM_Laser_Cut | 0.3157 | 0.2514 | 0.0666
GEN-B103-ANI-ANI-0006 | CUT_EX_CI_B103_LAT6_REPLACE | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED | 6 |  | NA | EX_CI_B103_LAT6_REPLACE | PLM-B103-DEM-PIPE-0006 | ANIM_Laser_Cut | 0.07 | 1.5 | 0.0666
GEN-B103-ANI-ANI-0007 | CUT_EX_CI_B103_MAIN4 | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED | 4 |  | NA | EX_CI_B103_MAIN4 | PLM-B103-DEM-PIPE-0007 | ANIM_Laser_Cut | 9.975 | 27.5504 | 0.0666
GEN-B103-ANI-ANI-0008 | Protection_Roll_B103 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 02 | Staging + Fixture Removal | 85 | 168 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Floor_Protection | 0.028 | 5 | 0.035
GEN-B103-ANI-SEG-0001 | CUT_GROWTH_EX_CI_B103_BR2_lav_n_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 6.5045 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B103_BR2_lav_n | PLM-B103-DEM-PIPE-0001 | ANIM_Laser_Cut | 0.0468 | 0.0602 | 0.07
GEN-B103-ANI-SEG-0002 | CUT_GROWTH_EX_CI_B103_BR2_lav_s_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 9.129 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B103_BR2_lav_s | PLM-B103-DEM-PIPE-0002 | ANIM_Laser_Cut | 0.0271 | 0.07 | 0.07
GEN-B103-ANI-SEG-0003 | CUT_GROWTH_EX_CI_B103_BR3_bath_n_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | BATH_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 5.7973 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B103_BR3_bath_n | PLM-B103-DEM-PIPE-0003 | ANIM_Laser_Cut | 0.0106 | 0.0702 | 0.07
GEN-B103-ANI-SEG-0004 | CUT_GROWTH_EX_CI_B103_BR3_bath_s_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | BATH_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 7.7524 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B103_BR3_bath_s | PLM-B103-DEM-PIPE-0004 | ANIM_Laser_Cut | 0.0149 | 0.0704 | 0.07
GEN-B103-ANI-SEG-0005 | CUT_GROWTH_EX_CI_B103_BR3_laundry_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 0.337 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B103_BR3_laundry | PLM-B103-DEM-PIPE-0005 | ANIM_Laser_Cut | 0.0406 | 0.0574 | 0.07
GEN-B103-ANI-SEG-0006 | CUT_GROWTH_EX_CI_B103_LAT6_REPLACE_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | LATERAL | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 1.5 | FT | GROWTH_LENGTH | 6 |  | NOT_DOCUMENTED | EX_CI_B103_LAT6_REPLACE | PLM-B103-DEM-PIPE-0006 | ANIM_Laser_Cut | 0.07 | 0.0015 | 0.07
GEN-B103-ANI-SEG-0007 | CUT_GROWTH_EX_CI_B103_MAIN4_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 14.1432 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B103_MAIN4 | PLM-B103-DEM-PIPE-0007 | ANIM_Laser_Cut | 0.0598 | 0.0592 | 0.07
GEN-B103-ANI-SEG-0008 | CUT_GROWTH_EX_CI_B103_MAIN4_001 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 5.1567 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B103_MAIN4 | PLM-B103-DEM-PIPE-0007 | ANIM_Laser_Cut | 0.07 | 0.0052 | 0.07
GEN-B103-ANI-SEG-0009 | CUT_GROWTH_EX_CI_B103_MAIN4_002 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 7.47 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B103_MAIN4 | PLM-B103-DEM-PIPE-0007 | ANIM_Laser_Cut | 0.07 | 0.0075 | 0.07
GEN-B103-ANI-SEG-0010 | CUT_GROWTH_EX_CI_B103_MAIN4_003 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B103 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 4.8133 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B103_MAIN4 | PLM-B103-DEM-PIPE-0007 | ANIM_Laser_Cut | 0.07 | 0.0048 | 0.07
GEN-B103-TMP-PRO-0001 | B103_DustPartition | MESH | Temporary_Protection | Temporary_Protection | B103 | L1 | GENERAL_REQUIREMENTS | TEMPORARY_PROTECTION | TEMPORARY | 02 | Staging + Fixture Removal | 85 | 168 | PROTECTION_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Phase 2 floor-to-ceiling dustproof partition | DOCUMENT_DERIVED | 01-500 | PROVISIONAL | 200 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Temp_Dust_Poly | 1 | 1 | 1
GEN-B103-TMP-PRO-0002 | B103_WalkoffMat | MESH | Temporary_Protection | Temporary_Protection | B103 | L1 | GENERAL_REQUIREMENTS | TEMPORARY_PROTECTION | TEMPORARY | 02 | Staging + Fixture Removal | 85 | 168 | PROTECTION_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Temporary walk-off mat | DOCUMENT_DERIVED | 01-500 | PROVISIONAL | 200 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Walkoff | 1 | 1 | 1
GEN-B104-ANI-ANI-0001 | CUT_EX_CI_B104_BR2_lav_n | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B104_BR2_lav_n | PLM-B104-DEM-PIPE-0001 | ANIM_Laser_Cut | 3.508 | 3.91 | 0.0666
GEN-B104-ANI-ANI-0002 | CUT_EX_CI_B104_BR2_lav_s | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B104_BR2_lav_s | PLM-B104-DEM-PIPE-0002 | ANIM_Laser_Cut | 3.1763 | 1.8459 | 0.0666
GEN-B104-ANI-ANI-0003 | CUT_EX_CI_B104_BR3_bath_n | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B104_BR3_bath_n | PLM-B104-DEM-PIPE-0003 | ANIM_Laser_Cut | 3.4638 | 0.4662 | 0.0666
GEN-B104-ANI-ANI-0004 | CUT_EX_CI_B104_BR3_bath_s | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B104_BR3_bath_s | PLM-B104-DEM-PIPE-0004 | ANIM_Laser_Cut | 2.2174 | 0.6626 | 0.0666
GEN-B104-ANI-ANI-0005 | CUT_EX_CI_B104_BR3_laundry | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA | EX_CI_B104_BR3_laundry | PLM-B104-DEM-PIPE-0005 | ANIM_Laser_Cut | 10.1292 | 0.07 | 0.0666
GEN-B104-ANI-ANI-0006 | CUT_EX_CI_B104_LAT6_REPLACE | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED | 6 |  | NA | EX_CI_B104_LAT6_REPLACE | PLM-B104-DEM-PIPE-0006 | ANIM_Laser_Cut | 0.07 | 1.5 | 0.0666
GEN-B104-ANI-ANI-0007 | CUT_EX_CI_B104_MAIN4 | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | DEMOLITION_ROUTE_DUPLICATE | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED | 4 |  | NA | EX_CI_B104_MAIN4 | PLM-B104-DEM-PIPE-0007 | ANIM_Laser_Cut | 10.71 | 39.3936 | 0.0666
GEN-B104-ANI-ANI-0008 | Protection_Roll_B104 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 02 | Staging + Fixture Removal | 85 | 168 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Floor_Protection | 0.028 | 5 | 0.035
GEN-B104-ANI-SEG-0001 | CUT_GROWTH_EX_CI_B104_BR2_lav_n_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 5.1834 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B104_BR2_lav_n | PLM-B104-DEM-PIPE-0001 | ANIM_Laser_Cut | 0.0556 | 0.0505 | 0.07
GEN-B104-ANI-SEG-0002 | CUT_GROWTH_EX_CI_B104_BR2_lav_s_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 3.6134 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B104_BR2_lav_s | PLM-B104-DEM-PIPE-0002 | ANIM_Laser_Cut | 0.0377 | 0.0626 | 0.07
GEN-B104-ANI-SEG-0003 | CUT_GROWTH_EX_CI_B104_BR3_bath_n_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | BATH_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 3.4785 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B104_BR3_bath_n | PLM-B104-DEM-PIPE-0003 | ANIM_Laser_Cut | 0.0114 | 0.0699 | 0.07
GEN-B104-ANI-SEG-0004 | CUT_GROWTH_EX_CI_B104_BR3_bath_s_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | BATH_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 2.2782 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B104_BR3_bath_s | PLM-B104-DEM-PIPE-0004 | ANIM_Laser_Cut | 0.0205 | 0.0682 | 0.07
GEN-B104-ANI-SEG-0005 | CUT_GROWTH_EX_CI_B104_BR3_laundry_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 10.1292 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | EX_CI_B104_BR3_laundry | PLM-B104-DEM-PIPE-0005 | ANIM_Laser_Cut | 0.0101 | 0.07 | 0.07
GEN-B104-ANI-SEG-0006 | CUT_GROWTH_EX_CI_B104_LAT6_REPLACE_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | LATERAL | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 1.5 | FT | GROWTH_LENGTH | 6 |  | NOT_DOCUMENTED | EX_CI_B104_LAT6_REPLACE | PLM-B104-DEM-PIPE-0006 | ANIM_Laser_Cut | 0.07 | 0.0015 | 0.07
GEN-B104-ANI-SEG-0007 | CUT_GROWTH_EX_CI_B104_MAIN4_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 15.7838 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B104_MAIN4 | PLM-B104-DEM-PIPE-0007 | ANIM_Laser_Cut | 0.0623 | 0.0589 | 0.07
GEN-B104-ANI-SEG-0008 | CUT_GROWTH_EX_CI_B104_MAIN4_001 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 10.4783 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B104_MAIN4 | PLM-B104-DEM-PIPE-0007 | ANIM_Laser_Cut | 0.07 | 0.0105 | 0.07
GEN-B104-ANI-SEG-0009 | CUT_GROWTH_EX_CI_B104_MAIN4_002 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 4.9583 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B104_MAIN4 | PLM-B104-DEM-PIPE-0007 | ANIM_Laser_Cut | 0.07 | 0.005 | 0.07
GEN-B104-ANI-SEG-0010 | CUT_GROWTH_EX_CI_B104_MAIN4_003 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 7.47 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B104_MAIN4 | PLM-B104-DEM-PIPE-0007 | ANIM_Laser_Cut | 0.07 | 0.0075 | 0.07
GEN-B104-ANI-SEG-0011 | CUT_GROWTH_EX_CI_B104_MAIN4_004 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | B104 | L1 | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 4.8133 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | EX_CI_B104_MAIN4 | PLM-B104-DEM-PIPE-0007 | ANIM_Laser_Cut | 0.07 | 0.0048 | 0.07
GEN-B104-TMP-PRO-0001 | B104_DustPartition | MESH | Temporary_Protection | Temporary_Protection | B104 | L1 | GENERAL_REQUIREMENTS | TEMPORARY_PROTECTION | TEMPORARY | 02 | Staging + Fixture Removal | 85 | 168 | PROTECTION_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Phase 2 floor-to-ceiling dustproof partition | DOCUMENT_DERIVED | 01-500 | PROVISIONAL | 200 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Temp_Dust_Poly | 1 | 1 | 1
GEN-B104-TMP-PRO-0002 | B104_WalkoffMat | MESH | Temporary_Protection | Temporary_Protection | B104 | L1 | GENERAL_REQUIREMENTS | TEMPORARY_PROTECTION | TEMPORARY | 02 | Staging + Fixture Removal | 85 | 168 | PROTECTION_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Temporary walk-off mat | DOCUMENT_DERIVED | 01-500 | PROVISIONAL | 200 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Walkoff | 1 | 1 | 1
GEN-SITE-ANI-ANI-0001 | Agency 4D Camera | CAMERA | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
GEN-SITE-ANI-ANI-0002 | CAMERA_Target | EMPTY | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
GEN-SITE-ANI-ANI-0003 | Completion warm light | LIGHT | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
GEN-SITE-ANI-ANI-0004 | Completion warm light.001 | LIGHT | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
GEN-SITE-ANI-ANI-0005 | Completion warm light.002 | LIGHT | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
GEN-SITE-ANI-ANI-0006 | Completion warm light.003 | LIGHT | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
GEN-SITE-ANI-ANI-0007 | GridX-10 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0008 | GridX-20 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0009 | GridX0 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0010 | GridX10 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0011 | GridX100 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0012 | GridX110 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0013 | GridX120 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0014 | GridX130 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0015 | GridX140 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0016 | GridX150 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0017 | GridX160 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0018 | GridX170 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0019 | GridX180 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0020 | GridX190 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0021 | GridX20 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0022 | GridX200 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0023 | GridX30 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0024 | GridX40 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0025 | GridX50 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0026 | GridX60 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0027 | GridX70 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0028 | GridX80 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0029 | GridX90 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 0.025 | 180 | 0.015
GEN-SITE-ANI-ANI-0030 | GridY-10 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 220 | 0.025 | 0.015
GEN-SITE-ANI-ANI-0031 | GridY-20 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 220 | 0.025 | 0.015
GEN-SITE-ANI-ANI-0032 | GridY-30 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 220 | 0.025 | 0.015
GEN-SITE-ANI-ANI-0033 | GridY-40 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 220 | 0.025 | 0.015
GEN-SITE-ANI-ANI-0034 | GridY-50 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 220 | 0.025 | 0.015
GEN-SITE-ANI-ANI-0035 | GridY-60 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 220 | 0.025 | 0.015
GEN-SITE-ANI-ANI-0036 | GridY0 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 220 | 0.025 | 0.015
GEN-SITE-ANI-ANI-0037 | GridY10 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 220 | 0.025 | 0.015
GEN-SITE-ANI-ANI-0038 | GridY100 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 220 | 0.025 | 0.015
GEN-SITE-ANI-ANI-0039 | GridY20 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 220 | 0.025 | 0.015
GEN-SITE-ANI-ANI-0040 | GridY30 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 220 | 0.025 | 0.015
GEN-SITE-ANI-ANI-0041 | GridY40 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 220 | 0.025 | 0.015
GEN-SITE-ANI-ANI-0042 | GridY50 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 220 | 0.025 | 0.015
GEN-SITE-ANI-ANI-0043 | GridY60 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 220 | 0.025 | 0.015
GEN-SITE-ANI-ANI-0044 | GridY70 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 220 | 0.025 | 0.015
GEN-SITE-ANI-ANI-0045 | GridY80 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 220 | 0.025 | 0.015
GEN-SITE-ANI-ANI-0046 | GridY90 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Grid | 220 | 0.025 | 0.015
GEN-SITE-ANI-ANI-0047 | Studio fill | LIGHT | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
GEN-SITE-ANI-ANI-0048 | Studio floor | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Studio_Floor | 450 | 350 | 0.1
GEN-SITE-ANI-ANI-0049 | Studio key | LIGHT | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
GEN-SITE-ANI-ANI-0050 | Studio rim | LIGHT | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | ANIMATION_CONTROL |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
GEN-SITE-ANI-INS-0001 | SONAR_1_0 | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSPECTION_MARKER |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Cyan_Signal | 2.41 | 2.41 | 0.05
GEN-SITE-ANI-INS-0002 | SONAR_1_1 | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSPECTION_MARKER |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Cyan_Signal | 2.41 | 2.41 | 0.05
GEN-SITE-ANI-INS-0003 | SONAR_2_0 | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSPECTION_MARKER |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Cyan_Signal | 2.41 | 2.41 | 0.05
GEN-SITE-ANI-INS-0004 | SONAR_2_1 | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSPECTION_MARKER |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Cyan_Signal | 2.41 | 2.41 | 0.05
GEN-SITE-ANI-INS-0005 | SONAR_3_0 | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSPECTION_MARKER |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Cyan_Signal | 2.41 | 2.41 | 0.05
GEN-SITE-ANI-INS-0006 | SONAR_3_1 | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSPECTION_MARKER |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Cyan_Signal | 2.41 | 2.41 | 0.05
GEN-SITE-ANI-INS-0007 | SONAR_4_0 | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSPECTION_MARKER |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Cyan_Signal | 2.41 | 2.41 | 0.05
GEN-SITE-ANI-INS-0008 | SONAR_4_1 | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSPECTION_MARKER |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Cyan_Signal | 2.41 | 2.41 | 0.05
GEN-SITE-ANI-INS-0009 | CUT_Borescope_Interior_WestToEast_Path | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSPECTION_PATH |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Laser_Cut | 2.2433 | 37.2695 | 0.0666
GEN-SITE-ANI-INS-0010 | CUT_Borescope_SideSewer_SouthToNorth_Path | CURVE | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSPECTION_PATH |  | DERIVED_ANIMATION | ANIMATION_SUPPORT | Classified from collection ANIM_Construction_Effects and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_Laser_Cut | 190.4583 | 0.07 | 0.0666
GEN-SITE-ANI-SEG-0001 | CUT_GROWTH_Borescope_Interior_WestToEast_Path_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 2.2782 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | Borescope_Interior_WestToEast_Path | PLM-SITE-DEM-INS-0002 | ANIM_Laser_Cut | 0.0205 | 0.0682 | 0.07
GEN-SITE-ANI-SEG-0002 | CUT_GROWTH_Borescope_Interior_WestToEast_Path_001 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 4.9583 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | Borescope_Interior_WestToEast_Path | PLM-SITE-DEM-INS-0002 | ANIM_Laser_Cut | 0.07 | 0.005 | 0.07
GEN-SITE-ANI-SEG-0003 | CUT_GROWTH_Borescope_Interior_WestToEast_Path_002 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 7.47 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | Borescope_Interior_WestToEast_Path | PLM-SITE-DEM-INS-0002 | ANIM_Laser_Cut | 0.07 | 0.0075 | 0.07
GEN-SITE-ANI-SEG-0004 | CUT_GROWTH_Borescope_Interior_WestToEast_Path_003 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 4.8133 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | Borescope_Interior_WestToEast_Path | PLM-SITE-DEM-INS-0002 | ANIM_Laser_Cut | 0.07 | 0.0048 | 0.07
GEN-SITE-ANI-SEG-0005 | CUT_GROWTH_Borescope_Interior_WestToEast_Path_004 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 1.5 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | Borescope_Interior_WestToEast_Path | PLM-SITE-DEM-INS-0002 | ANIM_Laser_Cut | 0.07 | 0.0015 | 0.07
GEN-SITE-ANI-SEG-0006 | CUT_GROWTH_Borescope_Interior_WestToEast_Path_005 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 18.5 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | Borescope_Interior_WestToEast_Path | PLM-SITE-DEM-INS-0002 | ANIM_Laser_Cut | 0.07 | 0.0185 | 0.07
GEN-SITE-ANI-SEG-0007 | CUT_GROWTH_Borescope_SideSewer_SouthToNorth_Path_000 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 59.9283 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | Borescope_SideSewer_SouthToNorth_Path | PLM-SITE-DEM-INS-0004 | ANIM_Laser_Cut | 0.0599 | 0.07 | 0.07
GEN-SITE-ANI-SEG-0008 | CUT_GROWTH_Borescope_SideSewer_SouthToNorth_Path_001 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 59.3696 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | Borescope_SideSewer_SouthToNorth_Path | PLM-SITE-DEM-INS-0004 | ANIM_Laser_Cut | 0.0594 | 0.07 | 0.07
GEN-SITE-ANI-SEG-0009 | CUT_GROWTH_Borescope_SideSewer_SouthToNorth_Path_002 | MESH | ANIM_Construction_Effects | ANIM_Construction_Effects | SITE | SITE | GENERAL | ANIMATION | ANIMATION | 03 | Demolition + Excavation | 169 | 252 | INSTALLATION_SEGMENT | BRANCH | DERIVED_ANIMATION | DEMOLITION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA | 71.1604 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | Borescope_SideSewer_SouthToNorth_Path | PLM-SITE-DEM-INS-0004 | ANIM_Laser_Cut | 0.0712 | 0.07 | 0.07
GEN-SITE-TMP-STG-0001 | Staging_Area_1000SF | MESH | Staging_Area | Staging_Area | SITE | SITE | GENERAL_REQUIREMENTS | SITE_LOGISTICS | TEMPORARY | 02 | Staging + Fixture Removal | 85 | 168 | STAGING_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | 4D brief: ~1,000 sf fenced staging area | DOCUMENT_DERIVED | 01-500 | PROVISIONAL | 200 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Staging | 1 | 1 | 1
HVAC-B102-PRT-UTL-0001 | B102_220V_Radiant_Coil | CURVE | Radiant_Heating_Coils | Radiant_Heating_Coils | B102 | L1 | HVAC | RADIANT_HEATING | EXISTING_PROTECT | 03 | Demolition + Excavation | 169 | 252 | IN_SLAB_UTILITY |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum/brief: heated coil flooring system | DOCUMENT_DERIVED | 23-000 | PROVISIONAL | 200 | TRUE | LENGTH | 882 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_Radiant_Heating_Coil | 33 | 16 | 2
HVAC-B104-PRT-UTL-0001 | B104_220V_Radiant_Coil | CURVE | Radiant_Heating_Coils | Radiant_Heating_Coils | B104 | L1 | HVAC | RADIANT_HEATING | EXISTING_PROTECT | 03 | Demolition + Excavation | 169 | 252 | IN_SLAB_UTILITY |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum/brief: heated coil flooring system | DOCUMENT_DERIVED | 23-000 | PROVISIONAL | 200 | TRUE | LENGTH | 672 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_Radiant_Heating_Coil | 25.5 | 16 | 2
INT-B101-DEM-OPN-0001 | B101_DrywallCutout_1 | MESH | Drywall_Cutouts_DEMO | Drywall_Cutouts_DEMO | B101 | L1 | INTERIORS | GYPSUM_BOARD | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | WALL_OPENING_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01: lower wall exposure at stacks | DOCUMENT_DERIVED | 09-250 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_DemoCutout | 1 | 1 | 1
INT-B101-DEM-OPN-0002 | B101_DrywallCutout_2 | MESH | Drywall_Cutouts_DEMO | Drywall_Cutouts_DEMO | B101 | L1 | INTERIORS | GYPSUM_BOARD | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | WALL_OPENING_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01: lower wall exposure at stacks | DOCUMENT_DERIVED | 09-250 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_DemoCutout | 1 | 1 | 1
INT-B101-DEM-OPN-0003 | B101_DrywallCutout_3 | MESH | Drywall_Cutouts_DEMO | Drywall_Cutouts_DEMO | B101 | L1 | INTERIORS | GYPSUM_BOARD | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | WALL_OPENING_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01: lower wall exposure at stacks | DOCUMENT_DERIVED | 09-250 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_DemoCutout | 1 | 1 | 1
INT-B101-NEW-PAT-0001 | B101_FireSeal_1 | CURVE | Gypsum_Board_Patches | Gypsum_Board_Patches | B101 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Red acoustical/fire sealant | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 8.8 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Firestop_Red | 4.4 | 2 | 2
INT-B101-NEW-PAT-0002 | B101_FireSeal_2 | CURVE | Gypsum_Board_Patches | Gypsum_Board_Patches | B101 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Red acoustical/fire sealant | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 8.8 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Firestop_Red | 4.4 | 2 | 2
INT-B101-NEW-PAT-0003 | B101_FireSeal_3 | CURVE | Gypsum_Board_Patches | Gypsum_Board_Patches | B101 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Red acoustical/fire sealant | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 8.8 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Firestop_Red | 4.4 | 2 | 2
INT-B101-NEW-PAT-0004 | B101_GypsumPatch_1_L1 | MESH | Gypsum_Board_Patches | Gypsum_Board_Patches | B101 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL U305/U334 5/8in Type X/Firecore patch | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Gypsum_TypeX | 1 | 1 | 1
INT-B101-NEW-PAT-0005 | B101_GypsumPatch_2_L1 | MESH | Gypsum_Board_Patches | Gypsum_Board_Patches | B101 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL U305/U334 5/8in Type X/Firecore patch | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Gypsum_TypeX | 1 | 1 | 1
INT-B101-NEW-PAT-0006 | B101_GypsumPatch_2_L2 | MESH | Gypsum_Board_Patches | Gypsum_Board_Patches | B101 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL U305/U334 5/8in Type X/Firecore patch | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Gypsum_TypeX | 1 | 1 | 1
INT-B101-NEW-PAT-0007 | B101_GypsumPatch_3_L1 | MESH | Gypsum_Board_Patches | Gypsum_Board_Patches | B101 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL U305/U334 5/8in Type X/Firecore patch | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Gypsum_TypeX | 1 | 1 | 1
INT-B102-DEM-OPN-0001 | B102_DrywallCutout_1 | MESH | Drywall_Cutouts_DEMO | Drywall_Cutouts_DEMO | B102 | L1 | INTERIORS | GYPSUM_BOARD | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | WALL_OPENING_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01: lower wall exposure at stacks | DOCUMENT_DERIVED | 09-250 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_DemoCutout | 1 | 1 | 1
INT-B102-DEM-OPN-0002 | B102_DrywallCutout_2 | MESH | Drywall_Cutouts_DEMO | Drywall_Cutouts_DEMO | B102 | L1 | INTERIORS | GYPSUM_BOARD | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | WALL_OPENING_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01: lower wall exposure at stacks | DOCUMENT_DERIVED | 09-250 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_DemoCutout | 1 | 1 | 1
INT-B102-DEM-OPN-0003 | B102_DrywallCutout_3 | MESH | Drywall_Cutouts_DEMO | Drywall_Cutouts_DEMO | B102 | L1 | INTERIORS | GYPSUM_BOARD | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | WALL_OPENING_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01: lower wall exposure at stacks | DOCUMENT_DERIVED | 09-250 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_DemoCutout | 1 | 1 | 1
INT-B102-NEW-PAT-0001 | B102_FireSeal_1 | CURVE | Gypsum_Board_Patches | Gypsum_Board_Patches | B102 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Red acoustical/fire sealant | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 8.8 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Firestop_Red | 4.4 | 2 | 2
INT-B102-NEW-PAT-0002 | B102_FireSeal_2 | CURVE | Gypsum_Board_Patches | Gypsum_Board_Patches | B102 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Red acoustical/fire sealant | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 8.8 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Firestop_Red | 4.4 | 2 | 2
INT-B102-NEW-PAT-0003 | B102_FireSeal_3 | CURVE | Gypsum_Board_Patches | Gypsum_Board_Patches | B102 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Red acoustical/fire sealant | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 8.8 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Firestop_Red | 4.4 | 2 | 2
INT-B102-NEW-PAT-0004 | B102_GypsumPatch_1_L1 | MESH | Gypsum_Board_Patches | Gypsum_Board_Patches | B102 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL U305/U334 5/8in Type X/Firecore patch | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Gypsum_TypeX | 1 | 1 | 1
INT-B102-NEW-PAT-0005 | B102_GypsumPatch_2_L1 | MESH | Gypsum_Board_Patches | Gypsum_Board_Patches | B102 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL U305/U334 5/8in Type X/Firecore patch | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Gypsum_TypeX | 1 | 1 | 1
INT-B102-NEW-PAT-0006 | B102_GypsumPatch_2_L2 | MESH | Gypsum_Board_Patches | Gypsum_Board_Patches | B102 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL U305/U334 5/8in Type X/Firecore patch | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Gypsum_TypeX | 1 | 1 | 1
INT-B102-NEW-PAT-0007 | B102_GypsumPatch_3_L1 | MESH | Gypsum_Board_Patches | Gypsum_Board_Patches | B102 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL U305/U334 5/8in Type X/Firecore patch | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Gypsum_TypeX | 1 | 1 | 1
INT-B103-DEM-OPN-0001 | B103_DrywallCutout_1 | MESH | Drywall_Cutouts_DEMO | Drywall_Cutouts_DEMO | B103 | L1 | INTERIORS | GYPSUM_BOARD | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | WALL_OPENING_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01: lower wall exposure at stacks | DOCUMENT_DERIVED | 09-250 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_DemoCutout | 1 | 1 | 1
INT-B103-DEM-OPN-0002 | B103_DrywallCutout_2 | MESH | Drywall_Cutouts_DEMO | Drywall_Cutouts_DEMO | B103 | L1 | INTERIORS | GYPSUM_BOARD | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | WALL_OPENING_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01: lower wall exposure at stacks | DOCUMENT_DERIVED | 09-250 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_DemoCutout | 1 | 1 | 1
INT-B103-DEM-OPN-0003 | B103_DrywallCutout_3 | MESH | Drywall_Cutouts_DEMO | Drywall_Cutouts_DEMO | B103 | L1 | INTERIORS | GYPSUM_BOARD | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | WALL_OPENING_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01: lower wall exposure at stacks | DOCUMENT_DERIVED | 09-250 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_DemoCutout | 1 | 1 | 1
INT-B103-NEW-PAT-0001 | B103_FireSeal_1 | CURVE | Gypsum_Board_Patches | Gypsum_Board_Patches | B103 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Red acoustical/fire sealant | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 8.8 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Firestop_Red | 4.4 | 2 | 2
INT-B103-NEW-PAT-0002 | B103_FireSeal_2 | CURVE | Gypsum_Board_Patches | Gypsum_Board_Patches | B103 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Red acoustical/fire sealant | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 8.8 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Firestop_Red | 4.4 | 2 | 2
INT-B103-NEW-PAT-0003 | B103_FireSeal_3 | CURVE | Gypsum_Board_Patches | Gypsum_Board_Patches | B103 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Red acoustical/fire sealant | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 8.8 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Firestop_Red | 4.4 | 2 | 2
INT-B103-NEW-PAT-0004 | B103_GypsumPatch_1_L1 | MESH | Gypsum_Board_Patches | Gypsum_Board_Patches | B103 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL U305/U334 5/8in Type X/Firecore patch | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Gypsum_TypeX | 1 | 1 | 1
INT-B103-NEW-PAT-0005 | B103_GypsumPatch_2_L1 | MESH | Gypsum_Board_Patches | Gypsum_Board_Patches | B103 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL U305/U334 5/8in Type X/Firecore patch | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Gypsum_TypeX | 1 | 1 | 1
INT-B103-NEW-PAT-0006 | B103_GypsumPatch_2_L2 | MESH | Gypsum_Board_Patches | Gypsum_Board_Patches | B103 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL U305/U334 5/8in Type X/Firecore patch | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Gypsum_TypeX | 1 | 1 | 1
INT-B103-NEW-PAT-0007 | B103_GypsumPatch_3_L1 | MESH | Gypsum_Board_Patches | Gypsum_Board_Patches | B103 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL U305/U334 5/8in Type X/Firecore patch | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Gypsum_TypeX | 1 | 1 | 1
INT-B104-DEM-OPN-0001 | B104_DrywallCutout_1 | MESH | Drywall_Cutouts_DEMO | Drywall_Cutouts_DEMO | B104 | L1 | INTERIORS | GYPSUM_BOARD | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | WALL_OPENING_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01: lower wall exposure at stacks | DOCUMENT_DERIVED | 09-250 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_DemoCutout | 1 | 1 | 1
INT-B104-DEM-OPN-0002 | B104_DrywallCutout_2 | MESH | Drywall_Cutouts_DEMO | Drywall_Cutouts_DEMO | B104 | L1 | INTERIORS | GYPSUM_BOARD | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | WALL_OPENING_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01: lower wall exposure at stacks | DOCUMENT_DERIVED | 09-250 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_DemoCutout | 1 | 1 | 1
INT-B104-DEM-OPN-0003 | B104_DrywallCutout_3 | MESH | Drywall_Cutouts_DEMO | Drywall_Cutouts_DEMO | B104 | L1 | INTERIORS | GYPSUM_BOARD | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | WALL_OPENING_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01: lower wall exposure at stacks | DOCUMENT_DERIVED | 09-250 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_DemoCutout | 1 | 1 | 1
INT-B104-NEW-PAT-0001 | B104_FireSeal_1 | CURVE | Gypsum_Board_Patches | Gypsum_Board_Patches | B104 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Red acoustical/fire sealant | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 8.8 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Firestop_Red | 4.4 | 2 | 2
INT-B104-NEW-PAT-0002 | B104_FireSeal_2 | CURVE | Gypsum_Board_Patches | Gypsum_Board_Patches | B104 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Red acoustical/fire sealant | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 8.8 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Firestop_Red | 4.4 | 2 | 2
INT-B104-NEW-PAT-0003 | B104_FireSeal_3 | CURVE | Gypsum_Board_Patches | Gypsum_Board_Patches | B104 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Red acoustical/fire sealant | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 8.8 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Firestop_Red | 4.4 | 2 | 2
INT-B104-NEW-PAT-0004 | B104_GypsumPatch_1_L1 | MESH | Gypsum_Board_Patches | Gypsum_Board_Patches | B104 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL U305/U334 5/8in Type X/Firecore patch | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Gypsum_TypeX | 1 | 1 | 1
INT-B104-NEW-PAT-0005 | B104_GypsumPatch_2_L1 | MESH | Gypsum_Board_Patches | Gypsum_Board_Patches | B104 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL U305/U334 5/8in Type X/Firecore patch | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Gypsum_TypeX | 1 | 1 | 1
INT-B104-NEW-PAT-0006 | B104_GypsumPatch_2_L2 | MESH | Gypsum_Board_Patches | Gypsum_Board_Patches | B104 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL U305/U334 5/8in Type X/Firecore patch | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Gypsum_TypeX | 1 | 1 | 1
INT-B104-NEW-PAT-0007 | B104_GypsumPatch_3_L1 | MESH | Gypsum_Board_Patches | Gypsum_Board_Patches | B104 | L1 | INTERIORS | GYPSUM_BOARD | NEW | 07 | Patching + Finishes | 505 | 588 | PATCH_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | UL U305/U334 5/8in Type X/Firecore patch | DOCUMENT_DERIVED | 09-290 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_Gypsum_TypeX | 1 | 1 | 1
LND-SITE-CTX-CTX-0001 | Arching ornamental grass | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 2.5291 | 2.4733 | 1.3272
LND-SITE-CTX-CTX-0002 | Arching ornamental grass.001 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 2.4079 | 2.6166 | 1.2415
LND-SITE-CTX-CTX-0003 | Arching ornamental grass.002 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 2.2663 | 2.3155 | 1.1685
LND-SITE-CTX-CTX-0004 | Arching ornamental grass.003 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 1.8995 | 2.0353 | 0.9428
LND-SITE-CTX-CTX-0005 | Arching ornamental grass.004 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 2.3549 | 2.1479 | 1.1293
LND-SITE-CTX-CTX-0006 | Arching ornamental grass.005 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 2.6496 | 2.6613 | 1.4014
LND-SITE-CTX-CTX-0007 | Arching ornamental grass.006 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 2.1774 | 2.2514 | 1.1393
LND-SITE-CTX-CTX-0008 | Arching ornamental grass.007 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 2.6953 | 2.472 | 1.3641
LND-SITE-CTX-CTX-0009 | Arching ornamental grass.008 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 2.2988 | 2.3365 | 1.2107
LND-SITE-CTX-CTX-0010 | Arching ornamental grass.009 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 2.0578 | 1.8483 | 0.9971
LND-SITE-CTX-CTX-0011 | Arching ornamental grass.010 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 2.1177 | 2.0298 | 1.0735
LND-SITE-CTX-CTX-0012 | Arching ornamental grass.011 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 2.6615 | 2.5714 | 1.3111
LND-SITE-CTX-CTX-0013 | Arching ornamental grass.012 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 1.8463 | 2.0704 | 0.9913
LND-SITE-CTX-CTX-0014 | Arching ornamental grass.013 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 1.9029 | 1.9352 | 0.9188
LND-SITE-CTX-CTX-0015 | Arching ornamental grass.014 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 2.3697 | 2.3236 | 1.2308
LND-SITE-CTX-CTX-0016 | Arching ornamental grass.015 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 2.5665 | 2.7958 | 1.3969
LND-SITE-CTX-CTX-0017 | Arching ornamental grass.016 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 1.7215 | 1.7464 | 0.8967
LND-SITE-CTX-CTX-0018 | Arching ornamental grass.017 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 2.4434 | 2.4986 | 1.3011
LND-SITE-CTX-CTX-0019 | Arching ornamental grass.018 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 2.7595 | 2.6004 | 1.4447
LND-SITE-CTX-CTX-0020 | Arching ornamental grass.019 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 1.7419 | 1.8927 | 0.9191
LND-SITE-CTX-CTX-0021 | Continuous lawn | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Pacific Northwest lawn | 520 | 520 | 0.24
LND-SITE-CTX-CTX-0022 | Curving pedestrian path | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Board-formed architectural concrete | 210.723 | 9.6974 | 0
LND-SITE-CTX-CTX-0023 | Deciduous scaffold branch | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 5.3945 | 0.4185 | 10.32
LND-SITE-CTX-CTX-0024 | Deciduous scaffold branch.001 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 2.0669 | 5.2657 | 11.2019
LND-SITE-CTX-CTX-0025 | Deciduous scaffold branch.002 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 4.6006 | 3.5024 | 9.0248
LND-SITE-CTX-CTX-0026 | Deciduous scaffold branch.003 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 4.6138 | 3.512 | 10.9342
LND-SITE-CTX-CTX-0027 | Deciduous scaffold branch.004 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 2.0662 | 5.2635 | 10.8582
LND-SITE-CTX-CTX-0028 | Deciduous scaffold branch.005 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 5.3947 | 0.4185 | 10.344
LND-SITE-CTX-CTX-0029 | Deciduous scaffold branch.006 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 2.0642 | 5.2575 | 10.0215
LND-SITE-CTX-CTX-0030 | Deciduous scaffold branch.007 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 4.6217 | 3.5177 | 12.6903
LND-SITE-CTX-CTX-0031 | Deciduous scaffold branch.008 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 4.5976 | 3.5002 | 8.6887
LND-SITE-CTX-CTX-0032 | Deciduous scaffold branch.009 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 2.064 | 5.2569 | 9.9416
LND-SITE-CTX-CTX-0033 | Deciduous scaffold branch.010 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 5.3884 | 0.4185 | 9.5973
LND-SITE-CTX-CTX-0034 | Deciduous scaffold branch.011 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 2.0699 | 5.2748 | 13.0723
LND-SITE-CTX-CTX-0035 | Deciduous scaffold branch.012 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 4.6104 | 3.5095 | 10.3404
LND-SITE-CTX-CTX-0036 | Deciduous scaffold branch.013 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 4.6043 | 3.505 | 9.4688
LND-SITE-CTX-CTX-0037 | Deciduous scaffold branch.014 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 2.0585 | 5.2398 | 8.258
LND-SITE-CTX-CTX-0038 | Deciduous tree trunk | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 1.3 | 1.3 | 20.5
LND-SITE-CTX-CTX-0039 | Deciduous tree trunk.001 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 1.3 | 1.3 | 20.5
LND-SITE-CTX-CTX-0040 | Deciduous tree trunk.002 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 1.3 | 1.3 | 20.5
LND-SITE-CTX-CTX-0041 | Evergreen trunk | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 1.656 | 1.656 | 42.32
LND-SITE-CTX-CTX-0042 | Evergreen trunk.001 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 1.8 | 1.8 | 46
LND-SITE-CTX-CTX-0043 | Evergreen trunk.002 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 1.584 | 1.584 | 40.48
LND-SITE-CTX-CTX-0044 | Evergreen trunk.003 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 1.728 | 1.728 | 44.16
LND-SITE-CTX-CTX-0045 | Evergreen trunk.004 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 1.872 | 1.872 | 47.84
LND-SITE-CTX-CTX-0046 | Evergreen trunk.005 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 1.62 | 1.62 | 41.4
LND-SITE-CTX-CTX-0047 | Evergreen trunk.006 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 1.764 | 1.764 | 45.08
LND-SITE-CTX-CTX-0048 | Evergreen trunk.007 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Tree bark | 1.548 | 1.548 | 39.56
LND-SITE-CTX-CTX-0049 | Fine deciduous leaf canopy 0 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 18.2962 | 16.3928 | 14.0311
LND-SITE-CTX-CTX-0050 | Fine deciduous leaf canopy 1 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 18.3948 | 16.3263 | 14.1079
LND-SITE-CTX-CTX-0051 | Fine deciduous leaf canopy 2 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 18.3133 | 16.4676 | 14.0477
LND-SITE-CTX-CTX-0052 | Foundation shrub 00 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 5.1135 | 5.0162 | 3.1966
LND-SITE-CTX-CTX-0053 | Foundation shrub 01 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 4.2654 | 4.2095 | 2.5744
LND-SITE-CTX-CTX-0054 | Foundation shrub 02 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 4.758 | 4.6678 | 3.0322
LND-SITE-CTX-CTX-0055 | Foundation shrub 03 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 5.0738 | 5.1283 | 3.5783
LND-SITE-CTX-CTX-0056 | Foundation shrub 04 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 5.1525 | 5.1424 | 3.4249
LND-SITE-CTX-CTX-0057 | Foundation shrub 05 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 5.4955 | 5.4233 | 3.8555
LND-SITE-CTX-CTX-0058 | Foundation shrub 06 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 5.8857 | 5.8532 | 3.8212
LND-SITE-CTX-CTX-0059 | Foundation shrub 07 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 6.2602 | 6.3003 | 4.5438
LND-SITE-CTX-CTX-0060 | Ground-floor exposed aggregate patio | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Board-formed architectural concrete | 26.2 | 5.5 | 0.32
LND-SITE-CTX-CTX-0061 | Ground-floor exposed aggregate patio.001 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Board-formed architectural concrete | 26.2 | 5.5 | 0.32
LND-SITE-CTX-CTX-0062 | Ground-floor exposed aggregate patio.002 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Board-formed architectural concrete | 9.2 | 5.5 | 0.32
LND-SITE-CTX-CTX-0063 | Ground-floor exposed aggregate patio.003 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Board-formed architectural concrete | 13.2 | 5.5 | 0.32
LND-SITE-CTX-CTX-0064 | Ground-floor exposed aggregate patio.004 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Board-formed architectural concrete | 26.2 | 5.5 | 0.32
LND-SITE-CTX-CTX-0065 | Ground-floor exposed aggregate patio.005 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Board-formed architectural concrete | 26.2 | 5.5 | 0.32
LND-SITE-CTX-CTX-0066 | Ground-floor exposed aggregate patio.006 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Board-formed architectural concrete | 27.658 | 5.5 | 0.32
LND-SITE-CTX-CTX-0067 | Irregular evergreen needle canopy | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 24.3073 | 24.2323 | 36.9349
LND-SITE-CTX-CTX-0068 | Irregular evergreen needle canopy.001 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 20.3181 | 19.6562 | 36.9349
LND-SITE-CTX-CTX-0069 | Irregular evergreen needle canopy.002 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 23.1102 | 23.4466 | 36.9349
LND-SITE-CTX-CTX-0070 | Irregular evergreen needle canopy.003 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 28.5928 | 28.593 | 39.7813
LND-SITE-CTX-CTX-0071 | Irregular evergreen needle canopy.004 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 23.5469 | 23.5479 | 39.7813
LND-SITE-CTX-CTX-0072 | Irregular evergreen needle canopy.005 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 27.4251 | 27.4246 | 39.7813
LND-SITE-CTX-CTX-0073 | Irregular evergreen needle canopy.006 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 25.3516 | 25.3437 | 35.4443
LND-SITE-CTX-CTX-0074 | Irregular evergreen needle canopy.007 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 20.9094 | 20.8401 | 35.4443
LND-SITE-CTX-CTX-0075 | Irregular evergreen needle canopy.008 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 24.2946 | 24.3298 | 35.4443
LND-SITE-CTX-CTX-0076 | Irregular evergreen needle canopy.009 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 25.7285 | 25.7847 | 38.3857
LND-SITE-CTX-CTX-0077 | Irregular evergreen needle canopy.010 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 20.9635 | 21.4597 | 38.3857
LND-SITE-CTX-CTX-0078 | Irregular evergreen needle canopy.011 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 24.8305 | 24.5783 | 38.3857
LND-SITE-CTX-CTX-0079 | Irregular evergreen needle canopy.012 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 28.0404 | 28.1643 | 41.3557
LND-SITE-CTX-CTX-0080 | Irregular evergreen needle canopy.013 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 22.5965 | 23.6903 | 41.3557
LND-SITE-CTX-CTX-0081 | Irregular evergreen needle canopy.014 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 27.2323 | 26.6764 | 41.3557
LND-SITE-CTX-CTX-0082 | Irregular evergreen needle canopy.015 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 25.1744 | 25.2241 | 36.1658
LND-SITE-CTX-CTX-0083 | Irregular evergreen needle canopy.016 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 20.5336 | 20.9716 | 36.1658
LND-SITE-CTX-CTX-0084 | Irregular evergreen needle canopy.017 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 24.2812 | 24.0585 | 36.1658
LND-SITE-CTX-CTX-0085 | Irregular evergreen needle canopy.018 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 25.2622 | 25.3118 | 39.1896
LND-SITE-CTX-CTX-0086 | Irregular evergreen needle canopy.019 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 20.6057 | 21.044 | 39.1896
LND-SITE-CTX-CTX-0087 | Irregular evergreen needle canopy.020 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 24.3654 | 24.1426 | 39.1896
LND-SITE-CTX-CTX-0088 | Irregular evergreen needle canopy.021 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 22.2716 | 22.2442 | 34.7567
LND-SITE-CTX-CTX-0089 | Irregular evergreen needle canopy.022 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 18.4511 | 18.2094 | 34.7567
LND-SITE-CTX-CTX-0090 | Irregular evergreen needle canopy.023 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 21.2872 | 21.4101 | 34.7567
LND-SITE-CTX-CTX-0091 | Layered foundation planting | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 5.1135 | 5.0162 | 3.1966
LND-SITE-CTX-CTX-0092 | Layered foundation planting.001 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 4.2654 | 4.2095 | 2.5744
LND-SITE-CTX-CTX-0093 | Layered foundation planting.002 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 4.758 | 4.6678 | 3.0322
LND-SITE-CTX-CTX-0094 | Layered foundation planting.003 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 5.0738 | 5.1283 | 3.5783
LND-SITE-CTX-CTX-0095 | Layered foundation planting.004 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 5.1525 | 5.1424 | 3.4249
LND-SITE-CTX-CTX-0096 | Layered foundation planting.005 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 5.4955 | 5.4233 | 3.8555
LND-SITE-CTX-CTX-0097 | Layered foundation planting.006 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 5.8857 | 5.8532 | 3.8212
LND-SITE-CTX-CTX-0098 | Layered foundation planting.007 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 6.2602 | 6.3003 | 4.5438
LND-SITE-CTX-CTX-0099 | Layered foundation planting.008 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 5.1135 | 5.0162 | 3.1966
LND-SITE-CTX-CTX-0100 | Layered foundation planting.009 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 4.2654 | 4.2095 | 2.5744
LND-SITE-CTX-CTX-0101 | Layered foundation planting.010 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 4.758 | 4.6678 | 3.0322
LND-SITE-CTX-CTX-0102 | Layered foundation planting.011 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 5.0738 | 5.1283 | 3.5783
LND-SITE-CTX-CTX-0103 | Layered foundation planting.012 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 5.1525 | 5.1424 | 3.4249
LND-SITE-CTX-CTX-0104 | Layered foundation planting.013 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 5.4955 | 5.4233 | 3.8555
LND-SITE-CTX-CTX-0105 | Layered foundation planting.014 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 5.8857 | 5.8532 | 3.8212
LND-SITE-CTX-CTX-0106 | Layered foundation planting.015 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 6.2602 | 6.3003 | 4.5438
LND-SITE-CTX-CTX-0107 | Layered foundation planting.016 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 5.1135 | 5.0162 | 3.1966
LND-SITE-CTX-CTX-0108 | Layered foundation planting.017 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 4.2654 | 4.2095 | 2.5744
LND-SITE-CTX-CTX-0109 | Layered foundation planting.018 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 4.758 | 4.6678 | 3.0322
LND-SITE-CTX-CTX-0110 | Layered foundation planting.019 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 5.0738 | 5.1283 | 3.5783
LND-SITE-CTX-CTX-0111 | Layered foundation planting.020 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 5.1525 | 5.1424 | 3.4249
LND-SITE-CTX-CTX-0112 | Layered foundation planting.021 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 5.4955 | 5.4233 | 3.8555
LND-SITE-CTX-CTX-0113 | Layered foundation planting.022 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 5.8857 | 5.8532 | 3.8212
LND-SITE-CTX-CTX-0114 | Layered foundation planting.023 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 6.2602 | 6.3003 | 4.5438
LND-SITE-CTX-CTX-0115 | Mature reference hedge | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 8.693 | 8.5276 | 5.4343
LND-SITE-CTX-CTX-0116 | Mature reference hedge.001 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 7.6777 | 7.5771 | 4.6338
LND-SITE-CTX-CTX-0117 | Mature reference hedge.002 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 7.3749 | 7.2352 | 4.6999
LND-SITE-CTX-CTX-0118 | Mature reference hedge.003 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | ANIM_InteriorDetail_Foliage 0 | 9.1328 | 9.2309 | 6.441
LND-SITE-CTX-CTX-0119 | Mature reference hedge.004 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Foliage 0 | 6.9559 | 6.9422 | 4.6236
LND-SITE-CTX-CTX-0120 | Organic planting bed | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Dark bark mulch | 10 | 5 | 0.18
LND-SITE-CTX-CTX-0121 | Organic planting bed.001 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Dark bark mulch | 13 | 5 | 0.18
LND-SITE-CTX-CTX-0122 | Organic planting bed.002 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Dark bark mulch | 15 | 5 | 0.18
LND-SITE-CTX-CTX-0123 | Pacific Northwest evergreen canopy | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 16.7865 | 17.608 | 36.9349
LND-SITE-CTX-CTX-0124 | Pacific Northwest evergreen canopy.001 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 20.2612 | 20.2598 | 39.7813
LND-SITE-CTX-CTX-0125 | Pacific Northwest evergreen canopy.002 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 17.918 | 18.0039 | 35.4443
LND-SITE-CTX-CTX-0126 | Pacific Northwest evergreen canopy.003 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 18.5587 | 17.9428 | 38.3857
LND-SITE-CTX-CTX-0127 | Pacific Northwest evergreen canopy.004 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 20.5916 | 19.2342 | 41.3557
LND-SITE-CTX-CTX-0128 | Pacific Northwest evergreen canopy.005 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 18.1276 | 17.584 | 36.1658
LND-SITE-CTX-CTX-0129 | Pacific Northwest evergreen canopy.006 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 18.19 | 17.646 | 39.1896
LND-SITE-CTX-CTX-0130 | Pacific Northwest evergreen canopy.007 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Evergreen needles | 15.6216 | 15.9216 | 34.7567
LND-SITE-CTX-CTX-0131 | Patio sawcut joint | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0132 | Patio sawcut joint.001 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0133 | Patio sawcut joint.002 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0134 | Patio sawcut joint.003 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0135 | Patio sawcut joint.004 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0136 | Patio sawcut joint.005 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0137 | Patio sawcut joint.006 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0138 | Patio sawcut joint.007 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0139 | Patio sawcut joint.008 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0140 | Patio sawcut joint.009 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0141 | Patio sawcut joint.010 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0142 | Patio sawcut joint.011 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0143 | Patio sawcut joint.012 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0144 | Patio sawcut joint.013 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0145 | Patio sawcut joint.014 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0146 | Patio sawcut joint.015 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0147 | Patio sawcut joint.016 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0148 | Patio sawcut joint.017 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0149 | Patio sawcut joint.018 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0150 | Patio sawcut joint.019 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0151 | Patio sawcut joint.020 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0152 | Patio sawcut joint.021 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0153 | Patio sawcut joint.022 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0154 | Patio sawcut joint.023 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0155 | Patio sawcut joint.024 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0156 | Patio sawcut joint.025 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0157 | Patio sawcut joint.026 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0158 | Patio sawcut joint.027 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0159 | Patio sawcut joint.028 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0160 | Patio sawcut joint.029 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0161 | Patio sawcut joint.030 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0162 | Patio sawcut joint.031 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0163 | Patio sawcut joint.032 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0164 | Patio sawcut joint.033 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0165 | Patio sawcut joint.034 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
LND-SITE-CTX-CTX-0166 | Patio sawcut joint.035 | MESH | PHOTOREAL_Landscape | PHOTOREAL_Landscape | SITE | SITE | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | Existing + Investigation | 1 | 84 | CONTEXT |  | REFERENCE_CONTEXT | STATIC_CONTEXT | Classified from collection PHOTOREAL_Landscape and object name. | DOCUMENT_DERIVED | 00-000 | PROVISIONAL | 200 | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Anodized dark bronze aluminum | 0.025 | 5.35 | 0.012
MST-B101-NEW-MEM-0001 | B101_TCNA_Waterproofing | MESH | Waterproofing_Membrane | Waterproofing_Membrane | B101 | L1 | MOISTURE_PROTECTION | WATERPROOFING | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | MEMBRANE_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum/TCNA waterproofing + crack isolation | DOCUMENT_DERIVED | 07-100 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_TCNA_Waterproofing | 1 | 1 | 1
MST-B101-NEW-VB-0001 | Stego15mil_B101_001 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B101 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B101-NEW-VB-0002 | Stego15mil_B101_002 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B101 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B101-NEW-VB-0003 | Stego15mil_B101_003 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B101 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B101-NEW-VB-0004 | Stego15mil_B101_004 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B101 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B101-NEW-VB-0005 | Stego15mil_B101_005 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B101 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B101-NEW-VB-0006 | Stego15mil_B101_006 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B101 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B101-NEW-VB-0007 | Stego15mil_B101_007 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B101 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B101-NEW-VB-0008 | Stego15mil_B101_008 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B101 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B101-NEW-VB-0009 | Stego15mil_B101_009 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B101 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B101-NEW-VB-0010 | Stego15mil_B101_010 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B101 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B101-NEW-VB-0011 | Stego15mil_B101_011 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B101 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B102-NEW-MEM-0001 | B102_TCNA_Waterproofing | MESH | Waterproofing_Membrane | Waterproofing_Membrane | B102 | L1 | MOISTURE_PROTECTION | WATERPROOFING | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | MEMBRANE_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum/TCNA waterproofing + crack isolation | DOCUMENT_DERIVED | 07-100 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_TCNA_Waterproofing | 1 | 1 | 1
MST-B102-NEW-VB-0001 | Stego15mil_B102_012 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B102 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B102-NEW-VB-0002 | Stego15mil_B102_013 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B102 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B102-NEW-VB-0003 | Stego15mil_B102_014 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B102 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B102-NEW-VB-0004 | Stego15mil_B102_015 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B102 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B102-NEW-VB-0005 | Stego15mil_B102_016 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B102 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B102-NEW-VB-0006 | Stego15mil_B102_017 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B102 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B102-NEW-VB-0007 | Stego15mil_B102_018 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B102 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B102-NEW-VB-0008 | Stego15mil_B102_019 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B102 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B102-NEW-VB-0009 | Stego15mil_B102_020 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B102 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B102-NEW-VB-0010 | Stego15mil_B102_021 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B102 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B102-NEW-VB-0011 | Stego15mil_B102_022 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B102 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B103-NEW-MEM-0001 | B103_TCNA_Waterproofing | MESH | Waterproofing_Membrane | Waterproofing_Membrane | B103 | L1 | MOISTURE_PROTECTION | WATERPROOFING | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | MEMBRANE_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum/TCNA waterproofing + crack isolation | DOCUMENT_DERIVED | 07-100 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_TCNA_Waterproofing | 1 | 1 | 1
MST-B103-NEW-VB-0001 | Stego15mil_B103_023 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B103 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B103-NEW-VB-0002 | Stego15mil_B103_024 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B103 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B103-NEW-VB-0003 | Stego15mil_B103_025 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B103 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B103-NEW-VB-0004 | Stego15mil_B103_026 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B103 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B103-NEW-VB-0005 | Stego15mil_B103_027 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B103 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B103-NEW-VB-0006 | Stego15mil_B103_028 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B103 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B103-NEW-VB-0007 | Stego15mil_B103_029 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B103 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B103-NEW-VB-0008 | Stego15mil_B103_030 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B103 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B103-NEW-VB-0009 | Stego15mil_B103_031 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B103 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B104-NEW-MEM-0001 | B104_TCNA_Waterproofing | MESH | Waterproofing_Membrane | Waterproofing_Membrane | B104 | L1 | MOISTURE_PROTECTION | WATERPROOFING | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | MEMBRANE_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Addendum/TCNA waterproofing + crack isolation | DOCUMENT_DERIVED | 07-100 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_TCNA_Waterproofing | 1 | 1 | 1
MST-B104-NEW-VB-0001 | Stego15mil_B104_032 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B104 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B104-NEW-VB-0002 | Stego15mil_B104_033 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B104 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B104-NEW-VB-0003 | Stego15mil_B104_034 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B104 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B104-NEW-VB-0004 | Stego15mil_B104_035 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B104 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B104-NEW-VB-0005 | Stego15mil_B104_036 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B104 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B104-NEW-VB-0006 | Stego15mil_B104_037 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B104 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B104-NEW-VB-0007 | Stego15mil_B104_038 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B104 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B104-NEW-VB-0008 | Stego15mil_B104_039 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B104 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B104-NEW-VB-0009 | Stego15mil_B104_040 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B104 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
MST-B104-NEW-VB-0010 | Stego15mil_B104_041 | MESH | Vapor_Barrier_Stegowrap | Vapor_Barrier_Stegowrap | B104 | L1 | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | Backfill + Slab Pourback | 421 | 504 | VAPOR_BARRIER_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P5.1 / brief: 15-mil StegoWrap Class A | DOCUMENT_DERIVED | 07-260 | PROVISIONAL | 300 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | MAT_StegoWrap_15mil | 1 | 1 | 1
PLM-B101-DEM-PIPE-0001 | EX_CI_B101_BR2_lav_n | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B101 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | LAVATORY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing lavatory/fixture branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 11.9202 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 8.5875 | 4.0274 | 0.4461
PLM-B101-DEM-PIPE-0002 | EX_CI_B101_BR2_lav_s | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B101 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | LAVATORY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing lavatory/fixture branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 3.4621 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 2.6494 | 2.5237 | 0.27
PLM-B101-DEM-PIPE-0003 | EX_CI_B101_BR3_bath_n | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B101 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | BATH_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 5.09 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 5.0721 | 1.0814 | 0.3976
PLM-B101-DEM-PIPE-0004 | EX_CI_B101_BR3_bath_s | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B101 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | BATH_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 4.1614 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 4.1398 | 1.0796 | 0.3783
PLM-B101-DEM-PIPE-0005 | EX_CI_B101_BR3_laundry | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B101 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | LAUNDRY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 1.0196 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 1.0536 | 0.658 | 0.3128
PLM-B101-DEM-PIPE-0006 | EX_CI_B101_LAT6_REPLACE | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B101 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | LATERAL | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing 6in segment within 18in replacement limit; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE | 6 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 0.5521 | 1.5115 | 0.5832
PLM-B101-DEM-PIPE-0007 | EX_CI_B101_MAIN4 | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B101 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | MAIN | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Like-for-like existing route representation; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 45.4323 | FT | CURVE_CENTERLINE | 4 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 13.9651 | 39.1302 | 1.3212
PLM-B101-EXG-PIPE-0001 | B101_Prior_4in_ABS_REMAIN | CURVE | Ex_Unit101_&_104_Prior_ABS_REMAIN | Ex_Unit101_&_104_Prior_ABS_REMAIN | B101 | L1 | PLUMBING | DWV | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | PIPE_ROUTE | MAIN | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P3.1/P3.2: prior Schedule 40 ABS repair to remain | DOCUMENT_DERIVED | 22-000 | PROVISIONAL | 300 | TRUE | LENGTH | 2.2305 | FT | CURVE_CENTERLINE | 4 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Prior_Remain | 1.8612 | 1.8224 | 0.4214
PLM-B101-NEW-CO-0001 | B101_BaseOfStack_Cleanout_1 | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Base-of-stack cleanout | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Nickel_Bronze | 0.435 | 0.435 | 0.435
PLM-B101-NEW-CO-0002 | B101_BaseOfStack_Cleanout_2 | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Base-of-stack cleanout | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Nickel_Bronze | 0.3383 | 0.3383 | 0.3383
PLM-B101-NEW-CO-0003 | B101_BaseOfStack_Cleanout_3 | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Base-of-stack cleanout | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Nickel_Bronze | 0.3383 | 0.3383 | 0.3383
PLM-B101-NEW-CO-0004 | B101_Cleanout_12x12_Pad | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | 12x12 concrete cleanout pad | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
PLM-B101-NEW-CO-0005 | B101_Zurn_Z1450_6in_Cleanout | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | 4D brief / SOR: exterior 6in cleanout at replacement limit | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 6 |  | NA |  |  | MAT_ABS_Schedule40_Black | 2 | 2 | 5.7812
PLM-B101-NEW-FIT-0001 | B101_6in_TransitionCoupling | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02: 4in waste to 6in waste transition; match existing I.E. | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 6 |  | NA |  |  | MAT_ABS_Schedule40_Black | 0.6846 | 0.6846 | 0.8333
PLM-B101-NEW-FIT-0002 | B101_StackTieIn_1_4in | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01/P5.1 stack tie-in vertical exposure | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 4 |  | NA |  |  | MAT_ABS_Schedule40_Black | 2 | 2 | 6.3333
PLM-B101-NEW-FIT-0003 | B101_StackTieIn_2_3in | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01/P5.1 stack tie-in vertical exposure | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 3 |  | NA |  |  | MAT_ABS_Schedule40_Black | 2 | 2 | 6
PLM-B101-NEW-FIT-0004 | B101_StackTieIn_3_3in | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01/P5.1 stack tie-in vertical exposure | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 3 |  | NA |  |  | MAT_ABS_Schedule40_Black | 2 | 2 | 6
PLM-B101-NEW-FIT-0005 | B101_TestPlug | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WP2 test plug visualization | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_TestPlug | 0.3375 | 0.3375 | 0.1667
PLM-B101-NEW-FIT-0006 | B101_WP2_WaterTest | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Phase 5 water-test visualization | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Water_Test_Blue | 15.6583 | 40.9817 | 2.9463
PLM-B101-NEW-FIT-0007 | PTRAP_B101_laundry | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_ABS_Schedule40_Black | 2.6667 | 2 | 2.6667
PLM-B101-NEW-FIT-0008 | PTRAP_B101_lav_n | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_ABS_Schedule40_Black | 2.6667 | 2 | 2.6667
PLM-B101-NEW-FIT-0009 | PTRAP_B101_lav_s | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_ABS_Schedule40_Black | 2.6667 | 2 | 2.6667
PLM-B101-NEW-PIPE-0001 | NEW_ABS_B101_2in_lav_n | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | LAVATORY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 2in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 11.9202 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 10.4825 | 5.9267 | 2.2483
PLM-B101-NEW-PIPE-0002 | NEW_ABS_B101_2in_lav_s | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | LAVATORY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 2in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 3.4621 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 4.5133 | 4.38 | 2.0721
PLM-B101-NEW-PIPE-0003 | NEW_ABS_B101_3in_bath_n | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | BATH_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 5.09 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 7.0267 | 2.7933 | 2.106
PLM-B101-NEW-PIPE-0004 | NEW_ABS_B101_3in_bath_s | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | BATH_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 4.1614 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 6.0842 | 2.7933 | 2.0867
PLM-B101-NEW-PIPE-0005 | NEW_ABS_B101_3in_laundry | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | LAUNDRY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.0196 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 2.9425 | 2.3883 | 2.0212
PLM-B101-NEW-PIPE-0006 | NEW_ABS_B101_4in_MAIN | CURVE | New_ABS_UnderSlab_4in_6in | New_ABS_UnderSlab_4in_6in | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | MAIN | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3.1/P3.2 traced new Sch40 ABS | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 45.4323 | FT | CURVE_CENTERLINE | 4 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 15.6583 | 40.9817 | 2.9463
PLM-B101-NEW-PIPE-0007 | NEW_ABS_B101_6in_LATERAL_18IN_LIMIT | CURVE | New_ABS_UnderSlab_4in_6in | New_ABS_UnderSlab_4in_6in | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | LATERAL | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/SOR: new 6in to 18in beyond foundation, then tie to existing lateral | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE | 6 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 2 | 3.5 | 2.0312
PLM-B101-NEW-SEG-0001 | ABS_GROWTH_NEW_ABS_B101_2in_lav_n_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 3.4207 | FT | GROWTH_LENGTH | 2 |  | NOT_DOCUMENTED | NEW_ABS_B101_2in_lav_n | PLM-B101-NEW-PIPE-0001 | ANIM_ABS_Installation_Highlight | 0.1979 | 0.0075 | 0.1979
PLM-B101-NEW-SEG-0002 | ABS_GROWTH_NEW_ABS_B101_2in_lav_n_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 8.4995 | FT | GROWTH_LENGTH | 2 |  | NOT_DOCUMENTED | NEW_ABS_B101_2in_lav_n | PLM-B101-NEW-PIPE-0001 | ANIM_ABS_Installation_Highlight | 0.0244 | 0.1983 | 0.1981
PLM-B101-NEW-SEG-0003 | ABS_GROWTH_NEW_ABS_B101_2in_lav_s_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 3.4621 | FT | GROWTH_LENGTH | 2 |  | NOT_DOCUMENTED | NEW_ABS_B101_2in_lav_s | PLM-B101-NEW-PIPE-0002 | ANIM_ABS_Installation_Highlight | 0.1416 | 0.1489 | 0.1979
PLM-B101-NEW-SEG-0004 | ABS_GROWTH_NEW_ABS_B101_3in_bath_n_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | BATH_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 5.09 | FT | GROWTH_LENGTH | 3 |  | NOT_DOCUMENTED | NEW_ABS_B101_3in_bath_n | PLM-B101-NEW-PIPE-0003 | ANIM_ABS_Installation_Highlight | 0.0565 | 0.2898 | 0.2917
PLM-B101-NEW-SEG-0005 | ABS_GROWTH_NEW_ABS_B101_3in_bath_s_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | BATH_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 4.1614 | FT | GROWTH_LENGTH | 3 |  | NOT_DOCUMENTED | NEW_ABS_B101_3in_bath_s | PLM-B101-NEW-PIPE-0004 | ANIM_ABS_Installation_Highlight | 0.0657 | 0.2883 | 0.2917
PLM-B101-NEW-SEG-0006 | ABS_GROWTH_NEW_ABS_B101_3in_laundry_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.0196 | FT | GROWTH_LENGTH | 3 |  | NOT_DOCUMENTED | NEW_ABS_B101_3in_laundry | PLM-B101-NEW-PIPE-0005 | ANIM_ABS_Installation_Highlight | 0.1177 | 0.2724 | 0.2916
PLM-B101-NEW-SEG-0007 | ABS_GROWTH_NEW_ABS_B101_4in_MAIN_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 17.7062 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B101_4in_MAIN | PLM-B101-NEW-PIPE-0006 | ANIM_ABS_Installation_Highlight | 0.2582 | 0.3056 | 0.3753
PLM-B101-NEW-SEG-0008 | ABS_GROWTH_NEW_ABS_B101_4in_MAIN_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 11.0757 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B101_4in_MAIN | PLM-B101-NEW-PIPE-0006 | ANIM_ABS_Installation_Highlight | 0.375 | 0.0189 | 0.3751
PLM-B101-NEW-SEG-0009 | ABS_GROWTH_NEW_ABS_B101_4in_MAIN_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 4.761 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B101_4in_MAIN | PLM-B101-NEW-PIPE-0006 | ANIM_ABS_Installation_Highlight | 0.375 | 0.0126 | 0.375
PLM-B101-NEW-SEG-0010 | ABS_GROWTH_NEW_ABS_B101_4in_MAIN_003 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 7.0749 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B101_4in_MAIN | PLM-B101-NEW-PIPE-0006 | ANIM_ABS_Installation_Highlight | 0.375 | 0.0149 | 0.3751
PLM-B101-NEW-SEG-0011 | ABS_GROWTH_NEW_ABS_B101_4in_MAIN_004 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 4.8144 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B101_4in_MAIN | PLM-B101-NEW-PIPE-0006 | ANIM_ABS_Installation_Highlight | 0.375 | 0.0126 | 0.375
PLM-B101-NEW-SEG-0012 | ABS_GROWTH_NEW_ABS_B101_6in_LATERAL_18IN_LIMIT_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LATERAL | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | GROWTH_LENGTH | 6 |  | NOT_DOCUMENTED | NEW_ABS_B101_6in_LATERAL_18IN_LIMIT | PLM-B101-NEW-PIPE-0007 | ANIM_ABS_Installation_Highlight | 0.5521 | 0.013 | 0.552
PLM-B101-NEW-SEG-0013 | ABS_GROWTH_PTRAP_B101_laundry_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.5 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B101_laundry | PLM-B101-NEW-FIT-0007 | ANIM_ABS_Installation_Highlight | 0.2917 | 0.2917 | 0.0005
PLM-B101-NEW-SEG-0014 | ABS_GROWTH_PTRAP_B101_laundry_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.3727 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B101_laundry | PLM-B101-NEW-FIT-0007 | ANIM_ABS_Installation_Highlight | 0.1308 | 0.2917 | 0.261
PLM-B101-NEW-SEG-0015 | ABS_GROWTH_PTRAP_B101_laundry_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.4167 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B101_laundry | PLM-B101-NEW-FIT-0007 | ANIM_ABS_Installation_Highlight | 0.1753 | 0.2917 | 0.2336
PLM-B101-NEW-SEG-0016 | ABS_GROWTH_PTRAP_B101_lav_n_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.5 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B101_lav_n | PLM-B101-NEW-FIT-0008 | ANIM_ABS_Installation_Highlight | 0.1979 | 0.1979 | 0.0005
PLM-B101-NEW-SEG-0017 | ABS_GROWTH_PTRAP_B101_lav_n_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.3727 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B101_lav_n | PLM-B101-NEW-FIT-0008 | ANIM_ABS_Installation_Highlight | 0.0888 | 0.1979 | 0.1772
PLM-B101-NEW-SEG-0018 | ABS_GROWTH_PTRAP_B101_lav_n_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.4167 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B101_lav_n | PLM-B101-NEW-FIT-0008 | ANIM_ABS_Installation_Highlight | 0.1191 | 0.1979 | 0.1586
PLM-B101-NEW-SEG-0019 | ABS_GROWTH_PTRAP_B101_lav_s_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.5 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B101_lav_s | PLM-B101-NEW-FIT-0009 | ANIM_ABS_Installation_Highlight | 0.1979 | 0.1979 | 0.0005
PLM-B101-NEW-SEG-0020 | ABS_GROWTH_PTRAP_B101_lav_s_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.3727 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B101_lav_s | PLM-B101-NEW-FIT-0009 | ANIM_ABS_Installation_Highlight | 0.0888 | 0.1979 | 0.1772
PLM-B101-NEW-SEG-0021 | ABS_GROWTH_PTRAP_B101_lav_s_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.4167 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B101_lav_s | PLM-B101-NEW-FIT-0009 | ANIM_ABS_Installation_Highlight | 0.1191 | 0.1979 | 0.1586
PLM-B101-NEW-SEG-0022 | ABS_GROWTH_TracerWire_B101_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | TracerWire_B101 | PLM-B101-NEW-TRW-0001 | ANIM_ABS_Installation_Highlight | 0.01 | 0.0017 | 0.01
PLM-B101-NEW-TRW-0001 | TracerWire_B101 | CURVE | New_ABS_UnderSlab_4in_6in | New_ABS_UnderSlab_4in_6in | B101 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | TRACER_WIRE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | 4D brief: insulated copper tracer wire at new underground nonmetallic pipe | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_Copper_Tracer | 2 | 3.5 | 2.0312
PLM-B101-REI-FIX-0001 | B101_BT_ALT2_NEW | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B101 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | BT-1 Kohler Villager 60in cast-iron tub representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 1 | 1 | 1
PLM-B101-REI-FIX-0002 | B101_BT_EXISTING | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B101 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | BT-1 Kohler Villager 60in cast-iron tub representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B101_MAT_Porcelain_White | 1 | 1 | 1
PLM-B101-REI-FIX-0003 | B101_KS1 | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B101 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | KS-1 Grohe 31815SD0 representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B101_MAT_Stainless | 1 | 1 | 1
PLM-B101-REI-FIX-0004 | B101_LAV_N | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B101 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | LAV-1 Kohler Caxton representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B101_MAT_Porcelain_White | 2 | 2 | 2
PLM-B101-REI-FIX-0005 | B101_LAV_S | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B101 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | LAV-1 Kohler Caxton representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B101_MAT_Porcelain_White | 2 | 2 | 2
PLM-B101-REI-FIX-0006 | B101_SH_N_GLASS | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B101 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Frameless shower enclosure | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B101_MAT_Glass | 1 | 1 | 1
PLM-B101-REI-FIX-0007 | B101_SH_N_PAN | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B101 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | SH-1 alcove shower | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B101_MAT_Porcelain_White | 1 | 1 | 1
PLM-B101-REI-FIX-0008 | B101_WB1 | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B101 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | LG WM4000HWA representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B101_MAT_Appliance_White | 1 | 1 | 1
PLM-B101-REI-FIX-0009 | B101_WC1_N_BOWL | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B101 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WC-1 Kohler Veil representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B101_MAT_Porcelain_White | 2 | 2 | 2
PLM-B101-REI-FIX-0010 | B101_WC1_S_BOWL | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B101 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WC-1 Kohler Veil representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B101_MAT_Porcelain_White | 2 | 2 | 2
PLM-B101-REI-FIX-0011 | B101_WC_ALT1_Floor_N_BOWL | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B101 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WC-1 Kohler Veil representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 2 | 2 | 2
PLM-B101-REI-FIX-0012 | B101_WC_ALT1_Floor_N_TANK | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B101 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Alternate #1 floor-mounted WC | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 1 | 1 | 1
PLM-B101-REI-FIX-0013 | B101_WC_ALT1_Floor_S_BOWL | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B101 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WC-1 Kohler Veil representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 2 | 2 | 2
PLM-B101-REI-FIX-0014 | B101_WC_ALT1_Floor_S_TANK | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B101 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Alternate #1 floor-mounted WC | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 1 | 1 | 1
PLM-B101-REI-FIX-0015 | B101_WH1 | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B101 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Rheem 40-gal electric WH | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_WH_Gray | 1.6875 | 1.6875 | 4.02
PLM-B101-TST-TST-0001 | HYDRO_NEW_ABS_B101_2in_lav_n | CURVE | ANIM_Water_Test | ANIM_Water_Test | B101 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAVATORY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 2in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 11.9202 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED | NEW_ABS_B101_2in_lav_n | PLM-B101-NEW-PIPE-0001 | ANIM_Hydrostatic_Pulse | 10.4825 | 5.9267 | 2.2483
PLM-B101-TST-TST-0002 | HYDRO_NEW_ABS_B101_2in_lav_s | CURVE | ANIM_Water_Test | ANIM_Water_Test | B101 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAVATORY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 2in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 3.4621 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED | NEW_ABS_B101_2in_lav_s | PLM-B101-NEW-PIPE-0002 | ANIM_Hydrostatic_Pulse | 4.5133 | 4.38 | 2.0721
PLM-B101-TST-TST-0003 | HYDRO_NEW_ABS_B101_3in_bath_n | CURVE | ANIM_Water_Test | ANIM_Water_Test | B101 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | BATH_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 5.09 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED | NEW_ABS_B101_3in_bath_n | PLM-B101-NEW-PIPE-0003 | ANIM_Hydrostatic_Pulse | 7.0267 | 2.7933 | 2.106
PLM-B101-TST-TST-0004 | HYDRO_NEW_ABS_B101_3in_bath_s | CURVE | ANIM_Water_Test | ANIM_Water_Test | B101 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | BATH_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 4.1614 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED | NEW_ABS_B101_3in_bath_s | PLM-B101-NEW-PIPE-0004 | ANIM_Hydrostatic_Pulse | 6.0842 | 2.7933 | 2.0867
PLM-B101-TST-TST-0005 | HYDRO_NEW_ABS_B101_3in_laundry | CURVE | ANIM_Water_Test | ANIM_Water_Test | B101 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAUNDRY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.0196 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED | NEW_ABS_B101_3in_laundry | PLM-B101-NEW-PIPE-0005 | ANIM_Hydrostatic_Pulse | 2.9425 | 2.3883 | 2.0212
PLM-B101-TST-TST-0006 | HYDRO_NEW_ABS_B101_4in_MAIN | CURVE | ANIM_Water_Test | ANIM_Water_Test | B101 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | MAIN | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3.1/P3.2 traced new Sch40 ABS | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 45.4323 | FT | CURVE_CENTERLINE | 4 | 0.25 | DOCUMENTED | NEW_ABS_B101_4in_MAIN | PLM-B101-NEW-PIPE-0006 | ANIM_Hydrostatic_Pulse | 15.6583 | 40.9817 | 2.9463
PLM-B101-TST-TST-0007 | HYDRO_NEW_ABS_B101_6in_LATERAL_18IN_LIMIT | CURVE | ANIM_Water_Test | ANIM_Water_Test | B101 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LATERAL | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/SOR: new 6in to 18in beyond foundation, then tie to existing lateral | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE | 6 | 0.25 | DOCUMENTED | NEW_ABS_B101_6in_LATERAL_18IN_LIMIT | PLM-B101-NEW-PIPE-0007 | ANIM_Hydrostatic_Pulse | 2 | 3.5 | 2.0312
PLM-B101-TST-TST-0008 | HYDRO_PTRAP_B101_laundry | CURVE | ANIM_Water_Test | ANIM_Water_Test | B101 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAUNDRY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NOT_DOCUMENTED | PTRAP_B101_laundry | PLM-B101-NEW-FIT-0007 | ANIM_Hydrostatic_Pulse | 2.6667 | 2 | 2.6667
PLM-B101-TST-TST-0009 | HYDRO_PTRAP_B101_lav_n | CURVE | ANIM_Water_Test | ANIM_Water_Test | B101 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAVATORY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NOT_DOCUMENTED | PTRAP_B101_lav_n | PLM-B101-NEW-FIT-0008 | ANIM_Hydrostatic_Pulse | 2.6667 | 2 | 2.6667
PLM-B101-TST-TST-0010 | HYDRO_PTRAP_B101_lav_s | CURVE | ANIM_Water_Test | ANIM_Water_Test | B101 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAVATORY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NOT_DOCUMENTED | PTRAP_B101_lav_s | PLM-B101-NEW-FIT-0009 | ANIM_Hydrostatic_Pulse | 2.6667 | 2 | 2.6667
PLM-B101-TST-TST-0011 | HYDRO_TracerWire_B101 | CURVE | ANIM_Water_Test | ANIM_Water_Test | B101 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | 4D brief: insulated copper tracer wire at new underground nonmetallic pipe | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE |  |  | NOT_DOCUMENTED | TracerWire_B101 | PLM-B101-NEW-TRW-0001 | ANIM_Hydrostatic_Pulse | 2 | 3.5 | 2.0312
PLM-B102-DEM-PIPE-0001 | EX_CI_B102_BR2_lav_n | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B102 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | LAVATORY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing lavatory/fixture branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 7.2655 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 6.331 | 3.9064 | 0.3492
PLM-B102-DEM-PIPE-0002 | EX_CI_B102_BR2_lav_s | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B102 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | LAVATORY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing lavatory/fixture branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 6.4937 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 6.0369 | 2.76 | 0.3331
PLM-B102-DEM-PIPE-0003 | EX_CI_B102_BR3_bath_n | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B102 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | BATH_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 4.7565 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 4.6772 | 1.4724 | 0.3907
PLM-B102-DEM-PIPE-0004 | EX_CI_B102_BR3_bath_s | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B102 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | BATH_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 5.1278 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 4.9653 | 1.864 | 0.3984
PLM-B102-DEM-PIPE-0005 | EX_CI_B102_BR3_kitchen | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B102 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | KITCHEN_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 1.3333 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 1.2533 | 1.0137 | 0.3194
PLM-B102-DEM-PIPE-0006 | EX_CI_B102_BR3_laundry | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B102 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | LAUNDRY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 1.1511 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 1.1817 | 0.6629 | 0.3156
PLM-B102-DEM-PIPE-0007 | EX_CI_B102_LAT6_REPLACE | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B102 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | LATERAL | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing 6in segment within 18in replacement limit; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE | 6 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 0.5521 | 1.5115 | 0.5832
PLM-B102-DEM-PIPE-0008 | EX_CI_B102_MAIN4 | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B102 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | MAIN | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Like-for-like existing route representation; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 48.4342 | FT | CURVE_CENTERLINE | 4 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 23.176 | 39.65 | 1.3837
PLM-B102-NEW-CO-0001 | B102_BaseOfStack_Cleanout_1 | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Base-of-stack cleanout | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Nickel_Bronze | 0.435 | 0.435 | 0.435
PLM-B102-NEW-CO-0002 | B102_BaseOfStack_Cleanout_2 | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Base-of-stack cleanout | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Nickel_Bronze | 0.3383 | 0.3383 | 0.3383
PLM-B102-NEW-CO-0003 | B102_BaseOfStack_Cleanout_3 | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Base-of-stack cleanout | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Nickel_Bronze | 0.3383 | 0.3383 | 0.3383
PLM-B102-NEW-CO-0004 | B102_Cleanout_12x12_Pad | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | 12x12 concrete cleanout pad | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
PLM-B102-NEW-CO-0005 | B102_Zurn_Z1450_6in_Cleanout | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | 4D brief / SOR: exterior 6in cleanout at replacement limit | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 6 |  | NA |  |  | MAT_ABS_Schedule40_Black | 2 | 2 | 5.7812
PLM-B102-NEW-FIT-0001 | B102_6in_TransitionCoupling | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02: 4in waste to 6in waste transition; match existing I.E. | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 6 |  | NA |  |  | MAT_ABS_Schedule40_Black | 0.6846 | 0.6846 | 0.8333
PLM-B102-NEW-FIT-0002 | B102_StackTieIn_1_4in | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01/P5.1 stack tie-in vertical exposure | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 4 |  | NA |  |  | MAT_ABS_Schedule40_Black | 2 | 2 | 6.3333
PLM-B102-NEW-FIT-0003 | B102_StackTieIn_2_3in | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01/P5.1 stack tie-in vertical exposure | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 3 |  | NA |  |  | MAT_ABS_Schedule40_Black | 2 | 2 | 6
PLM-B102-NEW-FIT-0004 | B102_StackTieIn_3_3in | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01/P5.1 stack tie-in vertical exposure | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 3 |  | NA |  |  | MAT_ABS_Schedule40_Black | 2 | 2 | 6
PLM-B102-NEW-FIT-0005 | B102_TestPlug | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WP2 test plug visualization | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_TestPlug | 0.3375 | 0.3375 | 0.1667
PLM-B102-NEW-FIT-0006 | B102_WP2_WaterTest | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Phase 5 water-test visualization | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Water_Test_Blue | 24.9267 | 41.37 | 3.0088
PLM-B102-NEW-FIT-0007 | PTRAP_B102_kitchen | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_ABS_Schedule40_Black | 2.6667 | 2 | 2.6667
PLM-B102-NEW-FIT-0008 | PTRAP_B102_laundry | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_ABS_Schedule40_Black | 2.6667 | 2 | 2.6667
PLM-B102-NEW-FIT-0009 | PTRAP_B102_lav_n | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_ABS_Schedule40_Black | 2.6667 | 2 | 2.6667
PLM-B102-NEW-FIT-0010 | PTRAP_B102_lav_s | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_ABS_Schedule40_Black | 2.6667 | 2 | 2.6667
PLM-B102-NEW-PIPE-0001 | NEW_ABS_B102_2in_lav_n | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | LAVATORY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 2in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 7.2655 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 8.2292 | 5.7367 | 2.1513
PLM-B102-NEW-PIPE-0002 | NEW_ABS_B102_2in_lav_s | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | LAVATORY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 2in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 6.4937 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 7.9583 | 4.5783 | 2.1353
PLM-B102-NEW-PIPE-0003 | NEW_ABS_B102_3in_bath_n | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | BATH_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 4.7565 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 6.6042 | 3.19 | 2.0991
PLM-B102-NEW-PIPE-0004 | NEW_ABS_B102_3in_bath_s | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | BATH_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 5.1278 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 6.875 | 3.5867 | 2.1068
PLM-B102-NEW-PIPE-0005 | NEW_ABS_B102_3in_kitchen | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | KITCHEN_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.3333 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 3.0833 | 2.7767 | 2.0278
PLM-B102-NEW-PIPE-0006 | NEW_ABS_B102_3in_laundry | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | LAUNDRY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.1511 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 3.0833 | 2.3883 | 2.024
PLM-B102-NEW-PIPE-0007 | NEW_ABS_B102_4in_MAIN | CURVE | New_ABS_UnderSlab_4in_6in | New_ABS_UnderSlab_4in_6in | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | MAIN | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3.1/P3.2 traced new Sch40 ABS | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 48.4342 | FT | CURVE_CENTERLINE | 4 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 24.9267 | 41.37 | 3.0088
PLM-B102-NEW-PIPE-0008 | NEW_ABS_B102_6in_LATERAL_18IN_LIMIT | CURVE | New_ABS_UnderSlab_4in_6in | New_ABS_UnderSlab_4in_6in | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | LATERAL | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/SOR: new 6in to 18in beyond foundation, then tie to existing lateral | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE | 6 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 2 | 3.5 | 2.0312
PLM-B102-NEW-SEG-0001 | ABS_GROWTH_NEW_ABS_B102_2in_lav_n_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 7.2655 | FT | GROWTH_LENGTH | 2 |  | NOT_DOCUMENTED | NEW_ABS_B102_2in_lav_n | PLM-B102-NEW-PIPE-0001 | ANIM_ABS_Installation_Highlight | 0.1116 | 0.1756 | 0.198
PLM-B102-NEW-SEG-0002 | ABS_GROWTH_NEW_ABS_B102_2in_lav_s_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 6.4937 | FT | GROWTH_LENGTH | 2 |  | NOT_DOCUMENTED | NEW_ABS_B102_2in_lav_s | PLM-B102-NEW-PIPE-0002 | ANIM_ABS_Installation_Highlight | 0.0883 | 0.1859 | 0.198
PLM-B102-NEW-SEG-0003 | ABS_GROWTH_NEW_ABS_B102_3in_bath_n_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | BATH_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 4.7565 | FT | GROWTH_LENGTH | 3 |  | NOT_DOCUMENTED | NEW_ABS_B102_3in_bath_n | PLM-B102-NEW-PIPE-0003 | ANIM_ABS_Installation_Highlight | 0.0835 | 0.2851 | 0.2917
PLM-B102-NEW-SEG-0004 | ABS_GROWTH_NEW_ABS_B102_3in_bath_s_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | BATH_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 5.1278 | FT | GROWTH_LENGTH | 3 |  | NOT_DOCUMENTED | NEW_ABS_B102_3in_bath_s | PLM-B102-NEW-PIPE-0004 | ANIM_ABS_Installation_Highlight | 0.1009 | 0.2808 | 0.2917
PLM-B102-NEW-SEG-0005 | ABS_GROWTH_NEW_ABS_B102_3in_kitchen_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | KITCHEN_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.3333 | FT | GROWTH_LENGTH | 3 |  | NOT_DOCUMENTED | NEW_ABS_B102_3in_kitchen | PLM-B102-NEW-PIPE-0005 | ANIM_ABS_Installation_Highlight | 0.176 | 0.2414 | 0.2916
PLM-B102-NEW-SEG-0006 | ABS_GROWTH_NEW_ABS_B102_3in_laundry_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.1511 | FT | GROWTH_LENGTH | 3 |  | NOT_DOCUMENTED | NEW_ABS_B102_3in_laundry | PLM-B102-NEW-PIPE-0006 | ANIM_ABS_Installation_Highlight | 0.1052 | 0.277 | 0.2916
PLM-B102-NEW-SEG-0007 | ABS_GROWTH_NEW_ABS_B102_4in_MAIN_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 18.5313 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B102_4in_MAIN | PLM-B102-NEW-PIPE-0007 | ANIM_ABS_Installation_Highlight | 0.2637 | 0.3022 | 0.3753
PLM-B102-NEW-SEG-0008 | ABS_GROWTH_NEW_ABS_B102_4in_MAIN_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 9.1619 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B102_4in_MAIN | PLM-B102-NEW-PIPE-0007 | ANIM_ABS_Installation_Highlight | 0.3684 | 0.1052 | 0.3751
PLM-B102-NEW-SEG-0009 | ABS_GROWTH_NEW_ABS_B102_4in_MAIN_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 5.4175 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B102_4in_MAIN | PLM-B102-NEW-PIPE-0007 | ANIM_ABS_Installation_Highlight | 0.3727 | 0.0693 | 0.375
PLM-B102-NEW-SEG-0010 | ABS_GROWTH_NEW_ABS_B102_4in_MAIN_003 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 8.4311 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B102_4in_MAIN | PLM-B102-NEW-PIPE-0007 | ANIM_ABS_Installation_Highlight | 0.3748 | 0.0523 | 0.3751
PLM-B102-NEW-SEG-0011 | ABS_GROWTH_NEW_ABS_B102_4in_MAIN_004 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 6.8924 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B102_4in_MAIN | PLM-B102-NEW-PIPE-0007 | ANIM_ABS_Installation_Highlight | 0.2658 | 0.2849 | 0.3751
PLM-B102-NEW-SEG-0012 | ABS_GROWTH_NEW_ABS_B102_6in_LATERAL_18IN_LIMIT_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LATERAL | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | GROWTH_LENGTH | 6 |  | NOT_DOCUMENTED | NEW_ABS_B102_6in_LATERAL_18IN_LIMIT | PLM-B102-NEW-PIPE-0008 | ANIM_ABS_Installation_Highlight | 0.5521 | 0.013 | 0.552
PLM-B102-NEW-SEG-0013 | ABS_GROWTH_PTRAP_B102_kitchen_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | KITCHEN_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.5 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B102_kitchen | PLM-B102-NEW-FIT-0007 | ANIM_ABS_Installation_Highlight | 0.2917 | 0.2917 | 0.0005
PLM-B102-NEW-SEG-0014 | ABS_GROWTH_PTRAP_B102_kitchen_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | KITCHEN_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.3727 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B102_kitchen | PLM-B102-NEW-FIT-0007 | ANIM_ABS_Installation_Highlight | 0.1308 | 0.2917 | 0.261
PLM-B102-NEW-SEG-0015 | ABS_GROWTH_PTRAP_B102_kitchen_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | KITCHEN_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.4167 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B102_kitchen | PLM-B102-NEW-FIT-0007 | ANIM_ABS_Installation_Highlight | 0.1753 | 0.2917 | 0.2336
PLM-B102-NEW-SEG-0016 | ABS_GROWTH_PTRAP_B102_laundry_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.5 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B102_laundry | PLM-B102-NEW-FIT-0008 | ANIM_ABS_Installation_Highlight | 0.2917 | 0.2917 | 0.0005
PLM-B102-NEW-SEG-0017 | ABS_GROWTH_PTRAP_B102_laundry_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.3727 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B102_laundry | PLM-B102-NEW-FIT-0008 | ANIM_ABS_Installation_Highlight | 0.1308 | 0.2917 | 0.261
PLM-B102-NEW-SEG-0018 | ABS_GROWTH_PTRAP_B102_laundry_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.4167 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B102_laundry | PLM-B102-NEW-FIT-0008 | ANIM_ABS_Installation_Highlight | 0.1753 | 0.2917 | 0.2336
PLM-B102-NEW-SEG-0019 | ABS_GROWTH_PTRAP_B102_lav_n_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.5 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B102_lav_n | PLM-B102-NEW-FIT-0009 | ANIM_ABS_Installation_Highlight | 0.1979 | 0.1979 | 0.0005
PLM-B102-NEW-SEG-0020 | ABS_GROWTH_PTRAP_B102_lav_n_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.3727 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B102_lav_n | PLM-B102-NEW-FIT-0009 | ANIM_ABS_Installation_Highlight | 0.0888 | 0.1979 | 0.1772
PLM-B102-NEW-SEG-0021 | ABS_GROWTH_PTRAP_B102_lav_n_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.4167 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B102_lav_n | PLM-B102-NEW-FIT-0009 | ANIM_ABS_Installation_Highlight | 0.1191 | 0.1979 | 0.1586
PLM-B102-NEW-SEG-0022 | ABS_GROWTH_PTRAP_B102_lav_s_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.5 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B102_lav_s | PLM-B102-NEW-FIT-0010 | ANIM_ABS_Installation_Highlight | 0.1979 | 0.1979 | 0.0005
PLM-B102-NEW-SEG-0023 | ABS_GROWTH_PTRAP_B102_lav_s_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.3727 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B102_lav_s | PLM-B102-NEW-FIT-0010 | ANIM_ABS_Installation_Highlight | 0.0888 | 0.1979 | 0.1772
PLM-B102-NEW-SEG-0024 | ABS_GROWTH_PTRAP_B102_lav_s_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.4167 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B102_lav_s | PLM-B102-NEW-FIT-0010 | ANIM_ABS_Installation_Highlight | 0.1191 | 0.1979 | 0.1586
PLM-B102-NEW-SEG-0025 | ABS_GROWTH_TracerWire_B102_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | TracerWire_B102 | PLM-B102-NEW-TRW-0001 | ANIM_ABS_Installation_Highlight | 0.01 | 0.0017 | 0.01
PLM-B102-NEW-TRW-0001 | TracerWire_B102 | CURVE | New_ABS_UnderSlab_4in_6in | New_ABS_UnderSlab_4in_6in | B102 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | TRACER_WIRE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | 4D brief: insulated copper tracer wire at new underground nonmetallic pipe | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_Copper_Tracer | 2 | 3.5 | 2.0312
PLM-B102-REI-FIX-0001 | B102_BT_ALT2_NEW | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B102 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | BT-1 Kohler Villager 60in cast-iron tub representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 1 | 1 | 1
PLM-B102-REI-FIX-0002 | B102_BT_EXISTING | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B102 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | BT-1 Kohler Villager 60in cast-iron tub representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B102_MAT_Porcelain_White | 1 | 1 | 1
PLM-B102-REI-FIX-0003 | B102_KS1 | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B102 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | KS-1 Grohe 31815SD0 representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B102_MAT_Stainless | 1 | 1 | 1
PLM-B102-REI-FIX-0004 | B102_LAV_N | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B102 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | LAV-1 Kohler Caxton representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B102_MAT_Porcelain_White | 2 | 2 | 2
PLM-B102-REI-FIX-0005 | B102_LAV_S | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B102 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | LAV-1 Kohler Caxton representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B102_MAT_Porcelain_White | 2 | 2 | 2
PLM-B102-REI-FIX-0006 | B102_SH_N_GLASS | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B102 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Frameless shower enclosure | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B102_MAT_Glass | 1 | 1 | 1
PLM-B102-REI-FIX-0007 | B102_SH_N_PAN | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B102 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | SH-1 alcove shower | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B102_MAT_Porcelain_White | 1 | 1 | 1
PLM-B102-REI-FIX-0008 | B102_WB1 | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B102 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | LG WM4000HWA representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B102_MAT_Appliance_White | 1 | 1 | 1
PLM-B102-REI-FIX-0009 | B102_WC1_N_BOWL | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B102 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WC-1 Kohler Veil representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B102_MAT_Porcelain_White | 2 | 2 | 2
PLM-B102-REI-FIX-0010 | B102_WC1_S_BOWL | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B102 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WC-1 Kohler Veil representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B102_MAT_Porcelain_White | 2 | 2 | 2
PLM-B102-REI-FIX-0011 | B102_WC_ALT1_Floor_N_BOWL | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B102 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WC-1 Kohler Veil representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 2 | 2 | 2
PLM-B102-REI-FIX-0012 | B102_WC_ALT1_Floor_N_TANK | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B102 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Alternate #1 floor-mounted WC | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 1 | 1 | 1
PLM-B102-REI-FIX-0013 | B102_WC_ALT1_Floor_S_BOWL | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B102 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WC-1 Kohler Veil representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 2 | 2 | 2
PLM-B102-REI-FIX-0014 | B102_WC_ALT1_Floor_S_TANK | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B102 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Alternate #1 floor-mounted WC | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 1 | 1 | 1
PLM-B102-REI-FIX-0015 | B102_WH1 | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B102 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Rheem 40-gal electric WH | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_WH_Gray | 1.6875 | 1.6875 | 4.02
PLM-B102-TST-TST-0001 | HYDRO_NEW_ABS_B102_2in_lav_n | CURVE | ANIM_Water_Test | ANIM_Water_Test | B102 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAVATORY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 2in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 7.2655 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED | NEW_ABS_B102_2in_lav_n | PLM-B102-NEW-PIPE-0001 | ANIM_Hydrostatic_Pulse | 8.2292 | 5.7367 | 2.1513
PLM-B102-TST-TST-0002 | HYDRO_NEW_ABS_B102_2in_lav_s | CURVE | ANIM_Water_Test | ANIM_Water_Test | B102 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAVATORY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 2in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 6.4937 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED | NEW_ABS_B102_2in_lav_s | PLM-B102-NEW-PIPE-0002 | ANIM_Hydrostatic_Pulse | 7.9583 | 4.5783 | 2.1353
PLM-B102-TST-TST-0003 | HYDRO_NEW_ABS_B102_3in_bath_n | CURVE | ANIM_Water_Test | ANIM_Water_Test | B102 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | BATH_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 4.7565 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED | NEW_ABS_B102_3in_bath_n | PLM-B102-NEW-PIPE-0003 | ANIM_Hydrostatic_Pulse | 6.6042 | 3.19 | 2.0991
PLM-B102-TST-TST-0004 | HYDRO_NEW_ABS_B102_3in_bath_s | CURVE | ANIM_Water_Test | ANIM_Water_Test | B102 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | BATH_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 5.1278 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED | NEW_ABS_B102_3in_bath_s | PLM-B102-NEW-PIPE-0004 | ANIM_Hydrostatic_Pulse | 6.875 | 3.5867 | 2.1068
PLM-B102-TST-TST-0005 | HYDRO_NEW_ABS_B102_3in_kitchen | CURVE | ANIM_Water_Test | ANIM_Water_Test | B102 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | KITCHEN_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.3333 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED | NEW_ABS_B102_3in_kitchen | PLM-B102-NEW-PIPE-0005 | ANIM_Hydrostatic_Pulse | 3.0833 | 2.7767 | 2.0278
PLM-B102-TST-TST-0006 | HYDRO_NEW_ABS_B102_3in_laundry | CURVE | ANIM_Water_Test | ANIM_Water_Test | B102 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAUNDRY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.1511 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED | NEW_ABS_B102_3in_laundry | PLM-B102-NEW-PIPE-0006 | ANIM_Hydrostatic_Pulse | 3.0833 | 2.3883 | 2.024
PLM-B102-TST-TST-0007 | HYDRO_NEW_ABS_B102_4in_MAIN | CURVE | ANIM_Water_Test | ANIM_Water_Test | B102 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | MAIN | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3.1/P3.2 traced new Sch40 ABS | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 48.4342 | FT | CURVE_CENTERLINE | 4 | 0.25 | DOCUMENTED | NEW_ABS_B102_4in_MAIN | PLM-B102-NEW-PIPE-0007 | ANIM_Hydrostatic_Pulse | 24.9267 | 41.37 | 3.0088
PLM-B102-TST-TST-0008 | HYDRO_NEW_ABS_B102_6in_LATERAL_18IN_LIMIT | CURVE | ANIM_Water_Test | ANIM_Water_Test | B102 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LATERAL | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/SOR: new 6in to 18in beyond foundation, then tie to existing lateral | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE | 6 | 0.25 | DOCUMENTED | NEW_ABS_B102_6in_LATERAL_18IN_LIMIT | PLM-B102-NEW-PIPE-0008 | ANIM_Hydrostatic_Pulse | 2 | 3.5 | 2.0312
PLM-B102-TST-TST-0009 | HYDRO_PTRAP_B102_kitchen | CURVE | ANIM_Water_Test | ANIM_Water_Test | B102 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | KITCHEN_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NOT_DOCUMENTED | PTRAP_B102_kitchen | PLM-B102-NEW-FIT-0007 | ANIM_Hydrostatic_Pulse | 2.6667 | 2 | 2.6667
PLM-B102-TST-TST-0010 | HYDRO_PTRAP_B102_laundry | CURVE | ANIM_Water_Test | ANIM_Water_Test | B102 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAUNDRY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NOT_DOCUMENTED | PTRAP_B102_laundry | PLM-B102-NEW-FIT-0008 | ANIM_Hydrostatic_Pulse | 2.6667 | 2 | 2.6667
PLM-B102-TST-TST-0011 | HYDRO_PTRAP_B102_lav_n | CURVE | ANIM_Water_Test | ANIM_Water_Test | B102 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAVATORY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NOT_DOCUMENTED | PTRAP_B102_lav_n | PLM-B102-NEW-FIT-0009 | ANIM_Hydrostatic_Pulse | 2.6667 | 2 | 2.6667
PLM-B102-TST-TST-0012 | HYDRO_PTRAP_B102_lav_s | CURVE | ANIM_Water_Test | ANIM_Water_Test | B102 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAVATORY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NOT_DOCUMENTED | PTRAP_B102_lav_s | PLM-B102-NEW-FIT-0010 | ANIM_Hydrostatic_Pulse | 2.6667 | 2 | 2.6667
PLM-B102-TST-TST-0013 | HYDRO_TracerWire_B102 | CURVE | ANIM_Water_Test | ANIM_Water_Test | B102 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | 4D brief: insulated copper tracer wire at new underground nonmetallic pipe | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE |  |  | NOT_DOCUMENTED | TracerWire_B102 | PLM-B102-NEW-TRW-0001 | ANIM_Hydrostatic_Pulse | 2 | 3.5 | 2.0312
PLM-B103-DEM-PIPE-0001 | EX_CI_B103_BR2_lav_n | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B103 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | LAVATORY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing lavatory/fixture branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 6.5059 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 5.3505 | 4.0226 | 0.3334
PLM-B103-DEM-PIPE-0002 | EX_CI_B103_BR2_lav_s | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B103 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | LAVATORY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing lavatory/fixture branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 9.131 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 8.8649 | 2.5711 | 0.3881
PLM-B103-DEM-PIPE-0003 | EX_CI_B103_BR3_bath_n | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B103 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | BATH_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 5.7986 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 5.8041 | 0.6877 | 0.4124
PLM-B103-DEM-PIPE-0004 | EX_CI_B103_BR3_bath_s | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B103 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | BATH_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 7.7541 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 7.7415 | 1.0835 | 0.4531
PLM-B103-DEM-PIPE-0005 | EX_CI_B103_BR3_laundry | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B103 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | LAUNDRY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 0.337 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 0.4435 | 0.4325 | 0.2986
PLM-B103-DEM-PIPE-0006 | EX_CI_B103_LAT6_REPLACE | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B103 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | LATERAL | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing 6in segment within 18in replacement limit; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE | 6 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 0.5521 | 1.5115 | 0.5832
PLM-B103-DEM-PIPE-0007 | EX_CI_B103_MAIN4 | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B103 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | MAIN | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Like-for-like existing route representation; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 31.5901 | FT | CURVE_CENTERLINE | 4 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 10.2362 | 27.6612 | 1.0329
PLM-B103-NEW-CO-0001 | B103_BaseOfStack_Cleanout_1 | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Base-of-stack cleanout | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Nickel_Bronze | 0.435 | 0.435 | 0.435
PLM-B103-NEW-CO-0002 | B103_BaseOfStack_Cleanout_2 | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Base-of-stack cleanout | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Nickel_Bronze | 0.3383 | 0.3383 | 0.3383
PLM-B103-NEW-CO-0003 | B103_BaseOfStack_Cleanout_3 | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Base-of-stack cleanout | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Nickel_Bronze | 0.3383 | 0.3383 | 0.3383
PLM-B103-NEW-CO-0004 | B103_Cleanout_12x12_Pad | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | 12x12 concrete cleanout pad | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
PLM-B103-NEW-CO-0005 | B103_Zurn_Z1450_6in_Cleanout | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | 4D brief / SOR: exterior 6in cleanout at replacement limit | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 6 |  | NA |  |  | MAT_ABS_Schedule40_Black | 2 | 2 | 5.7812
PLM-B103-NEW-FIT-0001 | B103_6in_TransitionCoupling | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02: 4in waste to 6in waste transition; match existing I.E. | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 6 |  | NA |  |  | MAT_ABS_Schedule40_Black | 0.6846 | 0.6846 | 0.8333
PLM-B103-NEW-FIT-0002 | B103_StackTieIn_1_4in | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01/P5.1 stack tie-in vertical exposure | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 4 |  | NA |  |  | MAT_ABS_Schedule40_Black | 2 | 2 | 6.3333
PLM-B103-NEW-FIT-0003 | B103_StackTieIn_2_3in | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01/P5.1 stack tie-in vertical exposure | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 3 |  | NA |  |  | MAT_ABS_Schedule40_Black | 2 | 2 | 6
PLM-B103-NEW-FIT-0004 | B103_StackTieIn_3_3in | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01/P5.1 stack tie-in vertical exposure | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 3 |  | NA |  |  | MAT_ABS_Schedule40_Black | 2 | 2 | 6
PLM-B103-NEW-FIT-0005 | B103_TestPlug | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WP2 test plug visualization | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_TestPlug | 0.3375 | 0.3375 | 0.1667
PLM-B103-NEW-FIT-0006 | B103_WP2_WaterTest | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Phase 5 water-test visualization | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Water_Test_Blue | 11.915 | 29.5258 | 2.658
PLM-B103-NEW-FIT-0007 | PTRAP_B103_laundry | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_ABS_Schedule40_Black | 2.6667 | 2 | 2.6667
PLM-B103-NEW-FIT-0008 | PTRAP_B103_lav_n | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_ABS_Schedule40_Black | 2.6667 | 2 | 2.6667
PLM-B103-NEW-FIT-0009 | PTRAP_B103_lav_s | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_ABS_Schedule40_Black | 2.6667 | 2 | 2.6667
PLM-B103-NEW-PIPE-0001 | NEW_ABS_B103_2in_lav_n | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | LAVATORY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 2in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 6.5059 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 7.2329 | 5.8633 | 2.1355
PLM-B103-NEW-PIPE-0002 | NEW_ABS_B103_2in_lav_s | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | LAVATORY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 2in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 9.131 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 10.8133 | 4.38 | 2.1902
PLM-B103-NEW-PIPE-0003 | NEW_ABS_B103_3in_bath_n | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | BATH_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 5.7986 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 7.7838 | 2.3967 | 2.1208
PLM-B103-NEW-PIPE-0004 | NEW_ABS_B103_3in_bath_s | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | BATH_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 7.7541 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 9.7117 | 2.7933 | 2.1615
PLM-B103-NEW-PIPE-0005 | NEW_ABS_B103_3in_laundry | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | LAUNDRY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.337 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 2.2754 | 2.1942 | 2.007
PLM-B103-NEW-PIPE-0006 | NEW_ABS_B103_4in_MAIN | CURVE | New_ABS_UnderSlab_4in_6in | New_ABS_UnderSlab_4in_6in | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | MAIN | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3.1/P3.2 traced new Sch40 ABS | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 31.5901 | FT | CURVE_CENTERLINE | 4 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 11.915 | 29.5258 | 2.658
PLM-B103-NEW-PIPE-0007 | NEW_ABS_B103_4in_RAISED_FLOOR | CURVE | New_ABS_UnderSlab_4in_6in | New_ABS_UnderSlab_4in_6in | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P3.2 / 4D brief: B103 4in sanitary in raised floor assembly | FIELD_VERIFY_REQUIRED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 30.6833 | FT | CURVE_CENTERLINE | 4 |  | NOT_DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 18.5617 | 14.0383 | 4.0833
PLM-B103-NEW-PIPE-0008 | NEW_ABS_B103_6in_LATERAL_18IN_LIMIT | CURVE | New_ABS_UnderSlab_4in_6in | New_ABS_UnderSlab_4in_6in | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | LATERAL | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/SOR: new 6in to 18in beyond foundation, then tie to existing lateral | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE | 6 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 2 | 3.5 | 2.0312
PLM-B103-NEW-SEG-0001 | ABS_GROWTH_NEW_ABS_B103_2in_lav_n_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 6.5059 | FT | GROWTH_LENGTH | 2 |  | NOT_DOCUMENTED | NEW_ABS_B103_2in_lav_n | PLM-B103-NEW-PIPE-0001 | ANIM_ABS_Installation_Highlight | 0.1261 | 0.1655 | 0.198
PLM-B103-NEW-SEG-0002 | ABS_GROWTH_NEW_ABS_B103_2in_lav_s_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 9.131 | FT | GROWTH_LENGTH | 2 |  | NOT_DOCUMENTED | NEW_ABS_B103_2in_lav_s | PLM-B103-NEW-PIPE-0002 | ANIM_ABS_Installation_Highlight | 0.0644 | 0.1945 | 0.1981
PLM-B103-NEW-SEG-0003 | ABS_GROWTH_NEW_ABS_B103_3in_bath_n_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | BATH_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 5.7986 | FT | GROWTH_LENGTH | 3 |  | NOT_DOCUMENTED | NEW_ABS_B103_3in_bath_n | PLM-B103-NEW-PIPE-0003 | ANIM_ABS_Installation_Highlight | 0.0318 | 0.2918 | 0.2917
PLM-B103-NEW-SEG-0004 | ABS_GROWTH_NEW_ABS_B103_3in_bath_s_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | BATH_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 7.7541 | FT | GROWTH_LENGTH | 3 |  | NOT_DOCUMENTED | NEW_ABS_B103_3in_bath_s | PLM-B103-NEW-PIPE-0004 | ANIM_ABS_Installation_Highlight | 0.0436 | 0.2915 | 0.2918
PLM-B103-NEW-SEG-0005 | ABS_GROWTH_NEW_ABS_B103_3in_laundry_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.337 | FT | GROWTH_LENGTH | 3 |  | NOT_DOCUMENTED | NEW_ABS_B103_3in_laundry | PLM-B103-NEW-PIPE-0005 | ANIM_ABS_Installation_Highlight | 0.1733 | 0.2421 | 0.2916
PLM-B103-NEW-SEG-0006 | ABS_GROWTH_NEW_ABS_B103_4in_MAIN_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 14.1463 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B103_4in_MAIN | PLM-B103-NEW-PIPE-0006 | ANIM_ABS_Installation_Highlight | 0.2828 | 0.2785 | 0.3752
PLM-B103-NEW-SEG-0007 | ABS_GROWTH_NEW_ABS_B103_4in_MAIN_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 5.1578 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B103_4in_MAIN | PLM-B103-NEW-PIPE-0006 | ANIM_ABS_Installation_Highlight | 0.375 | 0.013 | 0.375
PLM-B103-NEW-SEG-0008 | ABS_GROWTH_NEW_ABS_B103_4in_MAIN_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 7.4716 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B103_4in_MAIN | PLM-B103-NEW-PIPE-0006 | ANIM_ABS_Installation_Highlight | 0.375 | 0.0153 | 0.3751
PLM-B103-NEW-SEG-0009 | ABS_GROWTH_NEW_ABS_B103_4in_MAIN_003 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 4.8144 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B103_4in_MAIN | PLM-B103-NEW-PIPE-0006 | ANIM_ABS_Installation_Highlight | 0.375 | 0.0126 | 0.375
PLM-B103-NEW-SEG-0010 | ABS_GROWTH_NEW_ABS_B103_4in_RAISED_FLOOR_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 16.5617 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B103_4in_RAISED_FLOOR | PLM-B103-NEW-PIPE-0007 | ANIM_ABS_Installation_Highlight | 0.0166 | 0.375 | 0.375
PLM-B103-NEW-SEG-0011 | ABS_GROWTH_NEW_ABS_B103_4in_RAISED_FLOOR_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 12.0383 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B103_4in_RAISED_FLOOR | PLM-B103-NEW-PIPE-0007 | ANIM_ABS_Installation_Highlight | 0.375 | 0.012 | 0.375
PLM-B103-NEW-SEG-0012 | ABS_GROWTH_NEW_ABS_B103_4in_RAISED_FLOOR_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 2.0833 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B103_4in_RAISED_FLOOR | PLM-B103-NEW-PIPE-0007 | ANIM_ABS_Installation_Highlight | 0.375 | 0.375 | 0.0021
PLM-B103-NEW-SEG-0013 | ABS_GROWTH_NEW_ABS_B103_6in_LATERAL_18IN_LIMIT_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LATERAL | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | GROWTH_LENGTH | 6 |  | NOT_DOCUMENTED | NEW_ABS_B103_6in_LATERAL_18IN_LIMIT | PLM-B103-NEW-PIPE-0008 | ANIM_ABS_Installation_Highlight | 0.5521 | 0.013 | 0.552
PLM-B103-NEW-SEG-0014 | ABS_GROWTH_PTRAP_B103_laundry_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.5 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B103_laundry | PLM-B103-NEW-FIT-0007 | ANIM_ABS_Installation_Highlight | 0.2917 | 0.2917 | 0.0005
PLM-B103-NEW-SEG-0015 | ABS_GROWTH_PTRAP_B103_laundry_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.3727 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B103_laundry | PLM-B103-NEW-FIT-0007 | ANIM_ABS_Installation_Highlight | 0.1308 | 0.2917 | 0.261
PLM-B103-NEW-SEG-0016 | ABS_GROWTH_PTRAP_B103_laundry_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.4167 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B103_laundry | PLM-B103-NEW-FIT-0007 | ANIM_ABS_Installation_Highlight | 0.1753 | 0.2917 | 0.2336
PLM-B103-NEW-SEG-0017 | ABS_GROWTH_PTRAP_B103_lav_n_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.5 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B103_lav_n | PLM-B103-NEW-FIT-0008 | ANIM_ABS_Installation_Highlight | 0.1979 | 0.1979 | 0.0005
PLM-B103-NEW-SEG-0018 | ABS_GROWTH_PTRAP_B103_lav_n_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.3727 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B103_lav_n | PLM-B103-NEW-FIT-0008 | ANIM_ABS_Installation_Highlight | 0.0888 | 0.1979 | 0.1772
PLM-B103-NEW-SEG-0019 | ABS_GROWTH_PTRAP_B103_lav_n_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.4167 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B103_lav_n | PLM-B103-NEW-FIT-0008 | ANIM_ABS_Installation_Highlight | 0.1191 | 0.1979 | 0.1586
PLM-B103-NEW-SEG-0020 | ABS_GROWTH_PTRAP_B103_lav_s_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.5 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B103_lav_s | PLM-B103-NEW-FIT-0009 | ANIM_ABS_Installation_Highlight | 0.1979 | 0.1979 | 0.0005
PLM-B103-NEW-SEG-0021 | ABS_GROWTH_PTRAP_B103_lav_s_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.3727 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B103_lav_s | PLM-B103-NEW-FIT-0009 | ANIM_ABS_Installation_Highlight | 0.0888 | 0.1979 | 0.1772
PLM-B103-NEW-SEG-0022 | ABS_GROWTH_PTRAP_B103_lav_s_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.4167 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B103_lav_s | PLM-B103-NEW-FIT-0009 | ANIM_ABS_Installation_Highlight | 0.1191 | 0.1979 | 0.1586
PLM-B103-NEW-SEG-0023 | ABS_GROWTH_TracerWire_B103_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | TracerWire_B103 | PLM-B103-NEW-TRW-0001 | ANIM_ABS_Installation_Highlight | 0.01 | 0.0017 | 0.01
PLM-B103-NEW-TRW-0001 | TracerWire_B103 | CURVE | New_ABS_UnderSlab_4in_6in | New_ABS_UnderSlab_4in_6in | B103 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | TRACER_WIRE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | 4D brief: insulated copper tracer wire at new underground nonmetallic pipe | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_Copper_Tracer | 2 | 3.5 | 2.0312
PLM-B103-REI-FIX-0001 | B103_BT_ALT2_NEW | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B103 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | BT-1 Kohler Villager 60in cast-iron tub representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 1 | 1 | 1
PLM-B103-REI-FIX-0002 | B103_BT_EXISTING | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B103 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | BT-1 Kohler Villager 60in cast-iron tub representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B103_MAT_Porcelain_White | 1 | 1 | 1
PLM-B103-REI-FIX-0003 | B103_KS1 | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B103 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | KS-1 Grohe 31815SD0 representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B103_MAT_Stainless | 1 | 1 | 1
PLM-B103-REI-FIX-0004 | B103_LAV_N | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B103 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | LAV-1 Kohler Caxton representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B103_MAT_Porcelain_White | 2 | 2 | 2
PLM-B103-REI-FIX-0005 | B103_LAV_S | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B103 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | LAV-1 Kohler Caxton representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B103_MAT_Porcelain_White | 2 | 2 | 2
PLM-B103-REI-FIX-0006 | B103_SH_N_GLASS | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B103 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Frameless shower enclosure | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B103_MAT_Glass | 1 | 1 | 1
PLM-B103-REI-FIX-0007 | B103_SH_N_PAN | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B103 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | SH-1 alcove shower | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B103_MAT_Porcelain_White | 1 | 1 | 1
PLM-B103-REI-FIX-0008 | B103_WB1 | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B103 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | LG WM4000HWA representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B103_MAT_Appliance_White | 1 | 1 | 1
PLM-B103-REI-FIX-0009 | B103_WC1_N_BOWL | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B103 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WC-1 Kohler Veil representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B103_MAT_Porcelain_White | 2 | 2 | 2
PLM-B103-REI-FIX-0010 | B103_WC1_S_BOWL | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B103 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WC-1 Kohler Veil representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B103_MAT_Porcelain_White | 2 | 2 | 2
PLM-B103-REI-FIX-0011 | B103_WC_ALT1_Floor_N_BOWL | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B103 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WC-1 Kohler Veil representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 2 | 2 | 2
PLM-B103-REI-FIX-0012 | B103_WC_ALT1_Floor_N_TANK | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B103 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Alternate #1 floor-mounted WC | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 1 | 1 | 1
PLM-B103-REI-FIX-0013 | B103_WC_ALT1_Floor_S_BOWL | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B103 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WC-1 Kohler Veil representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 2 | 2 | 2
PLM-B103-REI-FIX-0014 | B103_WC_ALT1_Floor_S_TANK | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B103 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Alternate #1 floor-mounted WC | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 1 | 1 | 1
PLM-B103-REI-FIX-0015 | B103_WH1 | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B103 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Rheem 40-gal electric WH | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_WH_Gray | 1.6875 | 1.6875 | 4.02
PLM-B103-TST-TST-0001 | HYDRO_NEW_ABS_B103_2in_lav_n | CURVE | ANIM_Water_Test | ANIM_Water_Test | B103 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAVATORY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 2in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 6.5059 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED | NEW_ABS_B103_2in_lav_n | PLM-B103-NEW-PIPE-0001 | ANIM_Hydrostatic_Pulse | 7.2329 | 5.8633 | 2.1355
PLM-B103-TST-TST-0002 | HYDRO_NEW_ABS_B103_2in_lav_s | CURVE | ANIM_Water_Test | ANIM_Water_Test | B103 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAVATORY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 2in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 9.131 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED | NEW_ABS_B103_2in_lav_s | PLM-B103-NEW-PIPE-0002 | ANIM_Hydrostatic_Pulse | 10.8133 | 4.38 | 2.1902
PLM-B103-TST-TST-0003 | HYDRO_NEW_ABS_B103_3in_bath_n | CURVE | ANIM_Water_Test | ANIM_Water_Test | B103 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | BATH_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 5.7986 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED | NEW_ABS_B103_3in_bath_n | PLM-B103-NEW-PIPE-0003 | ANIM_Hydrostatic_Pulse | 7.7838 | 2.3967 | 2.1208
PLM-B103-TST-TST-0004 | HYDRO_NEW_ABS_B103_3in_bath_s | CURVE | ANIM_Water_Test | ANIM_Water_Test | B103 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | BATH_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 7.7541 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED | NEW_ABS_B103_3in_bath_s | PLM-B103-NEW-PIPE-0004 | ANIM_Hydrostatic_Pulse | 9.7117 | 2.7933 | 2.1615
PLM-B103-TST-TST-0005 | HYDRO_NEW_ABS_B103_3in_laundry | CURVE | ANIM_Water_Test | ANIM_Water_Test | B103 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAUNDRY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 0.337 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED | NEW_ABS_B103_3in_laundry | PLM-B103-NEW-PIPE-0005 | ANIM_Hydrostatic_Pulse | 2.2754 | 2.1942 | 2.007
PLM-B103-TST-TST-0006 | HYDRO_NEW_ABS_B103_4in_MAIN | CURVE | ANIM_Water_Test | ANIM_Water_Test | B103 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | MAIN | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3.1/P3.2 traced new Sch40 ABS | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 31.5901 | FT | CURVE_CENTERLINE | 4 | 0.25 | DOCUMENTED | NEW_ABS_B103_4in_MAIN | PLM-B103-NEW-PIPE-0006 | ANIM_Hydrostatic_Pulse | 11.915 | 29.5258 | 2.658
PLM-B103-TST-TST-0007 | HYDRO_NEW_ABS_B103_4in_RAISED_FLOOR | CURVE | ANIM_Water_Test | ANIM_Water_Test | B103 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P3.2 / 4D brief: B103 4in sanitary in raised floor assembly | FIELD_VERIFY_REQUIRED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 30.6833 | FT | CURVE_CENTERLINE | 4 |  | NOT_DOCUMENTED | NEW_ABS_B103_4in_RAISED_FLOOR | PLM-B103-NEW-PIPE-0007 | ANIM_Hydrostatic_Pulse | 18.5617 | 14.0383 | 4.0833
PLM-B103-TST-TST-0008 | HYDRO_NEW_ABS_B103_6in_LATERAL_18IN_LIMIT | CURVE | ANIM_Water_Test | ANIM_Water_Test | B103 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LATERAL | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/SOR: new 6in to 18in beyond foundation, then tie to existing lateral | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE | 6 | 0.25 | DOCUMENTED | NEW_ABS_B103_6in_LATERAL_18IN_LIMIT | PLM-B103-NEW-PIPE-0008 | ANIM_Hydrostatic_Pulse | 2 | 3.5 | 2.0312
PLM-B103-TST-TST-0009 | HYDRO_PTRAP_B103_laundry | CURVE | ANIM_Water_Test | ANIM_Water_Test | B103 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAUNDRY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NOT_DOCUMENTED | PTRAP_B103_laundry | PLM-B103-NEW-FIT-0007 | ANIM_Hydrostatic_Pulse | 2.6667 | 2 | 2.6667
PLM-B103-TST-TST-0010 | HYDRO_PTRAP_B103_lav_n | CURVE | ANIM_Water_Test | ANIM_Water_Test | B103 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAVATORY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NOT_DOCUMENTED | PTRAP_B103_lav_n | PLM-B103-NEW-FIT-0008 | ANIM_Hydrostatic_Pulse | 2.6667 | 2 | 2.6667
PLM-B103-TST-TST-0011 | HYDRO_PTRAP_B103_lav_s | CURVE | ANIM_Water_Test | ANIM_Water_Test | B103 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAVATORY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NOT_DOCUMENTED | PTRAP_B103_lav_s | PLM-B103-NEW-FIT-0009 | ANIM_Hydrostatic_Pulse | 2.6667 | 2 | 2.6667
PLM-B103-TST-TST-0012 | HYDRO_TracerWire_B103 | CURVE | ANIM_Water_Test | ANIM_Water_Test | B103 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | 4D brief: insulated copper tracer wire at new underground nonmetallic pipe | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE |  |  | NOT_DOCUMENTED | TracerWire_B103 | PLM-B103-NEW-TRW-0001 | ANIM_Hydrostatic_Pulse | 2 | 3.5 | 2.0312
PLM-B104-DEM-PIPE-0001 | EX_CI_B104_BR2_lav_n | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B104 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | LAVATORY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing lavatory/fixture branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 5.1846 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 3.6033 | 3.9953 | 0.3059
PLM-B104-DEM-PIPE-0002 | EX_CI_B104_BR2_lav_s | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B104 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | LAVATORY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing lavatory/fixture branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 3.6141 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 3.2395 | 1.9571 | 0.2732
PLM-B104-DEM-PIPE-0003 | EX_CI_B104_BR3_bath_n | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B104 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | BATH_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 3.4793 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 3.4891 | 0.6864 | 0.3641
PLM-B104-DEM-PIPE-0004 | EX_CI_B104_BR3_bath_s | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B104 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | BATH_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 2.2787 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 2.2753 | 0.8765 | 0.3391
PLM-B104-DEM-PIPE-0005 | EX_CI_B104_BR3_laundry | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B104 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | LAUNDRY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing branch route from P1.02/P3; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 10.1314 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 10.1352 | 0.2917 | 0.5026
PLM-B104-DEM-PIPE-0006 | EX_CI_B104_LAT6_REPLACE | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B104 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | LATERAL | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Existing 6in segment within 18in replacement limit; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE | 6 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 0.5521 | 1.5115 | 0.5832
PLM-B104-DEM-PIPE-0007 | EX_CI_B104_MAIN4 | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | B104 | L1 | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | PIPE_ROUTE | MAIN | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Like-for-like existing route representation; field verify | FIELD_VERIFY_REQUIRED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 43.5132 | FT | CURVE_CENTERLINE | 4 | 0.25 | DOCUMENTED |  |  | ANIM_ExistingCastIron_MAT_Existing_CastIron_Rust | 10.975 | 39.5004 | 1.2812
PLM-B104-EXG-PIPE-0001 | B104_Prior_4in_ABS_REMAIN | CURVE | Ex_Unit101_&_104_Prior_ABS_REMAIN | Ex_Unit101_&_104_Prior_ABS_REMAIN | B104 | L1 | PLUMBING | DWV | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | PIPE_ROUTE | MAIN | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P3.1/P3.2: prior Schedule 40 ABS repair to remain | DOCUMENT_DERIVED | 22-000 | PROVISIONAL | 300 | TRUE | LENGTH | 3.9035 | FT | CURVE_CENTERLINE | 4 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Prior_Remain | 3.8733 | 1.334 | 0.4562
PLM-B104-NEW-CO-0001 | B104_BaseOfStack_Cleanout_1 | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Base-of-stack cleanout | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Nickel_Bronze | 0.435 | 0.435 | 0.435
PLM-B104-NEW-CO-0002 | B104_BaseOfStack_Cleanout_2 | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Base-of-stack cleanout | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Nickel_Bronze | 0.3383 | 0.3383 | 0.3383
PLM-B104-NEW-CO-0003 | B104_BaseOfStack_Cleanout_3 | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Base-of-stack cleanout | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Nickel_Bronze | 0.3383 | 0.3383 | 0.3383
PLM-B104-NEW-CO-0004 | B104_Cleanout_12x12_Pad | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | 12x12 concrete cleanout pad | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Concrete_Pourback_KIM | 1 | 1 | 1
PLM-B104-NEW-CO-0005 | B104_Zurn_Z1450_6in_Cleanout | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | CLEANOUT |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | 4D brief / SOR: exterior 6in cleanout at replacement limit | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 6 |  | NA |  |  | MAT_ABS_Schedule40_Black | 2 | 2 | 5.7812
PLM-B104-NEW-FIT-0001 | B104_6in_TransitionCoupling | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02: 4in waste to 6in waste transition; match existing I.E. | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 6 |  | NA |  |  | MAT_ABS_Schedule40_Black | 0.6846 | 0.6846 | 0.8333
PLM-B104-NEW-FIT-0002 | B104_StackTieIn_1_4in | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01/P5.1 stack tie-in vertical exposure | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 4 |  | NA |  |  | MAT_ABS_Schedule40_Black | 2 | 2 | 6.3333
PLM-B104-NEW-FIT-0003 | B104_StackTieIn_2_3in | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01/P5.1 stack tie-in vertical exposure | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 3 |  | NA |  |  | MAT_ABS_Schedule40_Black | 2 | 2 | 6
PLM-B104-NEW-FIT-0004 | B104_StackTieIn_3_3in | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01/P5.1 stack tie-in vertical exposure | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT | 3 |  | NA |  |  | MAT_ABS_Schedule40_Black | 2 | 2 | 6
PLM-B104-NEW-FIT-0005 | B104_TestPlug | MESH | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WP2 test plug visualization | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_TestPlug | 0.3375 | 0.3375 | 0.1667
PLM-B104-NEW-FIT-0006 | B104_WP2_WaterTest | CURVE | New_Stack_TieIns_&_Cleanouts | New_Stack_TieIns_&_Cleanouts | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Phase 5 water-test visualization | DOCUMENT_DERIVED | 22-110 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Water_Test_Blue | 12.6492 | 41.37 | 2.9063
PLM-B104-NEW-FIT-0007 | PTRAP_B104_laundry | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_ABS_Schedule40_Black | 2.6667 | 2 | 2.6667
PLM-B104-NEW-FIT-0008 | PTRAP_B104_lav_n | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_ABS_Schedule40_Black | 2.6667 | 2 | 2.6667
PLM-B104-NEW-FIT-0009 | PTRAP_B104_lav_s | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | FITTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_ABS_Schedule40_Black | 2.6667 | 2 | 2.6667
PLM-B104-NEW-PIPE-0001 | NEW_ABS_B104_2in_lav_n | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | LAVATORY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 2in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 5.1846 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 5.4558 | 5.8633 | 2.108
PLM-B104-NEW-PIPE-0002 | NEW_ABS_B104_2in_lav_s | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | LAVATORY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 2in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 3.6141 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 5.1417 | 3.785 | 2.0753
PLM-B104-NEW-PIPE-0003 | NEW_ABS_B104_3in_bath_n | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | BATH_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 3.4793 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 5.4558 | 2.3967 | 2.0725
PLM-B104-NEW-PIPE-0004 | NEW_ABS_B104_3in_bath_s | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | BATH_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 2.2787 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 4.1992 | 2.595 | 2.0475
PLM-B104-NEW-PIPE-0005 | NEW_ABS_B104_3in_laundry | CURVE | New_ABS_Branches_&_Traps | New_ABS_Branches_&_Traps | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | LAUNDRY_BRANCH | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 10.1314 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 12.1292 | 2 | 2.211
PLM-B104-NEW-PIPE-0006 | NEW_ABS_B104_4in_MAIN | CURVE | New_ABS_UnderSlab_4in_6in | New_ABS_UnderSlab_4in_6in | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | MAIN | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/P3.1/P3.2 traced new Sch40 ABS | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 43.5132 | FT | CURVE_CENTERLINE | 4 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 12.6492 | 41.37 | 2.9063
PLM-B104-NEW-PIPE-0007 | NEW_ABS_B104_6in_LATERAL_18IN_LIMIT | CURVE | New_ABS_UnderSlab_4in_6in | New_ABS_UnderSlab_4in_6in | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | PIPE_ROUTE | LATERAL | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.02/SOR: new 6in to 18in beyond foundation, then tie to existing lateral | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE | 6 | 0.25 | DOCUMENTED |  |  | MAT_ABS_Schedule40_Black | 2 | 3.5 | 2.0312
PLM-B104-NEW-SEG-0001 | ABS_GROWTH_NEW_ABS_B104_2in_lav_n_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 5.1846 | FT | GROWTH_LENGTH | 2 |  | NOT_DOCUMENTED | NEW_ABS_B104_2in_lav_n | PLM-B104-NEW-PIPE-0001 | ANIM_ABS_Installation_Highlight | 0.1537 | 0.1389 | 0.198
PLM-B104-NEW-SEG-0002 | ABS_GROWTH_NEW_ABS_B104_2in_lav_s_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 3.6141 | FT | GROWTH_LENGTH | 2 |  | NOT_DOCUMENTED | NEW_ABS_B104_2in_lav_s | PLM-B104-NEW-PIPE-0002 | ANIM_ABS_Installation_Highlight | 0.1045 | 0.1759 | 0.1979
PLM-B104-NEW-SEG-0003 | ABS_GROWTH_NEW_ABS_B104_3in_bath_n_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | BATH_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 3.4793 | FT | GROWTH_LENGTH | 3 |  | NOT_DOCUMENTED | NEW_ABS_B104_3in_bath_n | PLM-B104-NEW-PIPE-0003 | ANIM_ABS_Installation_Highlight | 0.0428 | 0.2909 | 0.2917
PLM-B104-NEW-SEG-0004 | ABS_GROWTH_NEW_ABS_B104_3in_bath_s_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | BATH_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 2.2787 | FT | GROWTH_LENGTH | 3 |  | NOT_DOCUMENTED | NEW_ABS_B104_3in_bath_s | PLM-B104-NEW-PIPE-0004 | ANIM_ABS_Installation_Highlight | 0.0842 | 0.2837 | 0.2917
PLM-B104-NEW-SEG-0005 | ABS_GROWTH_NEW_ABS_B104_3in_laundry_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 10.1314 | FT | GROWTH_LENGTH | 3 |  | NOT_DOCUMENTED | NEW_ABS_B104_3in_laundry | PLM-B104-NEW-PIPE-0005 | ANIM_ABS_Installation_Highlight | 0.0162 | 0.2917 | 0.2918
PLM-B104-NEW-SEG-0006 | ABS_GROWTH_NEW_ABS_B104_4in_MAIN_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 15.7872 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B104_4in_MAIN | PLM-B104-NEW-PIPE-0006 | ANIM_ABS_Installation_Highlight | 0.2927 | 0.2704 | 0.3752
PLM-B104-NEW-SEG-0007 | ABS_GROWTH_NEW_ABS_B104_4in_MAIN_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 10.4806 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B104_4in_MAIN | PLM-B104-NEW-PIPE-0006 | ANIM_ABS_Installation_Highlight | 0.375 | 0.0183 | 0.3751
PLM-B104-NEW-SEG-0008 | ABS_GROWTH_NEW_ABS_B104_4in_MAIN_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 4.9594 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B104_4in_MAIN | PLM-B104-NEW-PIPE-0006 | ANIM_ABS_Installation_Highlight | 0.375 | 0.0128 | 0.375
PLM-B104-NEW-SEG-0009 | ABS_GROWTH_NEW_ABS_B104_4in_MAIN_003 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 7.4716 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B104_4in_MAIN | PLM-B104-NEW-PIPE-0006 | ANIM_ABS_Installation_Highlight | 0.375 | 0.0153 | 0.3751
PLM-B104-NEW-SEG-0010 | ABS_GROWTH_NEW_ABS_B104_4in_MAIN_004 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | MAIN | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 4.8144 | FT | GROWTH_LENGTH | 4 |  | NOT_DOCUMENTED | NEW_ABS_B104_4in_MAIN | PLM-B104-NEW-PIPE-0006 | ANIM_ABS_Installation_Highlight | 0.375 | 0.0126 | 0.375
PLM-B104-NEW-SEG-0011 | ABS_GROWTH_NEW_ABS_B104_6in_LATERAL_18IN_LIMIT_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LATERAL | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | GROWTH_LENGTH | 6 |  | NOT_DOCUMENTED | NEW_ABS_B104_6in_LATERAL_18IN_LIMIT | PLM-B104-NEW-PIPE-0007 | ANIM_ABS_Installation_Highlight | 0.5521 | 0.013 | 0.552
PLM-B104-NEW-SEG-0012 | ABS_GROWTH_PTRAP_B104_laundry_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.5 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B104_laundry | PLM-B104-NEW-FIT-0007 | ANIM_ABS_Installation_Highlight | 0.2917 | 0.2917 | 0.0005
PLM-B104-NEW-SEG-0013 | ABS_GROWTH_PTRAP_B104_laundry_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.3727 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B104_laundry | PLM-B104-NEW-FIT-0007 | ANIM_ABS_Installation_Highlight | 0.1308 | 0.2917 | 0.261
PLM-B104-NEW-SEG-0014 | ABS_GROWTH_PTRAP_B104_laundry_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAUNDRY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.4167 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B104_laundry | PLM-B104-NEW-FIT-0007 | ANIM_ABS_Installation_Highlight | 0.1753 | 0.2917 | 0.2336
PLM-B104-NEW-SEG-0015 | ABS_GROWTH_PTRAP_B104_lav_n_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.5 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B104_lav_n | PLM-B104-NEW-FIT-0008 | ANIM_ABS_Installation_Highlight | 0.1979 | 0.1979 | 0.0005
PLM-B104-NEW-SEG-0016 | ABS_GROWTH_PTRAP_B104_lav_n_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.3727 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B104_lav_n | PLM-B104-NEW-FIT-0008 | ANIM_ABS_Installation_Highlight | 0.0888 | 0.1979 | 0.1772
PLM-B104-NEW-SEG-0017 | ABS_GROWTH_PTRAP_B104_lav_n_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.4167 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B104_lav_n | PLM-B104-NEW-FIT-0008 | ANIM_ABS_Installation_Highlight | 0.1191 | 0.1979 | 0.1586
PLM-B104-NEW-SEG-0018 | ABS_GROWTH_PTRAP_B104_lav_s_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.5 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B104_lav_s | PLM-B104-NEW-FIT-0009 | ANIM_ABS_Installation_Highlight | 0.1979 | 0.1979 | 0.0005
PLM-B104-NEW-SEG-0019 | ABS_GROWTH_PTRAP_B104_lav_s_001 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.3727 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B104_lav_s | PLM-B104-NEW-FIT-0009 | ANIM_ABS_Installation_Highlight | 0.0888 | 0.1979 | 0.1772
PLM-B104-NEW-SEG-0020 | ABS_GROWTH_PTRAP_B104_lav_s_002 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | LAVATORY_BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 0.4167 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | PTRAP_B104_lav_s | PLM-B104-NEW-FIT-0009 | ANIM_ABS_Installation_Highlight | 0.1191 | 0.1979 | 0.1586
PLM-B104-NEW-SEG-0021 | ABS_GROWTH_TracerWire_B104_000 | MESH | ANIM_ABS_Extrusion | ANIM_ABS_Extrusion | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | INSTALLATION_SEGMENT | BRANCH | DERIVED_ANIMATION | INSTALLATION_GROWTH_SEGMENT | Derived from animated coordinated route geometry. | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | GROWTH_LENGTH |  |  | NOT_DOCUMENTED | TracerWire_B104 | PLM-B104-NEW-TRW-0001 | ANIM_ABS_Installation_Highlight | 0.01 | 0.0017 | 0.01
PLM-B104-NEW-TRW-0001 | TracerWire_B104 | CURVE | New_ABS_UnderSlab_4in_6in | New_ABS_UnderSlab_4in_6in | B104 | L1 | PLUMBING | DWV | NEW | 04 | New ABS Installation | 253 | 336 | TRACER_WIRE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | 4D brief: insulated copper tracer wire at new underground nonmetallic pipe | DOCUMENT_DERIVED | 22-100 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE |  |  | NA |  |  | MAT_Copper_Tracer | 2 | 3.5 | 2.0312
PLM-B104-REI-FIX-0001 | B104_BT_ALT2_NEW | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B104 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | BT-1 Kohler Villager 60in cast-iron tub representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 1 | 1 | 1
PLM-B104-REI-FIX-0002 | B104_BT_EXISTING | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B104 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | BT-1 Kohler Villager 60in cast-iron tub representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B104_MAT_Porcelain_White | 1 | 1 | 1
PLM-B104-REI-FIX-0003 | B104_KS1 | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B104 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | KS-1 Grohe 31815SD0 representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B104_MAT_Stainless | 1 | 1 | 1
PLM-B104-REI-FIX-0004 | B104_LAV_N | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B104 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | LAV-1 Kohler Caxton representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B104_MAT_Porcelain_White | 2 | 2 | 2
PLM-B104-REI-FIX-0005 | B104_LAV_S | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B104 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | LAV-1 Kohler Caxton representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B104_MAT_Porcelain_White | 2 | 2 | 2
PLM-B104-REI-FIX-0006 | B104_SH_N_GLASS | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B104 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Frameless shower enclosure | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B104_MAT_Glass | 1 | 1 | 1
PLM-B104-REI-FIX-0007 | B104_SH_N_PAN | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B104 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | SH-1 alcove shower | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B104_MAT_Porcelain_White | 1 | 1 | 1
PLM-B104-REI-FIX-0008 | B104_WB1 | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B104 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | LG WM4000HWA representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B104_MAT_Appliance_White | 1 | 1 | 1
PLM-B104-REI-FIX-0009 | B104_WC1_N_BOWL | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B104 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WC-1 Kohler Veil representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B104_MAT_Porcelain_White | 2 | 2 | 2
PLM-B104-REI-FIX-0010 | B104_WC1_S_BOWL | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B104 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WC-1 Kohler Veil representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | ANIM_Fixture_B104_MAT_Porcelain_White | 2 | 2 | 2
PLM-B104-REI-FIX-0011 | B104_WC_ALT1_Floor_N_BOWL | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B104 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WC-1 Kohler Veil representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 2 | 2 | 2
PLM-B104-REI-FIX-0012 | B104_WC_ALT1_Floor_N_TANK | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B104 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Alternate #1 floor-mounted WC | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 1 | 1 | 1
PLM-B104-REI-FIX-0013 | B104_WC_ALT1_Floor_S_BOWL | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B104 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | WC-1 Kohler Veil representation | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 2 | 2 | 2
PLM-B104-REI-FIX-0014 | B104_WC_ALT1_Floor_S_TANK | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B104 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Alternate #1 floor-mounted WC | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Porcelain_White | 1 | 1 | 1
PLM-B104-REI-FIX-0015 | B104_WH1 | MESH | Plumbing_Fixtures | Plumbing_Fixtures | B104 | L1 | PLUMBING | FIXTURES | REINSTALLED | 08 | Fixture Reinstall + As-Built | 589 | 672 | FIXTURE |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Rheem 40-gal electric WH | DOCUMENT_DERIVED | 22-420 | PROVISIONAL | 300 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_WH_Gray | 1.6875 | 1.6875 | 4.02
PLM-B104-TST-TST-0001 | HYDRO_NEW_ABS_B104_2in_lav_n | CURVE | ANIM_Water_Test | ANIM_Water_Test | B104 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAVATORY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 2in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 5.1846 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED | NEW_ABS_B104_2in_lav_n | PLM-B104-NEW-PIPE-0001 | ANIM_Hydrostatic_Pulse | 5.4558 | 5.8633 | 2.108
PLM-B104-TST-TST-0002 | HYDRO_NEW_ABS_B104_2in_lav_s | CURVE | ANIM_Water_Test | ANIM_Water_Test | B104 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAVATORY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 2in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 3.6141 | FT | CURVE_CENTERLINE | 2 | 0.25 | DOCUMENTED | NEW_ABS_B104_2in_lav_s | PLM-B104-NEW-PIPE-0002 | ANIM_Hydrostatic_Pulse | 5.1417 | 3.785 | 2.0753
PLM-B104-TST-TST-0003 | HYDRO_NEW_ABS_B104_3in_bath_n | CURVE | ANIM_Water_Test | ANIM_Water_Test | B104 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | BATH_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 3.4793 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED | NEW_ABS_B104_3in_bath_n | PLM-B104-NEW-PIPE-0003 | ANIM_Hydrostatic_Pulse | 5.4558 | 2.3967 | 2.0725
PLM-B104-TST-TST-0004 | HYDRO_NEW_ABS_B104_3in_bath_s | CURVE | ANIM_Water_Test | ANIM_Water_Test | B104 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | BATH_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 2.2787 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED | NEW_ABS_B104_3in_bath_s | PLM-B104-NEW-PIPE-0004 | ANIM_Hydrostatic_Pulse | 4.1992 | 2.595 | 2.0475
PLM-B104-TST-TST-0005 | HYDRO_NEW_ABS_B104_3in_laundry | CURVE | ANIM_Water_Test | ANIM_Water_Test | B104 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAUNDRY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3 traced 3in branch | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 10.1314 | FT | CURVE_CENTERLINE | 3 | 0.25 | DOCUMENTED | NEW_ABS_B104_3in_laundry | PLM-B104-NEW-PIPE-0005 | ANIM_Hydrostatic_Pulse | 12.1292 | 2 | 2.211
PLM-B104-TST-TST-0006 | HYDRO_NEW_ABS_B104_4in_MAIN | CURVE | ANIM_Water_Test | ANIM_Water_Test | B104 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | MAIN | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/P3.1/P3.2 traced new Sch40 ABS | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 43.5132 | FT | CURVE_CENTERLINE | 4 | 0.25 | DOCUMENTED | NEW_ABS_B104_4in_MAIN | PLM-B104-NEW-PIPE-0006 | ANIM_Hydrostatic_Pulse | 12.6492 | 41.37 | 2.9063
PLM-B104-TST-TST-0007 | HYDRO_NEW_ABS_B104_6in_LATERAL_18IN_LIMIT | CURVE | ANIM_Water_Test | ANIM_Water_Test | B104 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LATERAL | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | P1.02/SOR: new 6in to 18in beyond foundation, then tie to existing lateral | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE | 6 | 0.25 | DOCUMENTED | NEW_ABS_B104_6in_LATERAL_18IN_LIMIT | PLM-B104-NEW-PIPE-0007 | ANIM_Hydrostatic_Pulse | 2 | 3.5 | 2.0312
PLM-B104-TST-TST-0008 | HYDRO_PTRAP_B104_laundry | CURVE | ANIM_Water_Test | ANIM_Water_Test | B104 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAUNDRY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NOT_DOCUMENTED | PTRAP_B104_laundry | PLM-B104-NEW-FIT-0007 | ANIM_Hydrostatic_Pulse | 2.6667 | 2 | 2.6667
PLM-B104-TST-TST-0009 | HYDRO_PTRAP_B104_lav_n | CURVE | ANIM_Water_Test | ANIM_Water_Test | B104 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAVATORY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NOT_DOCUMENTED | PTRAP_B104_lav_n | PLM-B104-NEW-FIT-0008 | ANIM_Hydrostatic_Pulse | 2.6667 | 2 | 2.6667
PLM-B104-TST-TST-0010 | HYDRO_PTRAP_B104_lav_s | CURVE | ANIM_Water_Test | ANIM_Water_Test | B104 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | LAVATORY_BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | First-floor p-trap replacement scope | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.2893 | FT | CURVE_CENTERLINE |  |  | NOT_DOCUMENTED | PTRAP_B104_lav_s | PLM-B104-NEW-FIT-0009 | ANIM_Hydrostatic_Pulse | 2.6667 | 2 | 2.6667
PLM-B104-TST-TST-0011 | HYDRO_TracerWire_B104 | CURVE | ANIM_Water_Test | ANIM_Water_Test | B104 | L1 | PLUMBING | DWV | TEST | 05 | Water Test | 337 | 420 | HYDRO_TEST_ROUTE | BRANCH | DERIVED_ANIMATION | HYDRO_TEST_DUPLICATE | 4D brief: insulated copper tracer wire at new underground nonmetallic pipe | DOCUMENT_DERIVED | 22-900 | PROVISIONAL | 300 | TRUE | LENGTH | 1.5003 | FT | CURVE_CENTERLINE |  |  | NOT_DOCUMENTED | TracerWire_B104 | PLM-B104-NEW-TRW-0001 | ANIM_Hydrostatic_Pulse | 2 | 3.5 | 2.0312
PLM-SITE-DEM-INS-0001 | Borescope_Interior_Locator | MESH | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | SITE | SITE | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | INSPECTION_PATH |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | RF locator marker | DOCUMENT_DERIVED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 0.3333 | FT | BBOX_APPROX |  |  | NA |  |  | ANIM_ExistingCastIron_MAT_Borescope_Locator | 0.3333 | 0.3333 | 0.3333
PLM-SITE-DEM-INS-0002 | Borescope_Interior_WestToEast_Path | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | SITE | SITE | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | INSPECTION_PATH |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | SOR investigation: camera inserted from unit toilet west-to-east | DOCUMENT_DERIVED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 39.538 | FT | CURVE_CENTERLINE |  |  | NA |  |  | ANIM_ExistingCastIron_MAT_Borescope_Locator | 2.2076 | 37.2471 | 1.0032
PLM-SITE-DEM-INS-0003 | Borescope_SideSewer_Locator | MESH | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | SITE | SITE | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | INSPECTION_PATH |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | RF locator marker | DOCUMENT_DERIVED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 0.3333 | FT | BBOX_APPROX |  |  | NA |  |  | ANIM_ExistingCastIron_MAT_Borescope_Locator | 0.3333 | 0.3333 | 0.3333
PLM-SITE-DEM-INS-0004 | Borescope_SideSewer_SouthToNorth_Path | CURVE | Ex_Cast_Iron_Pipes_DEMO | Ex_Cast_Iron_Pipes_DEMO | SITE | SITE | PLUMBING | DWV | DEMOLITION | 03 | Demolition + Excavation | 169 | 252 | INSPECTION_PATH |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | SOR investigation: second camera from Building C cleanout south-to-north | DOCUMENT_DERIVED | 22-050 | PROVISIONAL | 300 | TRUE | LENGTH | 190.4583 | FT | CURVE_CENTERLINE |  |  | NA |  |  | ANIM_ExistingCastIron_MAT_Borescope_Locator | 190.4583 | 0.0133 | 0.0133
STR-B101-EXG-SLB-0001 | B101_West_Bay_Slab | MESH | Concrete_Slab_Unmodified | Concrete_Slab_Unmodified | B101 | L1 | STRUCTURE | SLAB_ON_GRADE | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | SLAB_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1/P2 plan bay-window projection context | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 137.75 | SF | BBOX_APPROX |  |  | NA |  |  | ANIM_GhostSlab_MAT_Concrete_Shell_Xray | 27.55 | 5 | 0.4583
STR-B102-EXG-SLB-0001 | B102_West_Bay_Slab | MESH | Concrete_Slab_Unmodified | Concrete_Slab_Unmodified | B102 | L1 | STRUCTURE | SLAB_ON_GRADE | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | SLAB_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1/P2 plan bay-window projection context | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 123.25 | SF | BBOX_APPROX |  |  | NA |  |  | ANIM_GhostSlab_MAT_Concrete_Shell_Xray | 24.65 | 5 | 0.4583
STR-B103-EXG-SLB-0001 | B103_West_Bay_Slab | MESH | Concrete_Slab_Unmodified | Concrete_Slab_Unmodified | B103 | L1 | STRUCTURE | SLAB_ON_GRADE | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | SLAB_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1/P2 plan bay-window projection context | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 126.125 | SF | BBOX_APPROX |  |  | NA |  |  | ANIM_GhostSlab_MAT_Concrete_Shell_Xray | 25.225 | 5 | 0.4583
STR-B104-EXG-SLB-0001 | B104_West_Bay_Slab | MESH | Concrete_Slab_Unmodified | Concrete_Slab_Unmodified | B104 | L1 | STRUCTURE | SLAB_ON_GRADE | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | SLAB_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1/P2 plan bay-window projection context | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 94.25 | SF | BBOX_APPROX |  |  | NA |  |  | ANIM_GhostSlab_MAT_Concrete_Shell_Xray | 18.85 | 5 | 0.4583
STR-SITE-EXG-FTG-0001 | Footing_East | MESH | Foundation_Footings | Foundation_Footings | SITE | SITE | STRUCTURE | FOUNDATION | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FOOTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Classified from collection Foundation_Footings and object name. | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Foundation_Concrete | 160.4583 | 2 | 1
STR-SITE-EXG-FTG-0002 | Footing_North | MESH | Foundation_Footings | Foundation_Footings | SITE | SITE | STRUCTURE | FOUNDATION | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FOOTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Classified from collection Foundation_Footings and object name. | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Foundation_Concrete | 2 | 66.3333 | 1
STR-SITE-EXG-FTG-0003 | Footing_South | MESH | Foundation_Footings | Foundation_Footings | SITE | SITE | STRUCTURE | FOUNDATION | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FOOTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Classified from collection Foundation_Footings and object name. | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Foundation_Concrete | 2 | 66.3333 | 1
STR-SITE-EXG-FTG-0004 | Footing_West | MESH | Foundation_Footings | Foundation_Footings | SITE | SITE | STRUCTURE | FOUNDATION | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | FOOTING |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Classified from collection Foundation_Footings and object name. | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | COUNT | 1 | EA | COUNT |  |  | NA |  |  | MAT_Foundation_Concrete | 160.4583 | 2 | 1
STR-SITE-EXG-SLB-0001 | BuildingB_SOG_5p5in | MESH | Concrete_Slab_Unmodified | Concrete_Slab_Unmodified | SITE | SITE | STRUCTURE | SLAB_ON_GRADE | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | SLAB_AREA |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1.01/P5.1: existing 5–6 in slab | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 10643.7362 | SF | BBOX_APPROX | 5 |  | NA |  |  | ANIM_GhostSlab_MAT_Concrete_Shell_Xray | 160.4583 | 66.3333 | 0.4583
STR-SITE-EXG-WAL-0001 | Core_N_CrossWall | MESH | Precast_Concrete_Walls | Precast_Concrete_Walls | SITE | SITE | STRUCTURE | FOUNDATION_WALL | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | WALL |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | record/permit plan core | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 68 | SF | BBOX_APPROX |  |  | NA |  |  | ANIM_GhostWalls_MAT_Precast_Xray | 8 | 0.5417 | 8.5
STR-SITE-EXG-WAL-0002 | Core_N_EastWall | MESH | Precast_Concrete_Walls | Precast_Concrete_Walls | SITE | SITE | STRUCTURE | FOUNDATION_WALL | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | WALL |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | record/permit plan core | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 187 | SF | BBOX_APPROX |  |  | NA |  |  | ANIM_GhostWalls_MAT_Precast_Xray | 0.5417 | 22 | 8.5
STR-SITE-EXG-WAL-0003 | Core_N_WestWall | MESH | Precast_Concrete_Walls | Precast_Concrete_Walls | SITE | SITE | STRUCTURE | FOUNDATION_WALL | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | WALL |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | record/permit plan core | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 187 | SF | BBOX_APPROX |  |  | NA |  |  | ANIM_GhostWalls_MAT_Precast_Xray | 0.5417 | 22 | 8.5
STR-SITE-EXG-WAL-0004 | Core_S_CrossWall | MESH | Precast_Concrete_Walls | Precast_Concrete_Walls | SITE | SITE | STRUCTURE | FOUNDATION_WALL | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | WALL |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | record/permit plan core | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 68 | SF | BBOX_APPROX |  |  | NA |  |  | ANIM_GhostWalls_MAT_Precast_Xray | 8 | 0.5417 | 8.5
STR-SITE-EXG-WAL-0005 | Core_S_EastWall | MESH | Precast_Concrete_Walls | Precast_Concrete_Walls | SITE | SITE | STRUCTURE | FOUNDATION_WALL | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | WALL |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | record/permit plan core | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 187 | SF | BBOX_APPROX |  |  | NA |  |  | ANIM_GhostWalls_MAT_Precast_Xray | 0.5417 | 22 | 8.5
STR-SITE-EXG-WAL-0006 | Core_S_WestWall | MESH | Precast_Concrete_Walls | Precast_Concrete_Walls | SITE | SITE | STRUCTURE | FOUNDATION_WALL | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | WALL |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | record/permit plan core | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 187 | SF | BBOX_APPROX |  |  | NA |  |  | ANIM_GhostWalls_MAT_Precast_Xray | 0.5417 | 22 | 8.5
STR-SITE-EXG-WAL-0007 | East_Exterior_Wall | MESH | Precast_Concrete_Walls | Precast_Concrete_Walls | SITE | SITE | STRUCTURE | FOUNDATION_WALL | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | WALL |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Building B shell | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | ANIM_GhostWalls_MAT_Precast_Xray | 1 | 1 | 1
STR-SITE-EXG-WAL-0008 | North_Exterior_Wall | MESH | Precast_Concrete_Walls | Precast_Concrete_Walls | SITE | SITE | STRUCTURE | FOUNDATION_WALL | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | WALL |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Classified from collection Precast_Concrete_Walls and object name. | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | ANIM_GhostWalls_MAT_Precast_Xray | 1 | 1 | 1
STR-SITE-EXG-WAL-0009 | Precast_Demising_E | MESH | Precast_Concrete_Walls | Precast_Concrete_Walls | SITE | SITE | STRUCTURE | FOUNDATION_WALL | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | WALL |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1/P2 plan unit separation | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 563.8334 | SF | BBOX_APPROX |  |  | NA |  |  | ANIM_GhostWalls_MAT_Precast_Xray | 0.5417 | 66.3333 | 8.5
STR-SITE-EXG-WAL-0010 | Precast_Demising_H | MESH | Precast_Concrete_Walls | Precast_Concrete_Walls | SITE | SITE | STRUCTURE | FOUNDATION_WALL | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | WALL |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1/P2 plan unit separation | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 563.8334 | SF | BBOX_APPROX |  |  | NA |  |  | ANIM_GhostWalls_MAT_Precast_Xray | 0.5417 | 66.3333 | 8.5
STR-SITE-EXG-WAL-0011 | Precast_Demising_L | MESH | Precast_Concrete_Walls | Precast_Concrete_Walls | SITE | SITE | STRUCTURE | FOUNDATION_WALL | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | WALL |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | P1/P2 plan unit separation | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 563.8334 | SF | BBOX_APPROX |  |  | NA |  |  | ANIM_GhostWalls_MAT_Precast_Xray | 0.5417 | 66.3333 | 8.5
STR-SITE-EXG-WAL-0012 | South_Exterior_Wall | MESH | Precast_Concrete_Walls | Precast_Concrete_Walls | SITE | SITE | STRUCTURE | FOUNDATION_WALL | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | WALL |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Classified from collection Precast_Concrete_Walls and object name. | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | ANIM_GhostWalls_MAT_Precast_Xray | 1 | 1 | 1
STR-SITE-EXG-WAL-0013 | West_Exterior_Wall | MESH | Precast_Concrete_Walls | Precast_Concrete_Walls | SITE | SITE | STRUCTURE | FOUNDATION_WALL | EXISTING_REMAIN | 01 | Existing + Investigation | 1 | 84 | WALL |  | SOURCE_GEOMETRY | SOURCE_GEOMETRY | Classified from collection Precast_Concrete_Walls and object name. | DOCUMENT_DERIVED | 03-000 | PROVISIONAL | 200 | TRUE | AREA | 1 | SF | BBOX_APPROX |  |  | NA |  |  | ANIM_GhostWalls_MAT_Precast_Xray | 1 | 1 | 1
VIZ-SITE-ANI-CAM-0001 | CAM_Photorealistic_Detail | CAMERA | PHOTOREAL_Cameras_&_Lighting | PHOTOREAL_Cameras_&_Lighting | SITE | SITE | VISUALIZATION | PRESENTATION | ANIMATION | 01 | Existing + Investigation | 1 | 84 | CAMERA_LIGHT |  | VISUALIZATION_CONTROL | CAMERA_OR_LIGHT | Classified from collection PHOTOREAL_Cameras_&_Lighting and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
VIZ-SITE-ANI-CAM-0002 | CAM_Photorealistic_Front | CAMERA | PHOTOREAL_Cameras_&_Lighting | PHOTOREAL_Cameras_&_Lighting | SITE | SITE | VISUALIZATION | PRESENTATION | ANIMATION | 01 | Existing + Investigation | 1 | 84 | CAMERA_LIGHT |  | VISUALIZATION_CONTROL | CAMERA_OR_LIGHT | Classified from collection PHOTOREAL_Cameras_&_Lighting and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
VIZ-SITE-ANI-CAM-0003 | CAM_Photorealistic_Hero | CAMERA | PHOTOREAL_Cameras_&_Lighting | PHOTOREAL_Cameras_&_Lighting | SITE | SITE | VISUALIZATION | PRESENTATION | ANIMATION | 01 | Existing + Investigation | 1 | 84 | CAMERA_LIGHT |  | VISUALIZATION_CONTROL | CAMERA_OR_LIGHT | Classified from collection PHOTOREAL_Cameras_&_Lighting and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
VIZ-SITE-ANI-CAM-0004 | CAM_Realistic_DWV_Cutaway | CAMERA | PHOTOREAL_Cameras_&_Lighting | PHOTOREAL_Cameras_&_Lighting | SITE | SITE | VISUALIZATION | PRESENTATION | ANIMATION | 01 | Existing + Investigation | 1 | 84 | CAMERA_LIGHT |  | VISUALIZATION_CONTROL | CAMERA_OR_LIGHT | Classified from collection PHOTOREAL_Cameras_&_Lighting and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
VIZ-SITE-ANI-CAM-0005 | Camera | CAMERA | Collection | Collection | SITE | SITE | VISUALIZATION | PRESENTATION | ANIMATION | 01 | Existing + Investigation | 1 | 84 | CAMERA_LIGHT |  | VISUALIZATION_CONTROL | CAMERA_OR_LIGHT | Classified from collection Collection and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
VIZ-SITE-ANI-CAM-0006 | Cube | MESH | Collection | Collection | SITE | SITE | VISUALIZATION | PRESENTATION | ANIMATION | 01 | Existing + Investigation | 1 | 84 | CAMERA_LIGHT |  | VISUALIZATION_CONTROL | CAMERA_OR_LIGHT | Classified from collection Collection and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  | Material | 2 | 2 | 2
VIZ-SITE-ANI-CAM-0007 | Late morning sun | LIGHT | PHOTOREAL_Cameras_&_Lighting | PHOTOREAL_Cameras_&_Lighting | SITE | SITE | VISUALIZATION | PRESENTATION | ANIMATION | 01 | Existing + Investigation | 1 | 84 | CAMERA_LIGHT |  | VISUALIZATION_CONTROL | CAMERA_OR_LIGHT | Classified from collection PHOTOREAL_Cameras_&_Lighting and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
VIZ-SITE-ANI-CAM-0008 | Light | LIGHT | Collection | Collection | SITE | SITE | VISUALIZATION | PRESENTATION | ANIMATION | 01 | Existing + Investigation | 1 | 84 | CAMERA_LIGHT |  | VISUALIZATION_CONTROL | CAMERA_OR_LIGHT | Classified from collection Collection and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0
VIZ-SITE-ANI-CAM-0009 | Soft sky fill | LIGHT | PHOTOREAL_Cameras_&_Lighting | PHOTOREAL_Cameras_&_Lighting | SITE | SITE | VISUALIZATION | PRESENTATION | ANIMATION | 01 | Existing + Investigation | 1 | 84 | CAMERA_LIGHT |  | VISUALIZATION_CONTROL | CAMERA_OR_LIGHT | Classified from collection PHOTOREAL_Cameras_&_Lighting and object name. | DOCUMENT_DERIVED | 99-000 | PROVISIONAL | NA | FALSE | NA |  | NA | NOT_COMPUTED |  |  | NA |  |  |  | 0 | 0 | 0

## Schema_Fields
Field | Type | Required | Description
vdc_schema_version | string | TRUE | Data-spine schema version.
vdc_revision | string | TRUE | Model data revision.
vdc_element_id | string | TRUE | Stable production element identifier.
vdc_legacy_name | string | TRUE | Original Blender object name preserved for animation compatibility.
vdc_project_number | string | TRUE | Project number.
vdc_unit | string | TRUE | Residential unit or SITE.
vdc_level | string | TRUE | Building level.
vdc_discipline | string | TRUE | Responsible discipline.
vdc_system | string | TRUE | Building system.
vdc_work_status | string | TRUE | NEW, DEMOLITION, EXISTING_REMAIN, TEMPORARY, TEST, REINSTALLED, RECORD, or context status.
vdc_component_type | string | TRUE | Production component type.
vdc_phase_id | string | TRUE | Current eight-phase sequence ID.
vdc_phase_name | string | TRUE | Current eight-phase sequence name.
vdc_cost_code | string | TRUE | Provisional project cost code.
vdc_cost_code_status | string | TRUE | PROVISIONAL until reconciled with estimating cost-code standard.
vdc_lod | string | TRUE | Target model detail level for the object role.
vdc_model_state | string | TRUE | SOURCE_GEOMETRY, DERIVED_ANIMATION, REFERENCE_CONTEXT, DOCUMENTATION, or VISUALIZATION_CONTROL.
vdc_animation_role | string | TRUE | How this object participates in the 4D animation.
vdc_source | string | TRUE | Source document, field note, or modeling basis.
vdc_verification_status | string | TRUE | DOCUMENT_DERIVED or FIELD_VERIFY_REQUIRED.
vdc_quantity_type | string | TRUE | LENGTH, AREA, VOLUME, COUNT, or NA.
vdc_quantity_value | number | FALSE | Computed quantity when available.
vdc_quantity_unit | string | FALSE | FT, SF, CF, EA, or NA.
vdc_quantity_basis | string | TRUE | CURVE_CENTERLINE, GROWTH_LENGTH, BBOX_APPROX, COUNT, or NOT_COMPUTED.
vdc_parent_route_name | string | FALSE | Source route object for derived animation geometry.
vdc_parent_route_id | string | FALSE | Source route VDC element ID.
vdc_nominal_diameter_in | number | FALSE | Nominal pipe diameter in inches.
vdc_slope_in_per_ft | number | FALSE | Pipe slope in inches per foot.
vdc_slope_status | string | FALSE | DOCUMENTED, NOT_DOCUMENTED, or NA.

## Collection_Map
Collection | Discipline | System | Status | Phase | Component | Quantity | Cost code | LOD | Managed scope | Model state
ANIM_ABS_Extrusion | PLUMBING | DWV | NEW | 04 | INSTALLATION_SEGMENT | LENGTH | 22-100 | 300 | TRUE | DERIVED_ANIMATION
ANIM_Water_Test | PLUMBING | DWV | TEST | 05 | HYDRO_TEST_ROUTE | LENGTH | 22-900 | 300 | TRUE | DERIVED_ANIMATION
ANIM_Construction_Effects | GENERAL | ANIMATION | ANIMATION | 03 | ANIMATION_CONTROL | NA | 99-000 | NA | FALSE | DERIVED_ANIMATION
Ex_Cast_Iron_Pipes_DEMO | PLUMBING | DWV | DEMOLITION | 03 | PIPE_ROUTE | LENGTH | 22-050 | 300 | TRUE | SOURCE_GEOMETRY
Ex_Unit101_&_104_Prior_ABS_REMAIN | PLUMBING | DWV | EXISTING_REMAIN | 01 | PIPE_ROUTE | LENGTH | 22-000 | 300 | TRUE | SOURCE_GEOMETRY
Concrete_Slab_Trench_Cuts_DEMO | CONCRETE | SLAB_ON_GRADE | DEMOLITION | 03 | SLAB_CUT_AREA | AREA | 03-050 | 300 | TRUE | SOURCE_GEOMETRY
Drywall_Cutouts_DEMO | INTERIORS | GYPSUM_BOARD | DEMOLITION | 03 | WALL_OPENING_AREA | AREA | 09-250 | 300 | TRUE | SOURCE_GEOMETRY
New_ABS_Branches_&_Traps | PLUMBING | DWV | NEW | 04 | PIPE_ROUTE | LENGTH | 22-100 | 300 | TRUE | SOURCE_GEOMETRY
New_ABS_UnderSlab_4in_6in | PLUMBING | DWV | NEW | 04 | PIPE_ROUTE | LENGTH | 22-100 | 300 | TRUE | SOURCE_GEOMETRY
New_Stack_TieIns_&_Cleanouts | PLUMBING | DWV | NEW | 04 | FITTING | COUNT | 22-110 | 300 | TRUE | SOURCE_GEOMETRY
Firestop_&_Sleeves | FIRESTOPPING | PENETRATION_FIRESTOP | NEW | 04 | FIRESTOP | COUNT | 07-840 | 300 | TRUE | SOURCE_GEOMETRY
Pipe_Zone_Bedding | EARTHWORK | TRENCH | NEW | 04 | BEDDING_VOLUME | VOLUME | 31-200 | 300 | TRUE | SOURCE_GEOMETRY
General_Trench_Backfill | EARTHWORK | TRENCH | NEW | 06 | BACKFILL_VOLUME | VOLUME | 31-230 | 300 | TRUE | SOURCE_GEOMETRY
Vapor_Barrier_Stegowrap | MOISTURE_PROTECTION | SLAB_VAPOR_BARRIER | NEW | 06 | VAPOR_BARRIER_AREA | AREA | 07-260 | 300 | TRUE | SOURCE_GEOMETRY
Concrete_Pourback | CONCRETE | SLAB_ON_GRADE | NEW | 06 | POURBACK_AREA | AREA | 03-300 | 300 | TRUE | SOURCE_GEOMETRY
Rebar_Dowels_&_Grid | CONCRETE | SLAB_REINFORCEMENT | NEW | 06 | REINFORCEMENT | COUNT | 03-210 | 300 | TRUE | SOURCE_GEOMETRY
Gypsum_Board_Patches | INTERIORS | GYPSUM_BOARD | NEW | 07 | PATCH_AREA | AREA | 09-290 | 300 | TRUE | SOURCE_GEOMETRY
Wall_Framing_Nailers | CARPENTRY | WALL_FRAMING | NEW | 07 | FRAMING_MEMBER | COUNT | 06-100 | 300 | TRUE | SOURCE_GEOMETRY
Waterproofing_Membrane | MOISTURE_PROTECTION | WATERPROOFING | NEW | 06 | MEMBRANE_AREA | AREA | 07-100 | 300 | TRUE | SOURCE_GEOMETRY
Vapor_Mitigating_Epoxy_Primer | FINISHES | FLOOR_PREP | NEW | 07 | COATING_AREA | AREA | 09-600 | 300 | TRUE | SOURCE_GEOMETRY
Temporary_Protection | GENERAL_REQUIREMENTS | TEMPORARY_PROTECTION | TEMPORARY | 02 | PROTECTION_AREA | AREA | 01-500 | 200 | TRUE | SOURCE_GEOMETRY
Staging_Area | GENERAL_REQUIREMENTS | SITE_LOGISTICS | TEMPORARY | 02 | STAGING_AREA | AREA | 01-500 | 200 | TRUE | SOURCE_GEOMETRY
Plumbing_Fixtures | PLUMBING | FIXTURES | REINSTALLED | 08 | FIXTURE | COUNT | 22-420 | 300 | TRUE | SOURCE_GEOMETRY
Cabinets_&_Countertops | FINISHES | CASEWORK | REINSTALLED | 08 | CASEWORK | COUNT | 12-300 | 300 | TRUE | SOURCE_GEOMETRY
Unit_B101_Finishes | FINISHES | UNIT_FINISHES | REINSTALLED | 08 | FINISH | COUNT | 09-900 | 200 | TRUE | SOURCE_GEOMETRY
Unit_B102_Finishes | FINISHES | UNIT_FINISHES | REINSTALLED | 08 | FINISH | COUNT | 09-900 | 200 | TRUE | SOURCE_GEOMETRY
Unit_B103_Finishes | FINISHES | UNIT_FINISHES | REINSTALLED | 08 | FINISH | COUNT | 09-900 | 200 | TRUE | SOURCE_GEOMETRY
Unit_B104_Finishes | FINISHES | UNIT_FINISHES | REINSTALLED | 08 | FINISH | COUNT | 09-900 | 200 | TRUE | SOURCE_GEOMETRY
As_Built_Callout_Overlay | DOCUMENTATION | AS_BUILT | RECORD | 08 | CALLOUT | COUNT | 01-780 | NA | TRUE | DOCUMENTATION
Side_Sewer_Main_6in | CIVIL | SITE_SEWER | EXISTING_REMAIN | 01 | PIPE_ROUTE | LENGTH | 33-300 | 300 | TRUE | SOURCE_GEOMETRY
Concrete_Slab_Unmodified | STRUCTURE | SLAB_ON_GRADE | EXISTING_REMAIN | 01 | SLAB_AREA | AREA | 03-000 | 200 | TRUE | SOURCE_GEOMETRY
Foundation_Footings | STRUCTURE | FOUNDATION | EXISTING_REMAIN | 01 | FOOTING | COUNT | 03-000 | 200 | TRUE | SOURCE_GEOMETRY
Precast_Concrete_Walls | STRUCTURE | FOUNDATION_WALL | EXISTING_REMAIN | 01 | WALL | AREA | 03-000 | 200 | TRUE | SOURCE_GEOMETRY
Wood_Stud_Partitions | CARPENTRY | WALL_FRAMING | EXISTING_REMAIN | 01 | FRAMING_MEMBER | COUNT | 06-000 | 200 | TRUE | SOURCE_GEOMETRY
Subgrade_&_Soil | EARTHWORK | SUBGRADE | EXISTING_REMAIN | 01 | SOIL_VOLUME | VOLUME | 31-000 | 200 | TRUE | SOURCE_GEOMETRY
Radiant_Heating_Coils | HVAC | RADIANT_HEATING | EXISTING_PROTECT | 03 | IN_SLAB_UTILITY | LENGTH | 23-000 | 200 | TRUE | SOURCE_GEOMETRY
00_Site_&_Context | ARCHITECTURE | SITE_CONTEXT | EXISTING_CONTEXT | 01 | CONTEXT | NA | 00-000 | 200 | FALSE | REFERENCE_CONTEXT
01_Structural_Base | STRUCTURE | BUILDING_STRUCTURE | EXISTING_CONTEXT | 01 | CONTEXT | NA | 03-000 | 200 | FALSE | REFERENCE_CONTEXT
02_Existing_Conditions_&_Demo | GENERAL | EXISTING_CONDITIONS | DEMOLITION | 03 | CONTEXT | NA | 02-410 | 200 | TRUE | SOURCE_GEOMETRY
03_New_Plumbing_DWV | PLUMBING | DWV | NEW | 04 | CONTEXT | NA | 22-100 | 300 | TRUE | SOURCE_GEOMETRY
04_Trench_Backfill_&_Slab_Pourback | CONSTRUCTION | TRENCH_AND_SLAB | NEW | 06 | CONTEXT | NA | 31-200 | 300 | TRUE | SOURCE_GEOMETRY
05_Wall_&_Floor_Substrates | INTERIORS | SUBSTRATES | NEW | 07 | CONTEXT | NA | 09-000 | 300 | TRUE | SOURCE_GEOMETRY
06_Interior_Finishes_&_Fixtures | FINISHES | FINISHES_AND_FIXTURES | REINSTALLED | 08 | CONTEXT | NA | 09-900 | 200 | TRUE | SOURCE_GEOMETRY
Bldg_B_Shell_&_Upper_Stacks | ARCHITECTURE | BUILDING_CONTEXT | EXISTING_CONTEXT | 01 | CONTEXT | NA | 00-000 | 200 | FALSE | REFERENCE_CONTEXT
East_Garages_&_Planter_Strip | ARCHITECTURE | SITE_CONTEXT | EXISTING_CONTEXT | 01 | CONTEXT | NA | 00-000 | 200 | FALSE | REFERENCE_CONTEXT
PHOTOREAL_Architecture | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | CONTEXT | NA | 00-000 | 200 | FALSE | REFERENCE_CONTEXT
PHOTOREAL_Fixtures_&_Details | ARCHITECTURE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | CONTEXT | NA | 00-000 | 200 | FALSE | REFERENCE_CONTEXT
PHOTOREAL_Landscape | LANDSCAPE | PRESENTATION_CONTEXT | EXISTING_CONTEXT | 01 | CONTEXT | NA | 00-000 | 200 | FALSE | REFERENCE_CONTEXT
PHOTOREAL_Cameras_&_Lighting | VISUALIZATION | PRESENTATION | ANIMATION | 01 | CAMERA_LIGHT | NA | 99-000 | NA | FALSE | VISUALIZATION_CONTROL
Collection | VISUALIZATION | PRESENTATION | ANIMATION | 01 | CAMERA_LIGHT | NA | 99-000 | NA | FALSE | VISUALIZATION_CONTROL

## Validation
Phase 1 validation
Blocking check | Result count
missing_required | 0
duplicate_element_ids | 0
managed_scope_missing_fields | 0
pipe_routes_missing_diameter | 0
unresolved_parent_routes | 0
Open data item | Object name
Pipe slope not documented | EX_Side_Sewer_Main_8in
Pipe slope not documented | NEW_ABS_B103_4in_RAISED_FLOOR
Integrity | Value
Core model fields changed | 0
Object count | 2980
Action count | 2971
F-curve count | 4394
Keyframe count | 19763
Render comparison | IDENTICAL_RGB
Post-save readback | PASS

## Quality_Rules
Quality rules
1 | Every object receives a unique vdc_element_id.
2 | Every managed-scope object receives unit, source, verification status, quantity type, and provisional cost code.
3 | Pipe routes require nominal diameter; undocumented slope is carried as an open data item rather than invented.
4 | Derived growth and hydrotest objects must resolve to a parent source route.
5 | Original Blender names are preserved as vdc_legacy_name during Phase 1.