## Summary
Meydenbauer VDC — Phase 2 Constructability Validation
Geometry, slope, clearance, and final-state quantity validation of the animated 4D coordination model
Revision | VDC-P2-002
Status | PHASE_2_PENETRATION_RESOLVED (rev VDC-P2-002)
Issued | 2026-10-27
Key Metrics |  | Sheets
Metric | Value | Issue_Register | 5 constructability issues with severity and recommended action
Pipe routes checked | 66 | Route_Diagnostics | 66 pipe routes: lengths, inverts, actual vs documented slope
Routes passing slope tolerance | 0 | Quantity_Refinements | 444 final-state quantities at frame 672 vs Phase 1 values
Routes with slope deviations | 0 | Quantity_Warnings | 12 fire-seal objects requiring area review
Routes with undocumented slope | 0 | Methodology | Evaluation contract, tolerances, and data sources
Clearance checks executed | 2025
Constructability issues raised | 5
High-severity issues (open) | 0
Issues resolved (VDC-P2-002) | 1
Final-state quantity refinements | 444
Quantity warnings (fire-seal areas) | 12
Structural proximity targets (BVH) | 46

## Issue_Register
Constructability Issue Register
Phase 2 geometry and clearance validation findings
Issue ID | Severity | Category | Element | Element ID | Related Object | Finding | Threshold | Recommended Action | Status | Resolution
VDC-P2-001 | HIGH | STRUCTURAL_CLEARANCE |  | PLM-B103-NEW-PIPE-0007 |  | Slope not documented in model metadata | 0.25 | Confirm penetration, sleeve, underside clearance, or routing intent; coordinate with structural/architectural documents. | RESOLVED | Designed penetration: 6in sleeve PLM-B103-NEW-SLEEVE-0001 installed at SOG penetration (123.39, 28.11); annular gap 1.35 in; sleeve extends +2in above slab top / -3in below soffit; resolved in revision VDC-P2-002
VDC-P2-002 | MEDIUM | SLOPE_DEVIATION |  | PLM-B101-DEM-PIPE-0001 |  | Slope not documented in model metadata | 0.0625 | Reconcile model centerline with design intent or update documented slope. | OPEN
VDC-P2-003 | MEDIUM | SLOPE_NOT_DOCUMENTED |  | CIV-SITE-EXG-PIPE-0001 |  | Slope not documented in model metadata |  | Obtain design/field slope confirmation; do not infer slope from modeled centerline alone. | OPEN
VDC-P2-004 | MEDIUM | SLOPE_DEVIATION |  | PLM-B101-NEW-PIPE-0001 |  | Slope not documented in model metadata | 0.0625 | Reconcile model centerline with design intent or update documented slope. | OPEN
VDC-P2-005 | MEDIUM | SLOPE_NOT_DOCUMENTED |  | PLM-B103-NEW-PIPE-0007 |  | Slope not documented in model metadata |  | Obtain design/field slope confirmation; do not infer slope from modeled centerline alone. | OPEN

## Route_Diagnostics
Pipe Route Diagnostics
Actual centerline geometry, estimated inverts, and slope compliance per route
Element | Element ID | Status | Nominal Dia (in) | Length (ft) | Start CL Elev (ft) | End CL Elev (ft) | Est. Start Invert (ft) | Est. End Invert (ft) | Actual Slope (in/ft) | Documented Slope (in/ft) | Deviation (in/ft) | Slope Status | Min Pipe Clearance (ft) | Min Structure Clearance (ft) | Issue IDs
| PLM-B101-EXG-PIPE-0001 | EXISTING_REMAIN | 4 | 2.231 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B104-EXG-PIPE-0001 | EXISTING_REMAIN | 4 | 3.904 |  |  |  |  | 0.25 | 0.25 | 0
| CIV-B101-EXG-PIPE-0001 | EXISTING_REMAIN | 6 | 18.504 |  |  |  |  | 0.25 | 0.25 | 0
| CIV-B102-EXG-PIPE-0001 | EXISTING_REMAIN | 6 | 18.504 |  |  |  |  | 0.25 | 0.25 | 0
| CIV-B103-EXG-PIPE-0001 | EXISTING_REMAIN | 6 | 18.504 |  |  |  |  | 0.25 | 0.25 | 0
| CIV-B104-EXG-PIPE-0001 | EXISTING_REMAIN | 6 | 18.504 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B101-DEM-PIPE-0001 | DEMOLITION | 2 | 11.92 |  |  |  |  | 0.319 | 0.25 | 0.069
| PLM-B101-DEM-PIPE-0002 | DEMOLITION | 2 | 3.462 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B101-DEM-PIPE-0003 | DEMOLITION | 3 | 5.09 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B101-DEM-PIPE-0004 | DEMOLITION | 3 | 4.161 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B101-DEM-PIPE-0005 | DEMOLITION | 3 | 1.02 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B101-DEM-PIPE-0006 | DEMOLITION | 6 | 1.5 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B101-DEM-PIPE-0007 | DEMOLITION | 4 | 45.432 |  |  |  |  | 0.275 | 0.25 | 0.025
| PLM-B102-DEM-PIPE-0001 | DEMOLITION | 2 | 7.266 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B102-DEM-PIPE-0002 | DEMOLITION | 2 | 6.494 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B102-DEM-PIPE-0003 | DEMOLITION | 3 | 4.756 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B102-DEM-PIPE-0004 | DEMOLITION | 3 | 5.128 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B102-DEM-PIPE-0005 | DEMOLITION | 3 | 1.333 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B102-DEM-PIPE-0006 | DEMOLITION | 3 | 1.151 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B102-DEM-PIPE-0007 | DEMOLITION | 6 | 1.5 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B102-DEM-PIPE-0008 | DEMOLITION | 4 | 48.434 |  |  |  |  | 0.266 | 0.25 | 0.016
| PLM-B103-DEM-PIPE-0001 | DEMOLITION | 2 | 6.506 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B103-DEM-PIPE-0002 | DEMOLITION | 2 | 9.131 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B103-DEM-PIPE-0003 | DEMOLITION | 3 | 5.799 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B103-DEM-PIPE-0004 | DEMOLITION | 3 | 7.754 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B103-DEM-PIPE-0005 | DEMOLITION | 3 | 0.337 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B103-DEM-PIPE-0006 | DEMOLITION | 6 | 1.5 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B103-DEM-PIPE-0007 | DEMOLITION | 4 | 31.59 |  |  |  |  | 0.27 | 0.25 | 0.02
| PLM-B104-DEM-PIPE-0001 | DEMOLITION | 2 | 5.185 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B104-DEM-PIPE-0002 | DEMOLITION | 2 | 3.614 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B104-DEM-PIPE-0003 | DEMOLITION | 3 | 3.479 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B104-DEM-PIPE-0004 | DEMOLITION | 3 | 2.279 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B104-DEM-PIPE-0005 | DEMOLITION | 3 | 10.131 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B104-DEM-PIPE-0006 | DEMOLITION | 6 | 1.5 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B104-DEM-PIPE-0007 | DEMOLITION | 4 | 43.513 |  |  |  |  | 0.267 | 0.25 | 0.017
| CIV-SITE-EXG-PIPE-0001 | EXISTING_REMAIN | 8 | 176.458 |  |  |  |  | 0
| PLM-B101-NEW-PIPE-0001 | NEW | 2 | 11.92 |  |  |  |  | 0.319 | 0.25 | 0.069
| PLM-B101-NEW-PIPE-0002 | NEW | 2 | 3.462 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B101-NEW-PIPE-0003 | NEW | 3 | 5.09 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B101-NEW-PIPE-0004 | NEW | 3 | 4.161 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B101-NEW-PIPE-0005 | NEW | 3 | 1.02 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B101-NEW-PIPE-0006 | NEW | 4 | 45.432 |  |  |  |  | 0.275 | 0.25 | 0.025
| PLM-B101-NEW-PIPE-0007 | NEW | 6 | 1.5 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B102-NEW-PIPE-0001 | NEW | 2 | 7.266 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B102-NEW-PIPE-0002 | NEW | 2 | 6.494 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B102-NEW-PIPE-0003 | NEW | 3 | 4.756 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B102-NEW-PIPE-0004 | NEW | 3 | 5.128 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B102-NEW-PIPE-0005 | NEW | 3 | 1.333 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B102-NEW-PIPE-0006 | NEW | 3 | 1.151 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B102-NEW-PIPE-0007 | NEW | 4 | 48.434 |  |  |  |  | 0.266 | 0.25 | 0.016
| PLM-B102-NEW-PIPE-0008 | NEW | 6 | 1.5 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B103-NEW-PIPE-0001 | NEW | 2 | 6.506 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B103-NEW-PIPE-0002 | NEW | 2 | 9.131 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B103-NEW-PIPE-0003 | NEW | 3 | 5.799 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B103-NEW-PIPE-0004 | NEW | 3 | 7.754 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B103-NEW-PIPE-0005 | NEW | 3 | 0.337 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B103-NEW-PIPE-0006 | NEW | 4 | 31.59 |  |  |  |  | 0.27 | 0.25 | 0.02
| PLM-B103-NEW-PIPE-0007 | NEW | 4 | 30.683 |  |  |  |  | 1.221
| PLM-B103-NEW-PIPE-0008 | NEW | 6 | 1.5 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B104-NEW-PIPE-0001 | NEW | 2 | 5.185 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B104-NEW-PIPE-0002 | NEW | 2 | 3.614 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B104-NEW-PIPE-0003 | NEW | 3 | 3.479 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B104-NEW-PIPE-0004 | NEW | 3 | 2.279 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B104-NEW-PIPE-0005 | NEW | 3 | 10.131 |  |  |  |  | 0.25 | 0.25 | 0
| PLM-B104-NEW-PIPE-0006 | NEW | 4 | 43.513 |  |  |  |  | 0.267 | 0.25 | 0.017
| PLM-B104-NEW-PIPE-0007 | NEW | 6 | 1.5 |  |  |  |  | 0.25 | 0.25 | 0

## Quantity_Refinements
Final-State Quantity Refinements
Quantities re-evaluated at frame 672 (completed construction state) with corrected world transforms
Element | Element ID | Unit | Phase 1 Quantity | Phase 2 Quantity | Delta % | Phase 2 Basis | Phase
INT-B101-DEM-OPN-0001
INT-B101-DEM-OPN-0002
INT-B101-DEM-OPN-0003
GEN-B101-TMP-PRO-0001
FIN-B101-NEW-CTG-0001
INT-B101-NEW-PAT-0004
INT-B101-NEW-PAT-0005
INT-B101-NEW-PAT-0006
INT-B101-NEW-PAT-0007
PLM-B101-EXG-PIPE-0001
MST-B101-NEW-MEM-0001
GEN-B101-TMP-PRO-0002
STR-B101-EXG-SLB-0001
HVAC-B102-PRT-UTL-0001
INT-B102-DEM-OPN-0001
INT-B102-DEM-OPN-0002
INT-B102-DEM-OPN-0003
GEN-B102-TMP-PRO-0001
FIN-B102-NEW-CTG-0001
INT-B102-NEW-PAT-0004
INT-B102-NEW-PAT-0005
INT-B102-NEW-PAT-0006
INT-B102-NEW-PAT-0007
MST-B102-NEW-MEM-0001
GEN-B102-TMP-PRO-0002
STR-B102-EXG-SLB-0001
INT-B103-DEM-OPN-0001
INT-B103-DEM-OPN-0002
INT-B103-DEM-OPN-0003
GEN-B103-TMP-PRO-0001
FIN-B103-NEW-CTG-0001
INT-B103-NEW-PAT-0004
INT-B103-NEW-PAT-0005
INT-B103-NEW-PAT-0006
INT-B103-NEW-PAT-0007
MST-B103-NEW-MEM-0001
GEN-B103-TMP-PRO-0002
STR-B103-EXG-SLB-0001
HVAC-B104-PRT-UTL-0001
INT-B104-DEM-OPN-0001
INT-B104-DEM-OPN-0002
INT-B104-DEM-OPN-0003
GEN-B104-TMP-PRO-0001
FIN-B104-NEW-CTG-0001
INT-B104-NEW-PAT-0004
INT-B104-NEW-PAT-0005
INT-B104-NEW-PAT-0006
INT-B104-NEW-PAT-0007
PLM-B104-EXG-PIPE-0001
MST-B104-NEW-MEM-0001
GEN-B104-TMP-PRO-0002
STR-B104-EXG-SLB-0001
EAR-B101-NEW-BED-0001
EAR-B101-NEW-BED-0002
EAR-B101-NEW-BED-0003
EAR-B101-NEW-BED-0004
EAR-B101-NEW-BED-0005
EAR-B101-NEW-BED-0006
EAR-B101-NEW-BED-0007
EAR-B101-NEW-BED-0008
EAR-B101-NEW-BED-0009
EAR-B101-NEW-BED-0010
EAR-B101-NEW-BED-0011
EAR-B102-NEW-BED-0001
EAR-B102-NEW-BED-0002
EAR-B102-NEW-BED-0003
EAR-B102-NEW-BED-0004
EAR-B102-NEW-BED-0005
EAR-B102-NEW-BED-0006
EAR-B102-NEW-BED-0007
EAR-B102-NEW-BED-0008
EAR-B102-NEW-BED-0009
EAR-B102-NEW-BED-0010
EAR-B102-NEW-BED-0011
EAR-B103-NEW-BED-0001
EAR-B103-NEW-BED-0002
EAR-B103-NEW-BED-0003
EAR-B103-NEW-BED-0004
EAR-B103-NEW-BED-0005
EAR-B103-NEW-BED-0006
EAR-B103-NEW-BED-0007
EAR-B103-NEW-BED-0008
EAR-B103-NEW-BED-0009
EAR-B104-NEW-BED-0001
EAR-B104-NEW-BED-0002
EAR-B104-NEW-BED-0003
EAR-B104-NEW-BED-0004
EAR-B104-NEW-BED-0005
EAR-B104-NEW-BED-0006
EAR-B104-NEW-BED-0007
EAR-B104-NEW-BED-0008
EAR-B104-NEW-BED-0009
EAR-B104-NEW-BED-0010
PLM-SITE-DEM-INS-0002
PLM-SITE-DEM-INS-0004
STR-SITE-EXG-SLB-0001
STR-SITE-EXG-WAL-0001
STR-SITE-EXG-WAL-0002
STR-SITE-EXG-WAL-0003
STR-SITE-EXG-WAL-0004
STR-SITE-EXG-WAL-0005
STR-SITE-EXG-WAL-0006
STR-SITE-EXG-WAL-0007
CIV-B101-EXG-PIPE-0001
CIV-B102-EXG-PIPE-0001
CIV-B103-EXG-PIPE-0001
CIV-B104-EXG-PIPE-0001
PLM-B101-DEM-PIPE-0001
PLM-B101-DEM-PIPE-0002
PLM-B101-DEM-PIPE-0003
PLM-B101-DEM-PIPE-0004
PLM-B101-DEM-PIPE-0005
PLM-B101-DEM-PIPE-0006
PLM-B101-DEM-PIPE-0007
PLM-B102-DEM-PIPE-0001
PLM-B102-DEM-PIPE-0002
PLM-B102-DEM-PIPE-0003
PLM-B102-DEM-PIPE-0004
PLM-B102-DEM-PIPE-0005
PLM-B102-DEM-PIPE-0006
PLM-B102-DEM-PIPE-0007
PLM-B102-DEM-PIPE-0008
PLM-B103-DEM-PIPE-0001
PLM-B103-DEM-PIPE-0002
PLM-B103-DEM-PIPE-0003
PLM-B103-DEM-PIPE-0004
PLM-B103-DEM-PIPE-0005
PLM-B103-DEM-PIPE-0006
PLM-B103-DEM-PIPE-0007
PLM-B104-DEM-PIPE-0001
PLM-B104-DEM-PIPE-0002
PLM-B104-DEM-PIPE-0003
PLM-B104-DEM-PIPE-0004
PLM-B104-DEM-PIPE-0005
PLM-B104-DEM-PIPE-0006
PLM-B104-DEM-PIPE-0007
CIV-SITE-EXG-PIPE-0001
EAR-B101-NEW-BF-0001
EAR-B101-NEW-BF-0002
EAR-B101-NEW-BF-0003
EAR-B101-NEW-BF-0004
EAR-B101-NEW-BF-0005
EAR-B101-NEW-BF-0006
EAR-B101-NEW-BF-0007
EAR-B101-NEW-BF-0008
EAR-B101-NEW-BF-0009
EAR-B101-NEW-BF-0010
EAR-B101-NEW-BF-0011
EAR-B102-NEW-BF-0001
EAR-B102-NEW-BF-0002
EAR-B102-NEW-BF-0003
EAR-B102-NEW-BF-0004
EAR-B102-NEW-BF-0005
EAR-B102-NEW-BF-0006
EAR-B102-NEW-BF-0007
EAR-B102-NEW-BF-0008
EAR-B102-NEW-BF-0009
EAR-B102-NEW-BF-0010
EAR-B102-NEW-BF-0011
EAR-B103-NEW-BF-0001
EAR-B103-NEW-BF-0002
EAR-B103-NEW-BF-0003
EAR-B103-NEW-BF-0004
EAR-B103-NEW-BF-0005
EAR-B103-NEW-BF-0006
EAR-B103-NEW-BF-0007
EAR-B103-NEW-BF-0008
EAR-B103-NEW-BF-0009
EAR-B104-NEW-BF-0001
EAR-B104-NEW-BF-0002
EAR-B104-NEW-BF-0003
EAR-B104-NEW-BF-0004
EAR-B104-NEW-BF-0005
EAR-B104-NEW-BF-0006
EAR-B104-NEW-BF-0007
EAR-B104-NEW-BF-0008
EAR-B104-NEW-BF-0009
EAR-B104-NEW-BF-0010
PLM-B101-TST-TST-0001
PLM-B101-TST-TST-0002
PLM-B101-TST-TST-0003
PLM-B101-TST-TST-0004
PLM-B101-TST-TST-0005
PLM-B101-TST-TST-0006
PLM-B101-TST-TST-0007
PLM-B102-TST-TST-0001
PLM-B102-TST-TST-0002
PLM-B102-TST-TST-0003
PLM-B102-TST-TST-0004
PLM-B102-TST-TST-0005
PLM-B102-TST-TST-0006
PLM-B102-TST-TST-0007
PLM-B102-TST-TST-0008
PLM-B103-TST-TST-0001
PLM-B103-TST-TST-0002
PLM-B103-TST-TST-0003
PLM-B103-TST-TST-0004
PLM-B103-TST-TST-0005
PLM-B103-TST-TST-0006
PLM-B103-TST-TST-0007
PLM-B103-TST-TST-0008
PLM-B104-TST-TST-0001
PLM-B104-TST-TST-0002
PLM-B104-TST-TST-0003
PLM-B104-TST-TST-0004
PLM-B104-TST-TST-0005
PLM-B104-TST-TST-0006
PLM-B104-TST-TST-0007
PLM-B101-TST-TST-0008
PLM-B101-TST-TST-0009
PLM-B101-TST-TST-0010
PLM-B102-TST-TST-0009
PLM-B102-TST-TST-0010
PLM-B102-TST-TST-0011
PLM-B102-TST-TST-0012
PLM-B103-TST-TST-0009
PLM-B103-TST-TST-0010
PLM-B103-TST-TST-0011
PLM-B104-TST-TST-0008
PLM-B104-TST-TST-0009
PLM-B104-TST-TST-0010
PLM-B101-TST-TST-0011
PLM-B102-TST-TST-0013
PLM-B103-TST-TST-0012
PLM-B104-TST-TST-0011
PLM-B101-NEW-PIPE-0001
PLM-B101-NEW-PIPE-0002
PLM-B101-NEW-PIPE-0003
PLM-B101-NEW-PIPE-0004
PLM-B101-NEW-PIPE-0005
PLM-B101-NEW-PIPE-0006
PLM-B101-NEW-PIPE-0007
PLM-B102-NEW-PIPE-0001
PLM-B102-NEW-PIPE-0002
PLM-B102-NEW-PIPE-0003
PLM-B102-NEW-PIPE-0004
PLM-B102-NEW-PIPE-0005
PLM-B102-NEW-PIPE-0006
PLM-B102-NEW-PIPE-0007
PLM-B102-NEW-PIPE-0008
PLM-B103-NEW-PIPE-0001
PLM-B103-NEW-PIPE-0002
PLM-B103-NEW-PIPE-0003
PLM-B103-NEW-PIPE-0004
PLM-B103-NEW-PIPE-0005
PLM-B103-NEW-PIPE-0006
PLM-B103-NEW-PIPE-0007
PLM-B103-NEW-PIPE-0008
PLM-B104-NEW-PIPE-0001
PLM-B104-NEW-PIPE-0002
PLM-B104-NEW-PIPE-0003
PLM-B104-NEW-PIPE-0004
PLM-B104-NEW-PIPE-0005
PLM-B104-NEW-PIPE-0006
PLM-B104-NEW-PIPE-0007
STR-SITE-EXG-WAL-0008
EAR-B101-NEW-BED-0012
EAR-B101-NEW-BED-0013
EAR-B101-NEW-BED-0014
EAR-B101-NEW-BED-0015
EAR-B101-NEW-BED-0016
EAR-B101-NEW-BED-0017
EAR-B101-NEW-BED-0018
EAR-B101-NEW-BED-0019
EAR-B101-NEW-BED-0020
EAR-B101-NEW-BED-0021
EAR-B101-NEW-BED-0022
EAR-B102-NEW-BED-0012
EAR-B102-NEW-BED-0013
EAR-B102-NEW-BED-0014
EAR-B102-NEW-BED-0015
EAR-B102-NEW-BED-0016
EAR-B102-NEW-BED-0017
EAR-B102-NEW-BED-0018
EAR-B102-NEW-BED-0019
EAR-B102-NEW-BED-0020
EAR-B102-NEW-BED-0021
EAR-B102-NEW-BED-0022
EAR-B103-NEW-BED-0010
EAR-B103-NEW-BED-0011
EAR-B103-NEW-BED-0012
EAR-B103-NEW-BED-0013
EAR-B103-NEW-BED-0014
EAR-B103-NEW-BED-0015
EAR-B103-NEW-BED-0016
EAR-B103-NEW-BED-0017
EAR-B103-NEW-BED-0018
EAR-B104-NEW-BED-0011
EAR-B104-NEW-BED-0012
EAR-B104-NEW-BED-0013
EAR-B104-NEW-BED-0014
EAR-B104-NEW-BED-0015
EAR-B104-NEW-BED-0016
EAR-B104-NEW-BED-0017
EAR-B104-NEW-BED-0018
EAR-B104-NEW-BED-0019
EAR-B104-NEW-BED-0020
CON-B101-NEW-PB-0001
CON-B101-NEW-PB-0002
CON-B101-NEW-PB-0003
CON-B101-NEW-PB-0004
CON-B101-NEW-PB-0005
CON-B101-NEW-PB-0006
CON-B101-NEW-PB-0007
CON-B101-NEW-PB-0008
CON-B101-NEW-PB-0009
CON-B101-NEW-PB-0010
CON-B101-NEW-PB-0011
CON-B102-NEW-PB-0001
CON-B102-NEW-PB-0002
CON-B102-NEW-PB-0003
CON-B102-NEW-PB-0004
CON-B102-NEW-PB-0005
CON-B102-NEW-PB-0006
CON-B102-NEW-PB-0007
CON-B102-NEW-PB-0008
CON-B102-NEW-PB-0009
CON-B102-NEW-PB-0010
CON-B102-NEW-PB-0011
CON-B103-NEW-PB-0001
CON-B103-NEW-PB-0002
CON-B103-NEW-PB-0003
CON-B103-NEW-PB-0004
CON-B103-NEW-PB-0005
CON-B103-NEW-PB-0006
CON-B103-NEW-PB-0007
CON-B103-NEW-PB-0008
CON-B103-NEW-PB-0009
CON-B104-NEW-PB-0001
CON-B104-NEW-PB-0002
CON-B104-NEW-PB-0003
CON-B104-NEW-PB-0004
CON-B104-NEW-PB-0005
CON-B104-NEW-PB-0006
CON-B104-NEW-PB-0007
CON-B104-NEW-PB-0008
CON-B104-NEW-PB-0009
CON-B104-NEW-PB-0010
STR-SITE-EXG-WAL-0009
STR-SITE-EXG-WAL-0010
STR-SITE-EXG-WAL-0011
PLM-B101-NEW-FIT-0007
PLM-B101-NEW-FIT-0008
PLM-B101-NEW-FIT-0009
PLM-B102-NEW-FIT-0007
PLM-B102-NEW-FIT-0008
PLM-B102-NEW-FIT-0009
PLM-B102-NEW-FIT-0010
PLM-B103-NEW-FIT-0007
PLM-B103-NEW-FIT-0008
PLM-B103-NEW-FIT-0009
PLM-B104-NEW-FIT-0007
PLM-B104-NEW-FIT-0008
PLM-B104-NEW-FIT-0009
STR-SITE-EXG-WAL-0012
GEN-SITE-TMP-STG-0001
MST-B101-NEW-VB-0001
MST-B101-NEW-VB-0002
MST-B101-NEW-VB-0003
MST-B101-NEW-VB-0004
MST-B101-NEW-VB-0005
MST-B101-NEW-VB-0006
MST-B101-NEW-VB-0007
MST-B101-NEW-VB-0008
MST-B101-NEW-VB-0009
MST-B101-NEW-VB-0010
MST-B101-NEW-VB-0011
MST-B102-NEW-VB-0001
MST-B102-NEW-VB-0002
MST-B102-NEW-VB-0003
MST-B102-NEW-VB-0004
MST-B102-NEW-VB-0005
MST-B102-NEW-VB-0006
MST-B102-NEW-VB-0007
MST-B102-NEW-VB-0008
MST-B102-NEW-VB-0009
MST-B102-NEW-VB-0010
MST-B102-NEW-VB-0011
MST-B103-NEW-VB-0001
MST-B103-NEW-VB-0002
MST-B103-NEW-VB-0003
MST-B103-NEW-VB-0004
MST-B103-NEW-VB-0005
MST-B103-NEW-VB-0006
MST-B103-NEW-VB-0007
MST-B103-NEW-VB-0008
MST-B103-NEW-VB-0009
MST-B104-NEW-VB-0001
MST-B104-NEW-VB-0002
MST-B104-NEW-VB-0003
MST-B104-NEW-VB-0004
MST-B104-NEW-VB-0005
MST-B104-NEW-VB-0006
MST-B104-NEW-VB-0007
MST-B104-NEW-VB-0008
MST-B104-NEW-VB-0009
MST-B104-NEW-VB-0010
EAR-SITE-EXG-SOIL-0001
PLM-B101-NEW-TRW-0001
PLM-B102-NEW-TRW-0001
PLM-B103-NEW-TRW-0001
PLM-B104-NEW-TRW-0001
CON-B101-DEM-CUT-0001
CON-B101-DEM-CUT-0002
CON-B101-DEM-CUT-0003
CON-B101-DEM-CUT-0004
CON-B101-DEM-CUT-0005
CON-B101-DEM-CUT-0006
CON-B101-DEM-CUT-0007
CON-B101-DEM-CUT-0008
CON-B101-DEM-CUT-0009
CON-B101-DEM-CUT-0010
CON-B101-DEM-CUT-0011
CON-B102-DEM-CUT-0001
CON-B102-DEM-CUT-0002
CON-B102-DEM-CUT-0003
CON-B102-DEM-CUT-0004
CON-B102-DEM-CUT-0005
CON-B102-DEM-CUT-0006
CON-B102-DEM-CUT-0007
CON-B102-DEM-CUT-0008
CON-B102-DEM-CUT-0009
CON-B102-DEM-CUT-0010
CON-B102-DEM-CUT-0011
CON-B103-DEM-CUT-0001
CON-B103-DEM-CUT-0002
CON-B103-DEM-CUT-0003
CON-B103-DEM-CUT-0004
CON-B103-DEM-CUT-0005
CON-B103-DEM-CUT-0006
CON-B103-DEM-CUT-0007
CON-B103-DEM-CUT-0008
CON-B103-DEM-CUT-0009
CON-B104-DEM-CUT-0001
CON-B104-DEM-CUT-0002
CON-B104-DEM-CUT-0003
CON-B104-DEM-CUT-0004
CON-B104-DEM-CUT-0005
CON-B104-DEM-CUT-0006
CON-B104-DEM-CUT-0007
CON-B104-DEM-CUT-0008
CON-B104-DEM-CUT-0009
CON-B104-DEM-CUT-0010
STR-SITE-EXG-WAL-0013

## Quantity_Warnings
Quantity Warnings
Objects where automated final-state area could not be computed — all are fire-seal penetration seals
Element | Element ID | Warning | Recommended Action
|  | Could not produce projected mesh area | Review fire-seal geometry; measure penetration area in model or field-verify
|  | Could not produce projected mesh area | Review fire-seal geometry; measure penetration area in model or field-verify
|  | Could not produce projected mesh area | Review fire-seal geometry; measure penetration area in model or field-verify
|  | Could not produce projected mesh area | Review fire-seal geometry; measure penetration area in model or field-verify
|  | Could not produce projected mesh area | Review fire-seal geometry; measure penetration area in model or field-verify
|  | Could not produce projected mesh area | Review fire-seal geometry; measure penetration area in model or field-verify
|  | Could not produce projected mesh area | Review fire-seal geometry; measure penetration area in model or field-verify
|  | Could not produce projected mesh area | Review fire-seal geometry; measure penetration area in model or field-verify
|  | Could not produce projected mesh area | Review fire-seal geometry; measure penetration area in model or field-verify
|  | Could not produce projected mesh area | Review fire-seal geometry; measure penetration area in model or field-verify
|  | Could not produce projected mesh area | Review fire-seal geometry; measure penetration area in model or field-verify
|  | Could not produce projected mesh area | Review fire-seal geometry; measure penetration area in model or field-verify

## Methodology
Phase 2 Methodology & Tolerances
Evaluation state | All quantities and clearances evaluated at frame 672 (completed construction state), not the saved early frame.
Transform handling | Evaluated world matrix used; matrix_basis fallback applied for legacy objects with stale world transforms.
Units | 1 Blender unit = 1 foot; Z-up; imperial throughout.
Slope contract | Actual slope computed from centerline end elevations / centerline length; documented slope compared with tolerance ±0.0625 in/ft; compliant band 0.125–0.50 in/ft.
Invert estimation | Estimated invert = centerline elevation minus nominal pipe radius. Labeled estimated pending field verification.
Pipe clearance | Segment-to-segment minimum distance between sampled route centerlines; threshold 0.25 ft.
Radiant heating clearance | Minimum distance to radiant heating geometry; threshold 0.50 ft.
Structure proximity | BVH nearest-point queries against 46 structural targets; threshold 0.25 ft.
Area quantities | Horizontal components: XY projected area (Shapely union). Walls/vertical: best-plane projected area (YZ/XZ).
Volume quantities | Final-state prism volume for extruded trench prisms; signed closed-mesh volume otherwise.
Issue severities | HIGH = physical conflict requiring resolution before install; MEDIUM = documentation or tolerance gap; LOW = advisory.
Data sources | Blender VDC model (Phase 1 data spine), Phase 2 diagnostic computation; no external data fetched.
Source file | Meydenbauer_4D_Construction_Sequence_VDC_Phase2.blend (core model verified unchanged; render pixel-identical to Phase 1).