## Summary
Meydenbauer VDC — Phase 3 Schedule-Driven 4D
Animation retimed from a working-day baseline schedule (Bellevue WA, non-union, Q1 2027)
Revision | VDC-P3-001
Schedule ID | MEYD-BL-001
Data date | 2027-01-04
Schedule start | 2027-01-04
Schedule finish | 2027-02-11
Total working days | 29
Total frames | 672 @ 12 fps
Activities | 8 + 2 milestones
Objects linked to activities | 2981
Keyframes retimed / preserved | 19769 (100% preserved)
Issued | 2026-10-27

## Schedule
Baseline Schedule MEYD-BL-001
5-day work week, no holidays; frame mapping is piecewise-linear per phase
Activity ID | Activity Name | Phase | Start | Finish | Duration (wd) | Predecessors | Old Frames | New Frames
A1010 | Existing + Investigation | 01 | 2027-01-04 | 2027-01-06 | 3 |  | 1-84 | 1.0-70.5
A1020 | Staging + Fixture Removal | 02 | 2027-01-07 | 2027-01-08 | 2 | A1010 | 85-168 | 70.5-116.9
A1030 | Demolition + Excavation | 03 | 2027-01-11 | 2027-01-15 | 5 | A1020 | 169-252 | 116.9-232.7
A1040 | New ABS Installation | 04 | 2027-01-18 | 2027-01-27 | 8 | A1030 | 253-336 | 232.7-418.1
A1050 | Water Test | 05 | 2027-01-28 | 2027-01-29 | 2 | A1040 | 337-420 | 418.1-464.4
A1060 | Backfill + Slab Pourback | 06 | 2027-02-01 | 2027-02-04 | 4 | A1050 | 421-504 | 464.4-557.1
A1070 | Patching + Finishes | 07 | 2027-02-05 | 2027-02-09 | 3 | A1060 | 505-588 | 557.1-626.7
A1080 | Fixture Reinstall + As-Built | 08 | 2027-02-10 | 2027-02-11 | 2 | A1070 | 589-672 | 626.7-673.0
Milestones
ID | Name | Date | Frame
M100 | Notice to Proceed | 2027-01-04 | 1
M900 | Substantial Completion | 2027-02-11 | 672

## Frame_Map
Old → New Phase Frame Boundaries
Phase | Old Start | Old End | New Start | New End | Compression
01 | 1 | 84 | 1 | 70.5 | 0.837
02 | 85 | 168 | 70.5 | 116.9 | 0.559
03 | 169 | 252 | 116.9 | 232.7 | 1.395
04 | 253 | 336 | 232.7 | 418.1 | 2.234
05 | 337 | 420 | 418.1 | 464.4 | 0.558
06 | 421 | 504 | 464.4 | 557.1 | 1.117
07 | 505 | 588 | 557.1 | 626.7 | 0.839
08 | 589 | 672 | 626.7 | 673 | 0.558