## Summary
Meydenbauer VDC — Phase 5 Field Installation Package
Field-ready installation data extracted from the Phase 4 model at final state
Revision | VDC-P5-001
New pipe install routes | 30
Penetration sleeves | 1
Hydro-test routes | 47
Field verification items | 75
Units | B101, B102, B103, B104
Coordinates | Model units = feet, Z-up; layout XY from project origin
Issued | 2026-10-27

## Installation
New Pipe Installation Schedule
Layout coordinates and inverts per route; flagged rows have open issues
Element ID | Name | Unit | Dia (in) | Length (ft) | Start X | Start Y | End X | End Y | Invert Start (ft) | Invert End (ft) | Slope (in/ft) | Slope Status | Activity | Window | Issues
PLM-B101-NEW-PIPE-0001 | NEW_ABS_B101_2in_lav_n | B101 | 2 | 11.92 | 14.766 | 0.887 | 23.248 | 4.813 | -3.318 | -3.566 | 0.319 | DEVIATES_FROM_DOCUMENTED | A1040 | 2027-01-18 → 2027-01-27 | VDC-P2-004
PLM-B101-NEW-PIPE-0002 | NEW_ABS_B101_2in_lav_s | B101 | 2 | 3.462 | 20.735 | 14.267 | 23.248 | 16.647 | -3.248 | -3.32 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B101-NEW-PIPE-0003 | NEW_ABS_B101_3in_bath_n | B101 | 3 | 5.09 | 18.222 | 11.093 | 23.248 | 11.887 | -3.355 | -3.461 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B101-NEW-PIPE-0004 | NEW_ABS_B101_3in_bath_s | B101 | 3 | 4.161 | 19.164 | 15.853 | 23.248 | 16.647 | -3.275 | -3.361 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B101-NEW-PIPE-0005 | NEW_ABS_B101_3in_laundry | B101 | 3 | 1.02 | 22.306 | 28.108 | 23.248 | 27.72 | -3.11 | -3.131 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B101-NEW-PIPE-0006 | NEW_ABS_B101_4in_MAIN | B101 | 4 | 45.432 | 36.907 | 38.982 | 23.248 | 0 | -2.804 | -3.75 | 0.275 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B101-NEW-PIPE-0007 | NEW_ABS_B101_6in_LATERAL_18IN_LIMIT | B101 | 6 | 1.5 | 23.248 | 0 | 23.248 | -1.5 | -3.833 | -3.865 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B102-NEW-PIPE-0001 | NEW_ABS_B102_2in_lav_n | B102 | 2 | 7.266 | 62.979 | 0.95 | 69.208 | 4.687 | -3.372 | -3.523 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B102-NEW-PIPE-0002 | NEW_ABS_B102_2in_lav_s | B102 | 2 | 6.494 | 61.625 | 15.853 | 67.583 | 18.432 | -3.099 | -3.235 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B102-NEW-PIPE-0003 | NEW_ABS_B102_3in_bath_n | B102 | 3 | 4.756 | 63.792 | 11.887 | 68.396 | 13.077 | -3.29 | -3.389 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B102-NEW-PIPE-0004 | NEW_ABS_B102_3in_bath_s | B102 | 3 | 5.128 | 62.708 | 16.845 | 67.583 | 18.432 | -3.17 | -3.276 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B102-NEW-PIPE-0005 | NEW_ABS_B102_3in_kitchen | B102 | 3 | 1.333 | 50.25 | 40.147 | 51.333 | 39.37 | -2.672 | -2.7 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B102-NEW-PIPE-0006 | NEW_ABS_B102_3in_laundry | B102 | 3 | 1.151 | 64.333 | 27.72 | 65.417 | 27.332 | -3.062 | -3.086 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B102-NEW-PIPE-0007 | NEW_ABS_B102_4in_MAIN | B102 | 4 | 48.434 | 51.333 | 39.37 | 74.26 | 0 | -2.741 | -3.75 | 0.266 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B102-NEW-PIPE-0008 | NEW_ABS_B102_6in_LATERAL_18IN_LIMIT | B102 | 6 | 1.5 | 74.26 | 0 | 74.26 | -1.5 | -3.833 | -3.865 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B103-NEW-PIPE-0001 | NEW_ABS_B103_2in_lav_n | B103 | 2 | 6.506 | 94.987 | 0.95 | 89.754 | 4.813 | -3.431 | -3.566 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B103-NEW-PIPE-0002 | NEW_ABS_B103_2in_lav_s | B103 | 2 | 9.131 | 98.567 | 15.06 | 89.754 | 17.44 | -3.113 | -3.303 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B103-NEW-PIPE-0003 | NEW_ABS_B103_3in_bath_n | B103 | 3 | 5.799 | 95.538 | 11.887 | 89.754 | 12.283 | -3.332 | -3.452 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B103-NEW-PIPE-0004 | NEW_ABS_B103_3in_bath_s | B103 | 3 | 7.754 | 97.466 | 16.647 | 89.754 | 17.44 | -3.183 | -3.345 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B103-NEW-PIPE-0005 | NEW_ABS_B103_3in_laundry | B103 | 3 | 0.337 | 99.945 | 27.72 | 99.669 | 27.526 | -3.043 | -3.05 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B103-NEW-PIPE-0006 | NEW_ABS_B103_4in_MAIN | B103 | 4 | 31.59 | 99.669 | 27.526 | 89.754 | 0 | -3.092 | -3.75 | 0.27 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B103-NEW-PIPE-0007 | NEW_ABS_B103_4in_RAISED_FLOOR | B103 | 4 | 30.683 | 106.83 | 40.147 | 123.392 | 28.108 | 0.25 | -1.833 | 1.221 | NOT_DOCUMENTED | A1040 | 2027-01-18 → 2027-01-27 | VDC-P2-005
PLM-B103-NEW-PIPE-0008 | NEW_ABS_B103_6in_LATERAL_18IN_LIMIT | B103 | 6 | 1.5 | 89.754 | 0 | 89.754 | -1.5 | -3.833 | -3.865 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B104-NEW-PIPE-0001 | NEW_ABS_B104_2in_lav_n | B104 | 2 | 5.185 | 142.237 | 0.95 | 138.781 | 4.813 | -3.458 | -3.566 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B104-NEW-PIPE-0002 | NEW_ABS_B104_2in_lav_s | B104 | 2 | 3.614 | 135.639 | 15.457 | 138.781 | 17.242 | -3.232 | -3.308 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B104-NEW-PIPE-0003 | NEW_ABS_B104_3in_bath_n | B104 | 3 | 3.479 | 142.237 | 11.887 | 138.781 | 12.283 | -3.38 | -3.452 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B104-NEW-PIPE-0004 | NEW_ABS_B104_3in_bath_s | B104 | 3 | 2.279 | 140.98 | 16.647 | 138.781 | 17.242 | -3.302 | -3.349 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B104-NEW-PIPE-0005 | NEW_ABS_B104_3in_laundry | B104 | 3 | 10.131 | 128.652 | 27.72 | 138.781 | 27.72 | -2.92 | -3.131 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B104-NEW-PIPE-0006 | NEW_ABS_B104_4in_MAIN | B104 | 4 | 43.513 | 128.132 | 39.37 | 138.781 | 0 | -2.844 | -3.75 | 0.267 | PASS | A1040 | 2027-01-18 → 2027-01-27
PLM-B104-NEW-PIPE-0007 | NEW_ABS_B104_6in_LATERAL_18IN_LIMIT | B104 | 6 | 1.5 | 138.781 | 0 | 138.781 | -1.5 | -3.833 | -3.865 | 0.25 | PASS | A1040 | 2027-01-18 → 2027-01-27

## Penetrations
Penetration & Sleeve Schedule
Designed penetrations with layout coordinates
Element ID | Name | Unit | Layout X (ft) | Layout Y (ft) | Bore Dia (in) | Serves Element | Ext Above (in) | Ext Below (in) | Activity | Verification
PLM-B103-NEW-SLEEVE-0001 | SLEEVE_B103_SOG_Penetration_001 | B103 | 0 | 0 | 7.2 | PLM-B103-NEW-PIPE-0007 | 2 | 3 | A1040 | FIELD_VERIFY_REQUIRED

## Hydrotest
Hydro-Test Package
Routes included in the water test (Phase 05)
Element ID | Name | Unit | Length (ft) | Activity | Window | Verification
PLM-B101-TST-TST-0001 | HYDRO_NEW_ABS_B101_2in_lav_n | B101 | 11.92 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B101-TST-TST-0002 | HYDRO_NEW_ABS_B101_2in_lav_s | B101 | 3.462 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B101-TST-TST-0003 | HYDRO_NEW_ABS_B101_3in_bath_n | B101 | 5.09 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B101-TST-TST-0004 | HYDRO_NEW_ABS_B101_3in_bath_s | B101 | 4.161 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B101-TST-TST-0005 | HYDRO_NEW_ABS_B101_3in_laundry | B101 | 1.02 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B101-TST-TST-0006 | HYDRO_NEW_ABS_B101_4in_MAIN | B101 | 45.432 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B101-TST-TST-0007 | HYDRO_NEW_ABS_B101_6in_LATERAL_18IN_LIMIT | B101 | 1.5 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B102-TST-TST-0001 | HYDRO_NEW_ABS_B102_2in_lav_n | B102 | 7.266 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B102-TST-TST-0002 | HYDRO_NEW_ABS_B102_2in_lav_s | B102 | 6.494 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B102-TST-TST-0003 | HYDRO_NEW_ABS_B102_3in_bath_n | B102 | 4.756 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B102-TST-TST-0004 | HYDRO_NEW_ABS_B102_3in_bath_s | B102 | 5.128 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B102-TST-TST-0005 | HYDRO_NEW_ABS_B102_3in_kitchen | B102 | 1.333 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B102-TST-TST-0006 | HYDRO_NEW_ABS_B102_3in_laundry | B102 | 1.151 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B102-TST-TST-0007 | HYDRO_NEW_ABS_B102_4in_MAIN | B102 | 48.434 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B102-TST-TST-0008 | HYDRO_NEW_ABS_B102_6in_LATERAL_18IN_LIMIT | B102 | 1.5 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B103-TST-TST-0001 | HYDRO_NEW_ABS_B103_2in_lav_n | B103 | 6.506 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B103-TST-TST-0002 | HYDRO_NEW_ABS_B103_2in_lav_s | B103 | 9.131 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B103-TST-TST-0003 | HYDRO_NEW_ABS_B103_3in_bath_n | B103 | 5.799 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B103-TST-TST-0004 | HYDRO_NEW_ABS_B103_3in_bath_s | B103 | 7.754 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B103-TST-TST-0005 | HYDRO_NEW_ABS_B103_3in_laundry | B103 | 0.337 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B103-TST-TST-0006 | HYDRO_NEW_ABS_B103_4in_MAIN | B103 | 31.59 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B103-TST-TST-0007 | HYDRO_NEW_ABS_B103_4in_RAISED_FLOOR | B103 | 30.683 | A1050 | 2027-01-28 → 2027-01-29 | FIELD_VERIFY_REQUIRED
PLM-B103-TST-TST-0008 | HYDRO_NEW_ABS_B103_6in_LATERAL_18IN_LIMIT | B103 | 1.5 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B104-TST-TST-0001 | HYDRO_NEW_ABS_B104_2in_lav_n | B104 | 5.185 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B104-TST-TST-0002 | HYDRO_NEW_ABS_B104_2in_lav_s | B104 | 3.614 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B104-TST-TST-0003 | HYDRO_NEW_ABS_B104_3in_bath_n | B104 | 3.479 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B104-TST-TST-0004 | HYDRO_NEW_ABS_B104_3in_bath_s | B104 | 2.279 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B104-TST-TST-0005 | HYDRO_NEW_ABS_B104_3in_laundry | B104 | 10.131 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B104-TST-TST-0006 | HYDRO_NEW_ABS_B104_4in_MAIN | B104 | 43.513 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B104-TST-TST-0007 | HYDRO_NEW_ABS_B104_6in_LATERAL_18IN_LIMIT | B104 | 1.5 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B101-TST-TST-0008 | HYDRO_PTRAP_B101_laundry | B101 | 1.289 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B101-TST-TST-0009 | HYDRO_PTRAP_B101_lav_n | B101 | 1.289 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B101-TST-TST-0010 | HYDRO_PTRAP_B101_lav_s | B101 | 1.289 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B102-TST-TST-0009 | HYDRO_PTRAP_B102_kitchen | B102 | 1.289 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B102-TST-TST-0010 | HYDRO_PTRAP_B102_laundry | B102 | 1.289 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B102-TST-TST-0011 | HYDRO_PTRAP_B102_lav_n | B102 | 1.289 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B102-TST-TST-0012 | HYDRO_PTRAP_B102_lav_s | B102 | 1.289 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B103-TST-TST-0009 | HYDRO_PTRAP_B103_laundry | B103 | 1.289 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B103-TST-TST-0010 | HYDRO_PTRAP_B103_lav_n | B103 | 1.289 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B103-TST-TST-0011 | HYDRO_PTRAP_B103_lav_s | B103 | 1.289 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B104-TST-TST-0008 | HYDRO_PTRAP_B104_laundry | B104 | 1.289 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B104-TST-TST-0009 | HYDRO_PTRAP_B104_lav_n | B104 | 1.289 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B104-TST-TST-0010 | HYDRO_PTRAP_B104_lav_s | B104 | 1.289 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B101-TST-TST-0011 | HYDRO_TracerWire_B101 | B101 | 1.5 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B102-TST-TST-0013 | HYDRO_TracerWire_B102 | B102 | 1.5 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B103-TST-TST-0012 | HYDRO_TracerWire_B103 | B103 | 1.5 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED
PLM-B104-TST-TST-0011 | HYDRO_TracerWire_B104 | B104 | 1.5 | A1050 | 2027-01-28 → 2027-01-29 | DOCUMENT_DERIVED

## Field_Checklist
Field Verification Checklist
Elements requiring field verification or with open issues — check off before covering work
Element ID | Name | Unit | Component | Check Required | Issues | Activity
PLM-B101-DEM-PIPE-0001 | EX_CI_B101_BR2_lav_n | B101 | PIPE_ROUTE | field-verify dimensions/location; resolve issue VDC-P2-002 | VDC-P2-002 | A1030
PLM-B101-DEM-PIPE-0002 | EX_CI_B101_BR2_lav_s | B101 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B101-DEM-PIPE-0003 | EX_CI_B101_BR3_bath_n | B101 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B101-DEM-PIPE-0004 | EX_CI_B101_BR3_bath_s | B101 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B101-DEM-PIPE-0005 | EX_CI_B101_BR3_laundry | B101 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B101-DEM-PIPE-0006 | EX_CI_B101_LAT6_REPLACE | B101 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B101-DEM-PIPE-0007 | EX_CI_B101_MAIN4 | B101 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B102-DEM-PIPE-0001 | EX_CI_B102_BR2_lav_n | B102 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B102-DEM-PIPE-0002 | EX_CI_B102_BR2_lav_s | B102 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B102-DEM-PIPE-0003 | EX_CI_B102_BR3_bath_n | B102 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B102-DEM-PIPE-0004 | EX_CI_B102_BR3_bath_s | B102 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B102-DEM-PIPE-0005 | EX_CI_B102_BR3_kitchen | B102 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B102-DEM-PIPE-0006 | EX_CI_B102_BR3_laundry | B102 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B102-DEM-PIPE-0007 | EX_CI_B102_LAT6_REPLACE | B102 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B102-DEM-PIPE-0008 | EX_CI_B102_MAIN4 | B102 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B103-DEM-PIPE-0001 | EX_CI_B103_BR2_lav_n | B103 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B103-DEM-PIPE-0002 | EX_CI_B103_BR2_lav_s | B103 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B103-DEM-PIPE-0003 | EX_CI_B103_BR3_bath_n | B103 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B103-DEM-PIPE-0004 | EX_CI_B103_BR3_bath_s | B103 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B103-DEM-PIPE-0005 | EX_CI_B103_BR3_laundry | B103 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B103-DEM-PIPE-0006 | EX_CI_B103_LAT6_REPLACE | B103 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B103-DEM-PIPE-0007 | EX_CI_B103_MAIN4 | B103 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B104-DEM-PIPE-0001 | EX_CI_B104_BR2_lav_n | B104 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B104-DEM-PIPE-0002 | EX_CI_B104_BR2_lav_s | B104 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B104-DEM-PIPE-0003 | EX_CI_B104_BR3_bath_n | B104 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B104-DEM-PIPE-0004 | EX_CI_B104_BR3_bath_s | B104 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B104-DEM-PIPE-0005 | EX_CI_B104_BR3_laundry | B104 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B104-DEM-PIPE-0006 | EX_CI_B104_LAT6_REPLACE | B104 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
PLM-B104-DEM-PIPE-0007 | EX_CI_B104_MAIN4 | B104 | PIPE_ROUTE | field-verify dimensions/location |  | A1030
CIV-SITE-EXG-PIPE-0001 | EX_Side_Sewer_Main_8in | SITE | PIPE_ROUTE | resolve issue VDC-P2-003 | VDC-P2-003 | A1010
PLM-B103-TST-TST-0007 | HYDRO_NEW_ABS_B103_4in_RAISED_FLOOR | B103 | HYDRO_TEST_ROUTE | field-verify dimensions/location |  | A1050
PLM-B101-NEW-PIPE-0001 | NEW_ABS_B101_2in_lav_n | B101 | PIPE_ROUTE | resolve issue VDC-P2-004 | VDC-P2-004 | A1040
PLM-B103-NEW-PIPE-0007 | NEW_ABS_B103_4in_RAISED_FLOOR | B103 | PIPE_ROUTE | field-verify dimensions/location; resolve issue VDC-P2-005 | VDC-P2-005 | A1040
PLM-B103-NEW-SLEEVE-0001 | SLEEVE_B103_SOG_Penetration_001 | B103 | PIPE_SLEEVE | field-verify dimensions/location |  | A1040
CON-B101-DEM-CUT-0001 | TrenchCutter_B101_001 | B101 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B101-DEM-CUT-0002 | TrenchCutter_B101_002 | B101 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B101-DEM-CUT-0003 | TrenchCutter_B101_003 | B101 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B101-DEM-CUT-0004 | TrenchCutter_B101_004 | B101 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B101-DEM-CUT-0005 | TrenchCutter_B101_005 | B101 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B101-DEM-CUT-0006 | TrenchCutter_B101_006 | B101 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B101-DEM-CUT-0007 | TrenchCutter_B101_007 | B101 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B101-DEM-CUT-0008 | TrenchCutter_B101_008 | B101 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B101-DEM-CUT-0009 | TrenchCutter_B101_009 | B101 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B101-DEM-CUT-0010 | TrenchCutter_B101_010 | B101 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B101-DEM-CUT-0011 | TrenchCutter_B101_011 | B101 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B102-DEM-CUT-0001 | TrenchCutter_B102_012 | B102 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B102-DEM-CUT-0002 | TrenchCutter_B102_013 | B102 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B102-DEM-CUT-0003 | TrenchCutter_B102_014 | B102 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B102-DEM-CUT-0004 | TrenchCutter_B102_015 | B102 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B102-DEM-CUT-0005 | TrenchCutter_B102_016 | B102 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B102-DEM-CUT-0006 | TrenchCutter_B102_017 | B102 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B102-DEM-CUT-0007 | TrenchCutter_B102_018 | B102 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B102-DEM-CUT-0008 | TrenchCutter_B102_019 | B102 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B102-DEM-CUT-0009 | TrenchCutter_B102_020 | B102 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B102-DEM-CUT-0010 | TrenchCutter_B102_021 | B102 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B102-DEM-CUT-0011 | TrenchCutter_B102_022 | B102 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B103-DEM-CUT-0001 | TrenchCutter_B103_023 | B103 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B103-DEM-CUT-0002 | TrenchCutter_B103_024 | B103 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B103-DEM-CUT-0003 | TrenchCutter_B103_025 | B103 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B103-DEM-CUT-0004 | TrenchCutter_B103_026 | B103 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B103-DEM-CUT-0005 | TrenchCutter_B103_027 | B103 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B103-DEM-CUT-0006 | TrenchCutter_B103_028 | B103 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B103-DEM-CUT-0007 | TrenchCutter_B103_029 | B103 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B103-DEM-CUT-0008 | TrenchCutter_B103_030 | B103 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B103-DEM-CUT-0009 | TrenchCutter_B103_031 | B103 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B104-DEM-CUT-0001 | TrenchCutter_B104_032 | B104 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B104-DEM-CUT-0002 | TrenchCutter_B104_033 | B104 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B104-DEM-CUT-0003 | TrenchCutter_B104_034 | B104 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B104-DEM-CUT-0004 | TrenchCutter_B104_035 | B104 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B104-DEM-CUT-0005 | TrenchCutter_B104_036 | B104 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B104-DEM-CUT-0006 | TrenchCutter_B104_037 | B104 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B104-DEM-CUT-0007 | TrenchCutter_B104_038 | B104 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B104-DEM-CUT-0008 | TrenchCutter_B104_039 | B104 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B104-DEM-CUT-0009 | TrenchCutter_B104_040 | B104 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030
CON-B104-DEM-CUT-0010 | TrenchCutter_B104_041 | B104 | SLAB_CUT_AREA | field-verify dimensions/location |  | A1030